## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of ground water based Andharkota PWSS to accommodate FHTC in Karimpur-I Block within Nadia District under Nadia Division | SM/10075 | Augmentation | Augmentation of ground water based Andharkota PWSS to accommodate FHTC in Karimpur-I Block within Nadia District under Nadia Division |  |  | VCH/001104/2021-2022 | 674/PFMS | 24/03/2022 | 24/03/2022 | RADIANT | 2.82 | 0 | 0 | 0
2 | NADIA |  | Central Drilling | Augmentation of ground water based Andharkota PWSS to accommodate FHTC in Karimpur-I Block within Nadia District under Nadia Division | SM/10075 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (300mm x 200mm x 250 Mtrs. Depth) by utilising Departmental Machineries for Andharkota W/S Scheme (T/W-I) Karimpur -I Block under nadia District, CDD PHE Dte. | Driller In Charge | Junior Engineer | ORD/000054/2023-2024 | 508/CDD | 01/06/2023 | 01/07/2023 | UNIVERSAL ENTERPRISES | 18.86 | 12.77 | 67.68 | 100
3 | NADIA |  | Nadia Division | Augmentation of ground water based Andharkota PWSS to accommodate FHTC in Karimpur-I Block within Nadia District under Nadia Division | SM/10075 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000039/2023-2024 | 1907/ND | 27/04/2023 | 27/04/2023 | Resource Division | 67.35 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Augmentation of ground water based Andharkota PWSS to accommodate FHTC in Karimpur-I Block within Nadia District under Nadia Division | SM/10075 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000059/2023-2024 | 2291/ND | 29/05/2023 | 29/05/2023 | Resource Division | 27.26 | 0 | 0 | 0
5 | NADIA |  | Eastern Mechanical | Augmentation of ground water based Andharkota PWSS to accommodate FHTC in Karimpur-I Block within Nadia District under Nadia Division | SM/10075 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under MAHISBATHAN W/S Scheme, Block- Karimpur-II & ANDHARKOTA W/S Scheme, Block- Karimpur-I, Dist. - Nadia. NIET No.- 33 of EE/EMD of 2022-23 (Sl. No.- 01) | Assistant Engineer | Junior Engineer | ORD/001928/2022-2023 | 1200/EMD | 22/03/2023 | 21/04/2023 | KARTICK BAL | 61.1 | 26.46 | 43.31 | 70
6 | NADIA |  | Eastern Mechanical | Augmentation of ground water based Andharkota PWSS to accommodate FHTC in Karimpur-I Block within Nadia District under Nadia Division | SM/10075 | Augmentation | Quotation charges and security deposit for new power connection at Andharkota PH-III under Eastern Mechanical Subdivision-III, Nadia |  |  | BILL/02246/2024-2025 | BP-175 | 13/12/2024 | 13/12/2024 | WBSEDCL KARIMPUR CCC | 14.8 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | Augmentation of ground water based Andharkota PWSS to accommodate FHTC in Karimpur-I Block within Nadia District under Nadia Division | SM/10075 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc., Construction Of 300 Cum Capacity 20 Mtr. Staging Height Rcc Over Head Reservoir (Excluding Pile Foundation), Pipe Connection And Cost Of Pipes, Specials & Soil Investigation all complete for Augmentation of Ground Based Water Supply Scheme at Andharkota to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000187/2022-2023 | 4466/ND | 18/10/2022 | 17/10/2026 | M/S S.S ENTERPRISE | 444.3 | 207.11 | 46.62 | 55
8 | NADIA |  | Nadia Division | Augmentation of ground water based Andharkota PWSS to accommodate FHTC in Karimpur-I Block within Nadia District under Nadia Division | SM/10075 | Augmentation | Construction of Arsenic-cum-Iron Removal Plant (AIRP) of 56.13 cum/Hour capacity at proposed headwork site for Augmentation of Ground Based Water Supply Scheme at Andharkota to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer |  | ORD/000156/2024-2025 | 4480/ND | 14/08/2024 | 10/02/2025 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 189.2 | 0 | 0 | 0
9 | NADIA |  | Nadia Division | Augmentation of ground water based Andharkota PWSS to accommodate FHTC in Karimpur-I Block within Nadia District under Nadia Division | SM/10075 | Augmentation | Repairing and renovation of Elevated Reservoir , Pump House and allied works of ground based piped water supply scheme for Andherkota water supply scheme under Tehatta Sub Division in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000395/2024-2025 | 7122/ND | 09/12/2024 | 04/03/2026 | GHOSH CONSTRUCTION | 31.29 | 0 | 0 | 70
10 | NADIA |  | Nadia Division | Augmentation of ground water based Andharkota PWSS to accommodate FHTC in Karimpur-I Block within Nadia District under Nadia Division | SM/10075 | Augmentation | Construction Of Pump House (5.4m X 3.6m) Including Sanitary Arrangement and consruction of Boundary wall at Head Work Site of Andherkota Water Supply Scheme Under Tehatta Sub-Division PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000739/2023-2024 | 1507/ND | 04/03/2024 | 27/02/2025 | SADHANA CONSTRUCTION | 23.05 | 0 | 0 | 100
11 | NADIA |  | Nadia Division | Augmentation of ground water based Andharkota PWSS to accommodate FHTC in Karimpur-I Block within Nadia District under Nadia Division | SM/10075 | Augmentation | Detail route survey, design of distribution network and preparation of estimate, drawing & dpr for providing FHTC in Arabpur, Betai Zone II, Nathna Zone II, Andherkota, Karimpur Jalangi Zone VII W/S Scheme | Assistant Engineer | Junior Engineer 2 | ORD/000016/2025-2026 | 1802/ND | 22/04/2025 | 13/05/2025 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 11.11 | 0 | 0 | 100
12 | NADIA |  | Nadia Division | Augmentation of ground water based Andharkota PWSS to accommodate FHTC in Karimpur-I Block within Nadia District under Nadia Division | SM/10075 | Augmentation | Construction of Arsenic-cum-Iron Removal Plant (AIRP) of 47.81 cum/Hour capacity at existing headwork site for Augmentation of Ground Based Water Supply Scheme at Andharkota to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000113/2024-2025 | 4368/ND | 09/08/2024 | 31/01/2026 | CARBON SERVICES INDIA | 178.59 | 0 | 0 | 0
Total | [13 empty] | 1069.72 | 246.34 | 23.03