## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground Water Based MAHISBATHAN Piped Water Supply Scheme for Block: Karimpur-II, Dist: Nadia | SM/10076 | Augmentation | Augmentation of Ground Water Based MAHISBATHAN Piped Water Supply Scheme for Block: Karimpur-II, Dist: Nadia |  |  | VCH/001103/2021-2022 | 673/PFMS | 24/03/2022 | 24/03/2022 | RADIANT | 2.79 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Augmentation of Ground Water Based MAHISBATHAN Piped Water Supply Scheme for Block: Karimpur-II, Dist: Nadia | SM/10076 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000147/2021-2022 | 1397/ND | 24/03/2022 | 24/03/2022 | Resource Division | 31.75 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Augmentation of Ground Water Based MAHISBATHAN Piped Water Supply Scheme for Block: Karimpur-II, Dist: Nadia | SM/10076 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000188/2022-2023 | 149/ND | 06/01/2023 | 06/01/2023 | Resource Division | 43.07 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Augmentation of Ground Water Based MAHISBATHAN Piped Water Supply Scheme for Block: Karimpur-II, Dist: Nadia | SM/10076 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000044/2023-2024 | 1904/ND | 27/04/2023 | 27/04/2023 | Resource Division | 57.16 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Augmentation of Ground Water Based MAHISBATHAN Piped Water Supply Scheme for Block: Karimpur-II, Dist: Nadia | SM/10076 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000111/2023-2024 | 4221/ND | 19/09/2023 | 19/09/2023 | Resource Division | 42 | 0 | 0 | 0
6 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based MAHISBATHAN Piped Water Supply Scheme for Block: Karimpur-II, Dist: Nadia | SM/10076 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under MAHISBATHAN W/S Scheme, Block- Karimpur-II & ANDHARKOTA W/S Scheme, Block- Karimpur-I, Dist. - Nadia. NIET No.- 33 of EE/EMD of 2022-23 (Sl. No.- 01) | Assistant Engineer | Junior Engineer | ORD/001928/2022-2023 | 1200/EMD | 22/03/2023 | 21/04/2023 | KARTICK BAL | 61.1 | 0 | 0 | 70
7 | NADIA |  | Nadia Division | Augmentation of Ground Water Based MAHISBATHAN Piped Water Supply Scheme for Block: Karimpur-II, Dist: Nadia | SM/10076 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 30/01/2024 | IMAGIN | 96.97 | 0 | 0 | 40
8 | NADIA |  | Nadia Division | Augmentation of Ground Water Based MAHISBATHAN Piped Water Supply Scheme for Block: Karimpur-II, Dist: Nadia | SM/10076 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete And Construction of 550 cum capacity 20 Mtr. staging height RCC Over Head Reservoir, pipe connection and cost of pipes, specials and Soil Investigation for Construction of 550 CUM OHR for Augmentation of Ground Based Water Supply Scheme at Mahisbathan to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000194/2023-2024 | 3449/ND | 09/08/2023 | 09/08/2025 | M/S DIPAK ENTERPRISE, GHOSH PARA,WARD NO-4, KALYANI, NADIA-741235 WEST BENGAL | 560.56 | 0 | 0 | 55
9 | NADIA |  | Nadia Division | Augmentation of Ground Water Based MAHISBATHAN Piped Water Supply Scheme for Block: Karimpur-II, Dist: Nadia | SM/10076 | Augmentation | Construction Of Pump House (5.4m X 3.6m) Including Sanitary Arrangemen At Hw Site At Mahisbathan Water Supply Scheme Under Kalyani Sub Division I PHE Dte) | Assistant Engineer | Junior Engineer 1 | ORD/000121/2024-2025 | 4531/ND | 20/08/2024 | 16/02/2025 | M/S BISWAS ENTERPRISE | 6.96 | 0 | 0 | 0
10 | NADIA |  | Nadia Division | Augmentation of Ground Water Based MAHISBATHAN Piped Water Supply Scheme for Block: Karimpur-II, Dist: Nadia | SM/10076 | Augmentation | Construction of boundary wall and repairing of pump house cum chlorin room at head work site,2nd tubewell site and alide work under Mahisbathan PWSS kalyani sub division-I under Nadia Division PHE Dte. |  |  | ORD/000836/2024-2025 | 280/ND | 16/01/2025 | 16/04/2025 | ZOOM CONSTRUCTION & INTERIO | 45.1 | 0 | 0 | 0
11 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based MAHISBATHAN Piped Water Supply Scheme for Block: Karimpur-II, Dist: Nadia | SM/10076 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Mahishbathan ground water based water supply scheme under Block_ Karimpur-II Dist. - Nadia under EMD, PHE Dte. SM/10076 | Assistant Engineer |  | ORD/000174/2025-2026 | 1107/EMD | 04/06/2025 | 02/09/2025 | S.P CONSTRUCTION | 20.8 | 0 | 0 | 0
Total | [13 empty] | 968.26 | 0 | 0