## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of ground water based Narayanpur PWSS to accommodate FHTC in Karimpur-II Block within Nadia District under Nadia Division | SM/10077 | Augmentation | Augmentation of ground water based Narayanpur PWSS to accommodate FHTC in Karimpur-II Block within Nadia District under Nadia Division |  |  | VCH/001101/2021-2022 | 671/PFMS | 24/03/2022 | 24/03/2022 | RADIANT | 3.13 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Augmentation of ground water based Narayanpur PWSS to accommodate FHTC in Karimpur-II Block within Nadia District under Nadia Division | SM/10077 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000085/2023-2024 | 2287/ND | 29/05/2023 | 29/05/2023 | Resource Division | 21 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Augmentation of ground water based Narayanpur PWSS to accommodate FHTC in Karimpur-II Block within Nadia District under Nadia Division | SM/10077 | Augmentation | Collection of Household data through mobile app for FHTC Connection at following schemes under Nadia Division PHE Dte.Schemes: i) Narayanpur ii) Palsunda iii) Dogachhi Zone-II iv)Dogachhi Zone-I | Assistant Engineer | Junior Engineer 2 | ORD/000067/2023-2024 | 679/KlySD-I | 31/05/2023 | 06/06/2023 | TECHVISION | 4.79 | 4.79 | 100 | 100
4 | NADIA |  | Nadia Division | Augmentation of ground water based Narayanpur PWSS to accommodate FHTC in Karimpur-II Block within Nadia District under Nadia Division | SM/10077 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed Augmentation of Rising Main system, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete, Construction of 200 Cum Capacity 20 Mtr. height RCC Over Head Reservoir (Excluding Pile Foundation), Pipe Connection and Cost of Pipes, Specials and Soil Investigation for construction of one no. 200 Cum OHR of Staging Height 20 Mtr. for Augmentation of Ground Based Water Supply Scheme at Narayanpur to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000437/2022-2023 | 966/ND | 09/03/2023 | 09/03/2026 | M/S S.S ENTERPRISE | 759.95 | 45.4 | 5.97 | 55
Total | [13 empty] | 788.87 | 50.19 | 6.36