## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BHANDAR KHOLA in Krishnagar I Block with in , Nadia district under Nadia Division | SM/10079 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Bhanderkhola to accommodate FHTC within Krishnagar-I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000017/2022-2023 | 2079/ND | 11/05/2022 | 09/08/2022 | M/S GHOSH CONSTRUCTION | 180.3 | 176.2 | 97.73 | 100
2 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BHANDAR KHOLA in Krishnagar I Block with in , Nadia district under Nadia Division | SM/10079 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000006/2022-2023 | 2163/ND | 18/05/2022 | 18/05/2022 | Resource Division | 76.79 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BHANDAR KHOLA in Krishnagar I Block with in , Nadia district under Nadia Division | SM/10079 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000010/2022-2023 | 3235/ND | 21/07/2022 | 21/07/2022 | Resource Division | 1.26 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BHANDAR KHOLA in Krishnagar I Block with in , Nadia district under Nadia Division | SM/10079 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000013/2022-2023 | 3304/ND | 27/07/2022 | 27/07/2022 | Resource Division | 10.78 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BHANDAR KHOLA in Krishnagar I Block with in , Nadia district under Nadia Division | SM/10079 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for BHANDAR KHOLA in Krishnagar I Block with in , Nadia district under Nadia Division |  |  | VCH/001075/2021-2022 | 638/PFMS | 16/03/2022 | 16/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.23 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BHANDAR KHOLA in Krishnagar I Block with in , Nadia district under Nadia Division | SM/10079 | Augmentation | Renovation of AIRP (Gravity Type) of capacity 58 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Bhanderkhola PWSS under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 1,Junior Engineer 3 | ORD/000084/2023-2024 | 2997/ND | 13/07/2023 | 30/09/2025 | TARUN KUMAR BHATTACHARYA | 87.75 | 44.39 | 50.59 | 68
7 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BHANDAR KHOLA in Krishnagar I Block with in , Nadia district under Nadia Division | SM/10079 | Augmentation | Repair and renovation works of R.C.C. Elevated Reservoir 250 cum, Repair & Renovation of Pump House, Boundary wall and allied works at 1st and 2nd Pump House at Bhanderkhola Water Supply Scheme within Krishnagar I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000394/2023-2024 | 5126/ND | 17/11/2023 | 15/02/2024 | ONKAR ENTERPRISE | 24.91 | 0 | 0 | 100
8 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BHANDAR KHOLA in Krishnagar I Block with in , Nadia district under Nadia Division | SM/10079 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000062/2023-2024 | 2302/ND | 29/05/2023 | 29/05/2023 | Resource Division | 6.23 | 0 | 0 | 0
9 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BHANDAR KHOLA in Krishnagar I Block with in , Nadia district under Nadia Division | SM/10079 | Augmentation | Providig FHTC at leftout household in connection to the Augmentation of Ground Based piped water supply scheme at Bhanderkhola to accommodate FHTC within Krishnagar I block under Krishnanagar Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000720/2023-2024 | 1371/ND | 28/02/2024 | 28/04/2024 | M/S GHOSH CONSTRUCTION | 32.47 | 25.99 | 80.05 | 100
10 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BHANDAR KHOLA in Krishnagar I Block with in , Nadia district under Nadia Division | SM/10079 | Augmentation | Construction and installation of Manifold at OHR site and allied works in connection to the Augmentation of Bhanderkhola Water Supply Scheme under Krishnagar I Block under Nadia Division, P.H.E Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000747/2024-2025 | 494/ND | 30/01/2025 | 26/03/2026 | SANJIB DEY | 27.42 | 0 | 0 | 80
Total | [13 empty] | 451.15 | 246.59 | 54.66