## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing FHTC by augmentation under Jal Swapna for Kulgachi PWSS, in Tehatta-II block with in Nadia district under Nadia Division | SM/10080 | Augmentation | Providing FHTC by augmentation under Jal Swapna for Kulgachi PWSS, in Tehatta-II block with in Nadia district under Nadia Division |  |  | VCH/001138/2021-2022 | 703/PFMS | 30/03/2022 | 30/03/2022 | HORIZEN | 2.45 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing FHTC by augmentation under Jal Swapna for Kulgachi PWSS, in Tehatta-II block with in Nadia district under Nadia Division | SM/10080 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000192/2022-2023 | 362/ND | 24/01/2023 | 24/01/2023 | Resource Division | 0.76 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Providing FHTC by augmentation under Jal Swapna for Kulgachi PWSS, in Tehatta-II block with in Nadia district under Nadia Division | SM/10080 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000078/2023-2024 | 2299/ND | 29/05/2023 | 29/05/2023 | Resource Division | 5.62 | 0 | 0 | 0
4 | NADIA |  | Eastern Mechanical | Providing FHTC by augmentation under Jal Swapna for Kulgachi PWSS, in Tehatta-II block with in Nadia district under Nadia Division | SM/10080 | Augmentation | Supply, Delivery Installation of Submersible Pumping Machinery alongwith allied Electro Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. rejuvenation to Accommodate FHTC at Pump House No. I and II under Kulgachi WS Scheme, Block KrishnagarI, Dist. Nadia. NIET No.- 23 of EE/EMD of 2022-23 (Sl. No.-09) | Assistant Engineer | Junior Engineer | ORD/000890/2022-2023 | 158/EMD | 06/01/2023 | 05/02/2023 | ABHISEK ENGINEERING CONCERN | 16.76 | 0 | 0 | 80
5 | NADIA |  | Nadia Division | Providing FHTC by augmentation under Jal Swapna for Kulgachi PWSS, in Tehatta-II block with in Nadia district under Nadia Division | SM/10080 | Augmentation | Repairing and renovation of Pump House ,boundary wall of ground basaedpiped water supply scheme for Kulgachi water supply scheme under Tehatta Sub Division in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer |  | ORD/000309/2024-2025 | 6837/ND | 12/11/2024 | 10/02/2025 | DAS CONSTRUCTION | 11.4 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | Providing FHTC by augmentation under Jal Swapna for Kulgachi PWSS, in Tehatta-II block with in Nadia district under Nadia Division | SM/10080 | Augmentation | Conversion of IEP to AIRP of capacity 30 Cu.m/hr at Kulgachi Water Supply Scheme within Tehatta-II Block block under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer |  | ORD/000126/2024-2025 | 4575/ND | 21/08/2024 | 17/02/2025 | B.M. ENGINEERING & CONSTRUCTION | 129.23 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | Providing FHTC by augmentation under Jal Swapna for Kulgachi PWSS, in Tehatta-II block with in Nadia district under Nadia Division | SM/10080 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Kulgachi Ground Based Water Supply Scheme under Tehatta-II Block under Nadia Division,P.H.E Dte. in connection with Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Kulgachi at Tehatta-II Block by Augmentation of Ground Water based PWSS for Kulgachi Water Supply Schemes under | Assistant Engineer |  | ORD/000645/2024-2025 | 7369/ND | 18/12/2024 | 16/02/2025 | CONSTRUCTURE | 19.15 | 0 | 0 | 0
8 | NADIA |  | Nadia Division | Providing FHTC by augmentation under Jal Swapna for Kulgachi PWSS, in Tehatta-II block with in Nadia district under Nadia Division | SM/10080 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete, Construction of 150 Cum Capacity 20 Mtr. Staging Height RCC Over Head Reservoir (Including Pile Foundation), Pipe Connection and Cost of Pipes, Specials and Soil Investigation for Augmentation of Ground Based Water Supply Scheme at Kulgachi to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000387/2022-2023 | 477/ND | 02/02/2023 | 02/02/2024 | A P POWER AND CONCRETE, 5D,HEMCHANDRA NASKAR ROAD, KOLKATA-700010 | 138.28 | 42.88 | 31.01 | 45
Total | [13 empty] | 323.64 | 42.88 | 13.25