## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for MADHPUR Block in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. | SM/10081 | Augmentation | New Service connection for Madhpur w/s scheme p.h No 2 | Assistant Engineer | Junior Engineer | ORD/000007/2022-2023 | 2865/EMD | 21/07/2022 | 20/08/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.34 | 0 | 0 | 0
2 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for MADHPUR Block in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. | SM/10081 | Augmentation | New Service connection for Madhpur w/s scheme p.h No 1 | Assistant Engineer | Junior Engineer | ORD/000008/2022-2023 | 2866/EMD | 21/07/2022 | 20/08/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.01 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MADHPUR Block in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. | SM/10081 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for MADHPUR Block in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. |  |  | VCH/001077/2021-2022 | 640/PFMS | 16/03/2022 | 16/03/2022 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT. LTD. | 2.95 | 0 | 0 | 0
4 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for MADHPUR Block in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. | SM/10081 | Augmentation | New Service connection bill for Madhpur W/s scheme |  |  | VCH/001927/2022-2023 | BP-2022-23-25 | 02/08/2022 | 02/08/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.01 | 0 | 0 | 0
5 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for MADHPUR Block in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. | SM/10081 | Augmentation | New Service connection bill for Madhupur W/s scheme |  |  | VCH/001926/2022-2023 | BP-2022-23-24 | 02/08/2022 | 02/08/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.34 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MADHPUR Block in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. | SM/10081 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000059/2022-2023 | 4319/ND | 29/09/2022 | 29/09/2022 | Resource Division | 4.87 | 0 | 0 | 0
7 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for MADHPUR Block in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. | SM/10081 | Augmentation | Supplementary quotation for argumentation of DTR from 25KVA to 63KVA at Madhpur Ref. ID 860261053 |  |  | BILL/01337/2022-2023 | 137/PFMS/EMD | 23/02/2023 | 23/02/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.89 | 0 | 0 | 0
8 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for MADHPUR Block in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. | SM/10081 | Augmentation | New Service Connection for madhpur Aplication No.3004022790 |  |  | BILL/01338/2022-2023 | 138/PFMS/EMD | 23/02/2023 | 23/02/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.01 | 0 | 0 | 0
9 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MADHPUR Block in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. | SM/10081 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Madhpur Ground Based Water Supply Scheme under Karimpur-II Block under Nadia Division,P.H.E Dte. in connection with Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Madhpur at Karimpur-II Block by Augmentation of Ground Water based PWSS for Madhpur Water Supply Schemes under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000642/2024-2025 | 7368/ND | 18/12/2024 | 16/02/2025 | K.K. MARKETING | 17.61 | 0 | 0 | 0
10 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MADHPUR Block in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. | SM/10081 | Augmentation | Renovation of AIRP (Gravity Type) of capacity 31.44 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Madhpur PWSS under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000546/2022-2023 | 1456/ND | 31/03/2023 | 25/03/2024 | APURBA MANDAL | 58.68 | 0 | 0 | 21
11 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for MADHPUR Block in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. | SM/10081 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under MADHPUR W/S Scheme, Block- Karimpur-I AND NATNA W/S Scheme, Block- Tehatta-I, Dist. - Nadia. NIET No.- 28 of EE/EMD of 2022-23 (Sl. No.- 03) | Assistant Engineer | Junior Engineer | ORD/001009/2022-2023 | 497/EMD | 24/01/2023 | 23/01/2025 | KARTICK BAL | 56.7 | 10 | 17.64 | 30
12 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MADHPUR Block in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. | SM/10081 | Augmentation | Laying of additional pipeline for Madhpur PWSS".under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000076/2024-2025 | 4078/ND | 26/07/2024 | 21/07/2025 | SUBHASIS MAJUMDER | 16.52 | 6.34 | 38.41 | 40
Total | [13 empty] | 161.91 | 16.34 | 10.09