## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for MADHPUR Block in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. | SM/10081 | Augmentation | New Service connection for Madhpur w/s scheme p.h No 2 | Assistant Engineer | Junior Engineer | ORD/000007/2022-2023 | 2865/EMD | 21/07/2022 | 20/08/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.34 | 0 | 0 | 0
2 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for MADHPUR Block in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. | SM/10081 | Augmentation | New Service connection for Madhpur w/s scheme p.h No 1 | Assistant Engineer | Junior Engineer | ORD/000008/2022-2023 | 2866/EMD | 21/07/2022 | 20/08/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.01 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MADHPUR Block in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. | SM/10081 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for MADHPUR Block in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. |  |  | VCH/001077/2021-2022 | 640/PFMS | 16/03/2022 | 16/03/2022 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT. LTD. | 2.95 | 0 | 0 | 0
4 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for MADHPUR Block in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. | SM/10081 | Augmentation | New Service connection bill for Madhpur W/s scheme |  |  | VCH/001927/2022-2023 | BP-2022-23-25 | 02/08/2022 | 02/08/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.01 | 0 | 0 | 0
5 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for MADHPUR Block in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. | SM/10081 | Augmentation | New Service connection bill for Madhupur W/s scheme |  |  | VCH/001926/2022-2023 | BP-2022-23-24 | 02/08/2022 | 02/08/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.34 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MADHPUR Block in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. | SM/10081 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000059/2022-2023 | 4319/ND | 29/09/2022 | 29/09/2022 | Resource Division | 4.87 | 0 | 0 | 0
7 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for MADHPUR Block in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. | SM/10081 | Augmentation | Supplementary quotation for argumentation of DTR from 25KVA to 63KVA at Madhpur Ref. ID 860261053 |  |  | BILL/01337/2022-2023 | 137/PFMS/EMD | 23/02/2023 | 23/02/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.89 | 0 | 0 | 0
8 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for MADHPUR Block in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. | SM/10081 | Augmentation | New Service Connection for madhpur Aplication No.3004022790 |  |  | BILL/01338/2022-2023 | 138/PFMS/EMD | 23/02/2023 | 23/02/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.01 | 0 | 0 | 0
9 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MADHPUR Block in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. | SM/10081 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Madhpur Ground Based Water Supply Scheme under Karimpur-II Block under Nadia Division,P.H.E Dte. in connection with Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Madhpur at Karimpur-II Block by Augmentation of Ground Water based PWSS for Madhpur Water Supply Schemes under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000642/2024-2025 | 7368/ND | 18/12/2024 | 16/02/2025 | K.K. MARKETING | 17.61 | 0 | 0 | 0
10 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MADHPUR Block in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. | SM/10081 | Augmentation | Renovation of AIRP (Gravity Type) of capacity 31.44 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Madhpur PWSS under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000546/2022-2023 | 1456/ND | 31/03/2023 | 29/06/2023 | APURBA MANDAL | 58.68 | 0 | 0 | 21
11 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MADHPUR Block in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. | SM/10081 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Madhpur to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000096/2022-2023 | 3383/ND | 29/07/2022 | 27/10/2022 | SUBHASIS MAJUMDER | 69.32 | 46.57 | 67.18 | 85
12 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MADHPUR Block in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. | SM/10081 | Augmentation | Laying of additional pipeline for Madhpur PWSS".under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000076/2024-2025 | 4078/ND | 26/07/2024 | 21/07/2025 | SUBHASIS MAJUMDER | 16.52 | 6.34 | 38.41 | 40
13 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MADHPUR Block in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. | SM/10081 | Augmentation | Repairing and renovation of Elevated Reservoir , Pump House and allied works of ground basaed piped water supply scheme for Madhpur water supply scheme under Tehatta Sub Division in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000480/2024-2025 | 7266/ND | 13/12/2024 | 08/12/2025 | SUMAN CHAKRABORTY | 29.68 | 0 | 0 | 0
14 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for MADHPUR Block in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. | SM/10081 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under MADHPUR W/S Scheme, Block- Karimpur-I AND NATNA W/S Scheme, Block- Tehatta-I, Dist. - Nadia. NIET No.- 28 of EE/EMD of 2022-23 (Sl. No.- 03) | Assistant Engineer | Junior Engineer | ORD/001009/2022-2023 | 497/EMD | 24/01/2023 | 23/01/2025 | KARTICK BAL | 56.7 | 10 | 17.64 | 30
Total | [13 empty] | 260.9 | 62.91 | 24.11