## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing FHTC by augmentation under Jal Swapna for Fazil Nagar PWSS in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. | SM/10082 | Augmentation | Providing FHTC by augmentation under Jal Swapna for Fazil Nagar PWSS in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. |  |  | VCH/001151/2021-2022 | 704/PFMS | 30/03/2022 | 30/03/2022 | TECHVISION | 2.87 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing FHTC by augmentation under Jal Swapna for Fazil Nagar PWSS in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. | SM/10082 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000030/2021-2022 | 431/ND | 31/01/2022 | 31/01/2022 | Resource Division | 0.76 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Providing FHTC by augmentation under Jal Swapna for Fazil Nagar PWSS in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. | SM/10082 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000057/2022-2023 | 4306/ND | 29/09/2022 | 29/09/2022 | Resource Division | 17.81 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Providing FHTC by augmentation under Jal Swapna for Fazil Nagar PWSS in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. | SM/10082 | Augmentation | Augmentation of FHTC (Part-B) of Fazilnagar Pipe Water Supply Scheme. |  |  | ORD/000160/2024-2025 | 4903/ND | 10/09/2024 | 09/11/2024 | PATHIK PABAN NANDI | 34.31 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Providing FHTC by augmentation under Jal Swapna for Fazil Nagar PWSS in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. | SM/10082 | Augmentation | Laying of additional pipeline for Fazilnagar Mouza and Phulkhali Mouza under Fazilnagar PWSS and Arabpur PWSS".under Tehatta Sub-Division under Nadia Division P.H.Engineering Dte. |  |  | ORD/000162/2024-2025 | 4905/ND | 10/09/2024 | 09/12/2024 | PATHIK PABAN NANDI | 41.67 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | Providing FHTC by augmentation under Jal Swapna for Fazil Nagar PWSS in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. | SM/10082 | Augmentation | Repairing existing Damage Pipe line from Fazilnagar Durgamandir Towards Lalnagar Under Fazilnagar PWSS.under Tehatta Sub-Division under Nadia Division P.H.Engineering Dte. | Assistant Engineer |  | ORD/000767/2023-2024 | 1820/ND | 14/03/2024 | 12/06/2024 | PATHIK PABAN NANDI | 29.99 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | Providing FHTC by augmentation under Jal Swapna for Fazil Nagar PWSS in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. | SM/10082 | Augmentation | Repairing of Existing Damage Pipe line from Fazilnagar towards Charmoktarpur via Pearpur under Fazilnagar PWSS under Nadia Division PHE Dte. | Assistant Engineer |  | ORD/000077/2024-2025 | 4087/ND | 26/07/2024 | 24/09/2024 | PATHIK PABAN NANDI | 33.36 | 0 | 0 | 0
8 | NADIA |  | Nadia Division | Providing FHTC by augmentation under Jal Swapna for Fazil Nagar PWSS in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. | SM/10082 | Augmentation | Laying of additional pipeline for Fazilnagar Mouza and Anandapur Mouza under Fazilnagar PWSS and Anandapur PWSS under Tehatta Sub-Division under Nadia Division P.H.Engineering Dte. |  |  | ORD/000161/2024-2025 | 4904/ND | 10/09/2024 | 09/12/2024 | PATHIK PABAN NANDI | 37.63 | 0 | 0 | 0
9 | NADIA |  | Nadia Division | Providing FHTC by augmentation under Jal Swapna for Fazil Nagar PWSS in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. | SM/10082 | Augmentation | Laying distribution system for providing FHTC (Functional Household Tap Connection) by Augmentation & Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Fazil Nagar Piped Water Supply Scheme at Karimpur - II block under Nadia Division P.H.E. Dte. | Assistant Engineer | Junior Engineer Chapra Block | ORD/000015/2022-2023 | 2005/ND | 05/05/2022 | 03/08/2022 | PATHIK PABAN NANDI | 271.88 | 219.13 | 80.6 | 100
10 | NADIA |  | Nadia Division | Providing FHTC by augmentation under Jal Swapna for Fazil Nagar PWSS in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. | SM/10082 | Augmentation | Renovation of AIRP (Gravity Type) of capacity 117 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Fazilnagar PWSS under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000029/2023-2024 | 1787/ND | 20/04/2023 | 22/09/2025 | B.M. ENGINEERING & CONSTRUCTION | 118.29 | 0 | 0 | 30
11 | NADIA |  | Nadia Division | Providing FHTC by augmentation under Jal Swapna for Fazil Nagar PWSS in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. | SM/10082 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Fazilnagar PWSS under Karimpur-II Block under Tehatta Sub Division under Nadia Division-,P.H.E Dte. under Jal Jeevan Mission(JJM). | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000746/2024-2025 | 424/ND | 27/01/2025 | 22/01/2026 | REAL TIME | 34.74 | 0 | 0 | 60
Total | [13 empty] | 623.32 | 219.13 | 35.15