## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of ground water based Dhoradaha PWSS to accommodate FHTC in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. | SM/10083 | Augmentation | Augmentation of ground water based Dhoradaha PWSS to accommodate FHTC in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. |  |  | VCH/001102/2021-2022 | 672/PFMS | 24/03/2022 | 24/03/2022 | RADIANT | 3.09 | 0 | 0 | 0
2 | NADIA |  | Central Drilling | Augmentation of ground water based Dhoradaha PWSS to accommodate FHTC in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. | SM/10083 | Augmentation | Providing Drilling Crew and other allied works for construction of Tube Well (300mm x 200mm x250 Mtrs. Depth) by utilising Departmental machineries for Dhoradaha W/S Scheme (T/W-I) karimpur-II Block under Nadia District, CDD PHE Dte. | Driller In Charge | Junior Engineer | ORD/000029/2023-2024 | 136/CDD | 17/04/2023 | 17/05/2023 | SUNRISE ENGINEERING CORPORATION | 18.87 | 11.42 | 60.49 | 100
3 | NADIA |  | Nadia Division | Augmentation of ground water based Dhoradaha PWSS to accommodate FHTC in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. | SM/10083 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000040/2023-2024 | 1905/ND | 27/04/2023 | 27/04/2023 | Resource Division | 105.7 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Augmentation of ground water based Dhoradaha PWSS to accommodate FHTC in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. | SM/10083 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000075/2023-2024 | 2296/ND | 29/05/2023 | 29/05/2023 | Resource Division | 26.74 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Augmentation of ground water based Dhoradaha PWSS to accommodate FHTC in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. | SM/10083 | Augmentation | Construction Of Pump House (3.6x 3.0m) Including Sanitary Arrangemen and Consruction of Boundary wall at Tube well No-3 Site at Dhoradaha Water Supply Scheme Under Tehatta Sub-Division PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000754/2023-2024 | 1629/ND | 07/03/2024 | 01/03/2026 | BANERJEE ENTERPRISE | 12.74 | 1.31 | 10.26 | 70
6 | NADIA |  | Nadia Division | Augmentation of ground water based Dhoradaha PWSS to accommodate FHTC in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. | SM/10083 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed Augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Dhoradaha to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000382/2022-2023 | 382/ND | 27/01/2023 | 27/04/2023 | SATYABRATA CHAKRABORTY | 457.46 | 93.98 | 20.54 | 65
7 | NADIA |  | Nadia Division | Augmentation of ground water based Dhoradaha PWSS to accommodate FHTC in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. | SM/10083 | Augmentation | Providing FHTC including Laying Distribution System in connection with J.J.M. Work under village Baruipota, Teinpur to cover up left out portion under Karimpur-II Block under RWS Nadia Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000708/2024-2025 | 134/ND | 08/01/2025 | 03/01/2026 | M/S FREEDOM CONSTRUCTION | 57.04 | 0 | 0 | 70
8 | NADIA |  | Nadia Division | Augmentation of ground water based Dhoradaha PWSS to accommodate FHTC in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. | SM/10083 | Augmentation | Repairing and renovation of Elevated Reservoir , Pump House and allied works of ground basaedpiped water supply scheme for Dhoradaha water supply scheme under Tehatta Sub Division in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000780/2024-2025 | 305/ND | 17/01/2025 | 14/10/2025 | J.P. CONSTRUCTION & SUPPLIERS | 35.46 | 0 | 0 | 45
9 | NADIA |  | Nadia Division | Augmentation of ground water based Dhoradaha PWSS to accommodate FHTC in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. | SM/10083 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Dhoradaha Ground Based Water Supply Scheme under Karimpur-II Block under Nadia Division, P.H.E Dte. in connection with Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Dhoradaha at Karimpur-II Block by Augmentation of Ground Water based PWSS for Dhoradaha Water Supply Schemes under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000738/2024-2025 | 416/ND | 27/01/2025 | 24/09/2025 | BANERJEE CONSTRUCTION | 23.41 | 0 | 0 | 40
10 | NADIA |  | Nadia Division | Augmentation of ground water based Dhoradaha PWSS to accommodate FHTC in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. | SM/10083 | Augmentation | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 11/10/2025 | IMAGIN | 96.97 | 0 | 0 | 0
11 | NADIA |  | Eastern Mechanical | Augmentation of ground water based Dhoradaha PWSS to accommodate FHTC in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. | SM/10083 | Augmentation | Quotation charges and security deposit for new service connection at PH-IiI of Doradaha W/S Scheme under EMSD-III,PHE Dte., Nadia. |  |  | BILL/02513/2024-2025 | BP-233 | 04/02/2025 | 04/02/2025 | WBSEDCL KARIMPUR CCC | 10.62 | 0 | 0 | 0
Total | [13 empty] | 848.1 | 106.7 | 12.58