## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Eastern Mechanical | Providing FHTC by augmentation for Madhugari water supply scheme with in Karimpur-I Block in Nadia District under Nadia Division P.H.E. Dte. (Phase-II) | SM/10084 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I, (Phase-II) under Madhugari ground water based water supply scheme under Block_ Karimpur-I Dist. - Nadia under EMD, PHE Dte. |  |  | ORD/001772/2023-2024 | 6396/EMD | 30/10/2023 | 29/11/2023 | S.P. ENTERPRISE (KOLKATA) | 16.32 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing FHTC by augmentation for Madhugari water supply scheme with in Karimpur-I Block in Nadia District under Nadia Division P.H.E. Dte. (Phase-II) | SM/10084 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000006/2023-2024 | 1577/ND | 06/04/2023 | 06/04/2023 | Resource Division | 0.41 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Providing FHTC by augmentation for Madhugari water supply scheme with in Karimpur-I Block in Nadia District under Nadia Division P.H.E. Dte. (Phase-II) | SM/10084 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000064/2023-2024 | 2307/ND | 29/05/2023 | 29/05/2023 | Resource Division | 0.62 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Providing FHTC by augmentation for Madhugari water supply scheme with in Karimpur-I Block in Nadia District under Nadia Division P.H.E. Dte. (Phase-II) | SM/10084 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Madhugari to accommodate FHTC within Karimpur-I block under RWS Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000294/2022-2023 | 5334/ND | 21/12/2022 | 06/03/2023 | SANJIB DEY | 74.59 | 0 | 0 | 60
5 | NADIA |  | Eastern Mechanical | Providing FHTC by augmentation for Madhugari water supply scheme with in Karimpur-I Block in Nadia District under Nadia Division P.H.E. Dte. (Phase-II) | SM/10084 | Augmentation | Repairing rectification of electro-mechanical works related to installation of submersible pump sets and others accessories in connection with JJM under Madhugari PWSS, Block- Karimpur-I, under EMSD-III, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000113/2024-2025 | 1220/EMSD-III | 28/06/2024 | 28/07/2024 | SMILE | 2.42 | 0 | 0 | 100
6 | NADIA |  | Nadia Division | Providing FHTC by augmentation for Madhugari water supply scheme with in Karimpur-I Block in Nadia District under Nadia Division P.H.E. Dte. (Phase-II) | SM/10084 | Augmentation | Additional work of providing FHTC and additional work of Laying Distribution System in connection with Augmentation of Madhugari PWSS within Karimpur-I Block under RWS Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000725/2023-2024 | 1254/ND | 22/02/2024 | 01/07/2025 | S.S. ENTERPRISE | 19.88 | 0 | 0 | 100
7 | NADIA |  | Nadia Division | Providing FHTC by augmentation for Madhugari water supply scheme with in Karimpur-I Block in Nadia District under Nadia Division P.H.E. Dte. (Phase-II) | SM/10084 | Augmentation | Conversion of IEP to AIRP of capacity 38 Cu.m/hr at Madhugari Water Supply Scheme within Karimpur-I block under RWS Nadia Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000799/2023-2024 | 1911/ND | 15/03/2024 | 05/11/2025 | MONDAL PRECISION PRIVATE LIMITED | 140.38 | 0 | 0 | 65
8 | NADIA |  | Nadia Division | Providing FHTC by augmentation for Madhugari water supply scheme with in Karimpur-I Block in Nadia District under Nadia Division P.H.E. Dte. (Phase-II) | SM/10084 | Augmentation | Repairing Works (existing OHR, Pump House, Boundary wall etc.) of Madhugari Water Supply Scheme, Karimpur-I Block Under R.W.S. Nadia Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000030/2024-2025 | 3431/ND | 19/06/2024 | 14/06/2025 | M/S DURGA SECURITIES & SERVICES | 22.18 | 0 | 0 | 100
Total | [13 empty] | 276.8 | 0 | 0