## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA ANDULIA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte.. | SM/10268 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA ANDULIA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte.. |  |  | VCH/001072/2021-2022 | 635/PFMS | 16/03/2022 | 16/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.6 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA ANDULIA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte.. | SM/10268 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure, Proposed augmentation of Rising Main system, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc., Construction of R.C.C. Elevated Reservoir of 600 Cum capacity (including pile foundation), Soil Investigation for construction of OHR, Construction of 1 No. Pump House at proposed Head Work site and Construction of boundary wall with gate all complete for Augmentation of Ground Based Water Supply Scheme at Bara Andulia Zone-II to accommodate FHTC within Chapra block under Krishnanagar Sub-division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000154/2023-2024 | 3220/ND | 26/07/2023 | 26/07/2024 | GHOSH ENTERPRISE | 467.16 | 0 | 0 | 0
3 | NADIA |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA ANDULIA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte.. | SM/10268 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilizing Departmental Machineries for Bara Andulia W/S Scheme (Z-II, T/W-I) , Chapra Block under Nadia District, Central Drilling Division, P.H.E. Dte. |  |  | ORD/000128/2023-2024 | 1231/CDD | 04/09/2023 | 04/10/2023 | MENAKA ENTERPRISE | 18.88 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA ANDULIA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte.. | SM/10268 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000148/2022-2023 | 82/ND | 05/01/2023 | 05/01/2023 | Resource Division | 234.57 | 0 | 0 | 0
5 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA ANDULIA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte.. | SM/10268 | Augmentation | Supply, Delivery and Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accommodate FHTC under Bara Andulia Z-II) WS Scheme, Block-Chapra , Dist. - Nadia. | Assistant Engineer | Junior Engineer | ORD/001125/2023-2024 | 4713/EMD | 04/08/2023 | 03/09/2023 | INDTECH ASSOCIATES | 29.24 | 0 | 0 | 60
6 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA ANDULIA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte.. | SM/10268 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 30/01/2024 | IMAGIN | 96.97 | 0 | 0 | 40
7 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA ANDULIA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte.. | SM/10268 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 116 m3/hr at Bara Andulia Zone-II Water Supply Scheme within Chapra Block under Krishnagar Sub-Divn. under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000384/2024-2025 | 7090/ND | 05/12/2024 | 03/06/2025 | APURBA MANDAL | 288.79 | 0 | 0 | 0
8 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA ANDULIA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte.. | SM/10268 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000147/2023-2024 | 258/ND | 11/01/2024 | 11/01/2024 | Resource Division | 10.9 | 0 | 0 | 0
9 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA ANDULIA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte.. | SM/10268 | Augmentation | Quotation for new service connection charges and security deposit for PH-3 under Bara-Andulia(Zone-I) w/s scheme, Under EMSD-III,PHE Dte,Nadia |  |  | BILL/01810/2024-2025 | BP-158-24-25 | 06/11/2024 | 06/11/2024 | W.B.S.E.D.C.L (GROUP CHAPRA C.C.C) | 3.71 | 0 | 0 | 0
10 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA ANDULIA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte.. | SM/10268 | Augmentation | Repair & Renovation of Pump House, Boundary wall and allied works at 1st and 2nd Pump House at Bara Andulia Zone II Water Supply Scheme within Chapra block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 4 | ORD/000477/2023-2024 | 155/ND | 09/01/2024 | 05/09/2024 | DIAMOND ENGINEERS CO.OP SOCIETY LTD. | 12.15 | 0 | 0 | 75
Total | [13 empty] | 1165.97 | 0 | 0