## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARAIA to Accommodate FHTC in Tehatta-II block of Nadia District under Nadia Division, PHE Dte. | SM/10269 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for BARAIA to Accommodate FHTC in Tehatta-II block of Nadia District under Nadia Division, PHE Dte. |  |  | VCH/001265/2021-2022 | 731/PFMS | 30/03/2022 | 30/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2.17 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARAIA to Accommodate FHTC in Tehatta-II block of Nadia District under Nadia Division, PHE Dte. | SM/10269 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for BARAIA to Accommodate FHTC in Tehatta-II block of Nadia District under Nadia Division, PHE Dte. |  |  | VCH/001266/2021-2022 | 732/PFMS | 30/03/2022 | 30/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.26 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARAIA to Accommodate FHTC in Tehatta-II block of Nadia District under Nadia Division, PHE Dte. | SM/10269 | Augmentation | Construction of barbed wire fencing with concrete pillars at Baraya Zone-II (2nd T.W). water supply scheme( New Land) under Tehatta Sub-Division under Nadia Division PHE Dte. in JJM project . | Assistant Engineer |  | ORD/000581/2022-2023 | 930/TSD | 14/03/2023 | 21/03/2023 | PRABIR KUMAR ROY | 0.7 | 0.69 | 99.76 | 0
4 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for BARAIA to Accommodate FHTC in Tehatta-II block of Nadia District under Nadia Division, PHE Dte. | SM/10269 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. rejuvenation to Accomodate FHTC at Pump House No.- I & II under Baraia W/S Scheme, Block-Tehatta-II, Dist. - Nadia. NIET No. 25 of EE/EMD of 2022-23 (Sl. No.- 04) |  |  | ORD/000898/2022-2023 | 408/EMD | 20/01/2023 | 19/02/2023 | PADMA ENGINEERING CO. | 22.18 | 21.91 | 98.8 | 55
5 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARAIA to Accommodate FHTC in Tehatta-II block of Nadia District under Nadia Division, PHE Dte. | SM/10269 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000175/2022-2023 | 152/ND | 06/01/2023 | 06/01/2023 | Resource Division | 26.67 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARAIA to Accommodate FHTC in Tehatta-II block of Nadia District under Nadia Division, PHE Dte. | SM/10269 | Augmentation | Construction of 250 cum capacity 20 Mtr. staging height RCC Over Head Reservoir, pipe connection and cost of pipes, specials and Soil Investigation for Construction of 250 CUM OHR at Bareya Zone-II W/S. scheme under Nadia Division P.H.E. Dte. in the District of Nadia . | Assistant Engineer |  | ORD/000068/2024-2025 | 3980/ND | 22/07/2024 | 22/07/2025 | CHOWDHURY & CO. | 130.34 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARAIA to Accommodate FHTC in Tehatta-II block of Nadia District under Nadia Division, PHE Dte. | SM/10269 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Bareya Zone-II Ground Based Water Supply Scheme under Tehatta-II Block under Nadia Division,P.H.E Dte. in connection with Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Bareya Zone-II at Bareya Zone-II Block by Augmentation of Ground Water based PWSS for Bareya Zone-II Water Supply Schemes under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000630/2024-2025 | 7361/ND | 18/12/2024 | 16/02/2025 | M/S DURGA SECURITIES & SERVICES | 20.41 | 0 | 0 | 0
8 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for BARAIA to Accommodate FHTC in Tehatta-II block of Nadia District under Nadia Division, PHE Dte. | SM/10269 | Augmentation | Quotation charges and security deposit for new power connection at Baraia(Zone-II) head worksite under Eastern Mechanical Subdivision-III, Nadia |  |  | BILL/02319/2024-2025 | BP-195-24-25 | 17/12/2024 | 17/12/2024 | W.B.S.E.D.C.L (PANCHDHARA ABHAYNAGAR C.C.C) | 14.83 | 0 | 0 | 0
9 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for BARAIA to Accommodate FHTC in Tehatta-II block of Nadia District under Nadia Division, PHE Dte. | SM/10269 | Augmentation | Quotation charges and security deposit for new power connection at Baraia(Zone-II) PH-II under Eastern Mechanical Subdivision-III, Nadia |  |  | BILL/02259/2024-2025 | BP-176 | 13/12/2024 | 13/12/2024 | W.B.S.E.D.C.L (PANCHDHARA ABHAYNAGAR C.C.C) | 4.04 | 0 | 0 | 0
10 | NADIA |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for BARAIA to Accommodate FHTC in Tehatta-II block of Nadia District under Nadia Division, PHE Dte. | SM/10269 | Augmentation | Sinking of 80 mm dia. Shallow Tube Well for requirement of drilling water for Baraia PWSS, District - Nadia and other PWSS under CMSD-II (D), CDD, PHE Dte. | Driller In Charge | Junior Engineer | ORD/000078/2023-2024 | 91/CMSD-II | 17/04/2023 | 01/03/2025 | PADMA ENGINEERING & CO. | 0.89 | 0 | 0 | 15
11 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARAIA to Accommodate FHTC in Tehatta-II block of Nadia District under Nadia Division, PHE Dte. | SM/10269 | Augmentation | Construction Of Pump House (3.6x 3.0m) Including Sanitary Arrangement and construction of boundary wall at Tube well No-2 Site at Bareya Water Supply Scheme(Z-II) Under Tehatta Sub-Division PHE Dte.) | Assistant Engineer | Junior Engineer 2 | ORD/000747/2023-2024 | 1625/ND | 07/03/2024 | 02/03/2025 | ROY ASSOCIATES | 12.15 | 0 | 0 | 0
12 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARAIA to Accommodate FHTC in Tehatta-II block of Nadia District under Nadia Division, PHE Dte. | SM/10269 | Augmentation | Repairing and renovation works of Pump House and allied works of ground based piped water supply scheme for Bareya Zone-I water supply scheme under Tehatta Sub Division in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000273/2024-2025 | 6695/ND | 29/10/2024 | 27/01/2025 | SHREEOM ENTERPRISE | 13.79 | 0 | 0 | 0
13 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARAIA to Accommodate FHTC in Tehatta-II block of Nadia District under Nadia Division, PHE Dte. | SM/10269 | Augmentation | Construction of Arsenic-Cum- Iron Removal Plant (AIRP) of 54 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Bareya Zone-I to accommodate FHTC within Tehatta-II block under Tehatta Sub-division under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000091/2024-2025 | 4315/ND | 06/08/2024 | 01/08/2025 | MONDAL PRECISION PRIVATE LIMITED | 186.88 | 0 | 0 | 0
14 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARAIA to Accommodate FHTC in Tehatta-II block of Nadia District under Nadia Division, PHE Dte. | SM/10269 | Augmentation | Construction Of Pump House (5.4m X 3.6m) Including Sanitary Arrangement and construction of Boundary wall at Head Work Site of Bareya Zone-II Water Supply Scheme Under Tehatta Sub-Division PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000072/2024-2025 | 4076/ND | 26/07/2024 | 22/01/2025 | MANAJIT BISWAS | 22.65 | 0 | 0 | 40
15 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARAIA to Accommodate FHTC in Tehatta-II block of Nadia District under Nadia Division, PHE Dte. | SM/10269 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme (Phase- II) at Bareya Zone-I to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000074/2024-2025 | 4077/ND | 26/07/2024 | 19/09/2025 | SANJIB DEY | 58.82 | 0 | 0 | 75
16 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARAIA to Accommodate FHTC in Tehatta-II block of Nadia District under Nadia Division, PHE Dte. | SM/10269 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Bareya Zone-II to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000075/2024-2025 | 4074/ND | 26/07/2024 | 19/10/2025 | CHOWDHURY & CO. | 185.28 | 0 | 0 | 10
17 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for BARAIA to Accommodate FHTC in Tehatta-II block of Nadia District under Nadia Division, PHE Dte. | SM/10269 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under BARAIA ground water based water supply scheme under Block_ Tehatta-II Dist. - Nadia under EMD, PHE Dte. SM/10269 | Assistant Engineer |  | ORD/000181/2025-2026 | 1118/EMD | 04/06/2025 | 02/09/2025 | GHOSH AND GHOSH | 17.48 | 0 | 0 | 0
18 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARAIA to Accommodate FHTC in Tehatta-II block of Nadia District under Nadia Division, PHE Dte. | SM/10269 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 42 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Bareya Zone-II to accommodate FHTC within Tehatta-II block under Tehatta Sub-division under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000849/2024-2025 | 4143/ND | 29/07/2024 | 25/01/2025 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 173.48 | 0 | 0 | 0
19 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARAIA to Accommodate FHTC in Tehatta-II block of Nadia District under Nadia Division, PHE Dte. | SM/10269 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Bareya Zone-I Ground Based Water Supply Scheme under Tehatta-II Block under Nadia Division, P.H.E Dte. in connection with Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Bareya Zone-I at Tehatta-II Block by Augmentation of Ground Water based PWSS for Bareya Zone-I Water Supply Schemes under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000078/2025-2026 | 2460/ND | 27/05/2025 | 26/07/2025 | S.D. CONSTRUCTION | 23.36 | 0 | 0 | 0
20 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARAIA to Accommodate FHTC in Tehatta-II block of Nadia District under Nadia Division, PHE Dte. | SM/10269 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Bareya Zone-I to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000731/2021-2022 | 1249/ND | 16/03/2022 | 27/06/2023 | DIAMOND ENGINEERS CO.OP SOCIETY LTD. | 196.39 | 189.23 | 96.35 | 100
Total | [13 empty] | 1115.76 | 211.84 | 18.99