## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Annual Procurement of Chemicals, Consumables, Glassware, Instruments & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of Different Water Testing Laboratories under Nadia Division, PHE Dte. | SM/10401 | Support-WQMSP | Continuation of Maintenance for computers and related accessories for Nadia District Water Testing Laboratory, 05(Five) nos of Sub-District Water Testing Laboratory and 05 (Five) nos of NGO managed water testing laboratories under Nadia Division, PHE Dte. (W.E.F 01/02/2022 to 31/07/2022) | Assistant Engineer |  | ORD/000653/2021-2022 | 78/Kly SD-I | 31/01/2022 | 31/07/2022 | IONET | 0.92 | 0.92 | 100 | 0
2 | NADIA |  | Nadia Division | Annual Procurement of Chemicals, Consumables, Glassware, Instruments & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of Different Water Testing Laboratories under Nadia Division, PHE Dte. | SM/10401 | Support-WQMSP | Procurement of consumables for OMAS (On-site Mobile Analysis System) at Krishnagar Sub-District Laboratory as directed by EIC under Nadia Division, Public Health Engineering Dte. | Assistant Engineer |  | ORD/000044/2022-2023 | 563/ Kly SD-I | 24/06/2022 | 09/07/2022 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD | 4.29 | 4.29 | 100 | 0
3 | NADIA |  | Nadia Division | Annual Procurement of Chemicals, Consumables, Glassware, Instruments & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of Different Water Testing Laboratories under Nadia Division, PHE Dte. | SM/10401 | Support-WQMSP | Supply and installation of Sign-Board for NABL recognition for NGO managed laboratories and other allied works at Nadia District Water Testing Laboratory under Nadia Division PHE Dte. | Assistant Engineer |  | ORD/000105/2022-2023 | 689/Kly SD-I | 01/08/2022 | 16/08/2022 | MANISHIKA CONSTRUCTION | 0.78 | 0.77 | 98.53 | 0
4 | NADIA |  | Nadia Division | Annual Procurement of Chemicals, Consumables, Glassware, Instruments & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of Different Water Testing Laboratories under Nadia Division, PHE Dte. | SM/10401 | Support-WQMSP | Continuation of Annual Service contract for Double beam Atomic Absorption Spectrophotometer AAS3300 including supply of necessary spare parts and consumables (As and when required) installed at Belpukur Water Testing Laboratory At Belpukur WTP Site, Nadia, under Nadia Division, PHE Dte.(W.E.F-01.08.2022 to 31.01.2023) | Assistant Engineer |  | ORD/000077/2022-2023 | 675/Kly SD-I | 26/07/2022 | 26/01/2023 | TARUN KUMAR BHATTACHARYA | 1.56 | 1.56 | 99.98 | 0
5 | NADIA |  | Nadia Division | Annual Procurement of Chemicals, Consumables, Glassware, Instruments & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of Different Water Testing Laboratories under Nadia Division, PHE Dte. | SM/10401 | Support-WQMSP | Continuation of Maintenance for computers and related accessories for Nadia District Water Testing Laboratory, 05(Five) nos of Sub-District Water Testing Laboratory and 05 (Five) nos of NGO managed water testing laboratories under Nadia Division, PHE Dte. (W.E.F 01/08/2022 to 31/01/2023) | Assistant Engineer |  | ORD/000075/2022-2023 | 673/Kly SD-I | 26/07/2022 | 26/01/2023 | IONET | 0.92 | 0.92 | 100 | 0
6 | NADIA |  | Nadia Division | Annual Procurement of Chemicals, Consumables, Glassware, Instruments & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of Different Water Testing Laboratories under Nadia Division, PHE Dte. | SM/10401 | Support-WQMSP | Continuation of Annual Service contract for Double beam Atomic Absorption Spectrometer AAS3300 including supply of necessary spare parts and consumables (As and when required) installed at Nadia District Water Testing Laboratory At Haringhata WTP Site, Nadia, under Nadia Division, PHE Dte.(W.E.F-01.08.2022 to 31.01.2023) | Assistant Engineer |  | ORD/000076/2022-2023 | 674/Kly SD-I | 26/07/2022 | 26/01/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 2.03 | 2.06 | 101.72 | 0
7 | NADIA |  | Nadia Division | Annual Procurement of Chemicals, Consumables, Glassware, Instruments & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of Different Water Testing Laboratories under Nadia Division, PHE Dte. | SM/10401 | Support-WQMSP | Annual Service contract for Double beam Atomic Absorption Spectrometer AAS3300 including supply of necessary spare parts and consumables (As and when required) installed at Nadia District Water Testing Laboratory At Haringhata WTP Site, Nadia, under Nadia Division, PHE Dte.(W.E.F-01.08.2021 to 31.07.2022) | Assistant Engineer |  | ORD/000121/2021-2022 | 229/Kly SD-1 | 27/07/2021 | 27/07/2022 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 4.06 | 3.98 | 97.94 | 0
8 | NADIA |  | Nadia Division | Annual Procurement of Chemicals, Consumables, Glassware, Instruments & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of Different Water Testing Laboratories under Nadia Division, PHE Dte. | SM/10401 | Support-WQMSP | Annual Service contract for Double beam Atomic Absorption Spectrophotometer AAS3300 including supply of necessary spare parts and consumables (As and when required) installed at Belpukur Water Testing Laboratory At Belpukur WTP Site, Nadia, under Nadia Division, PHE Dte.(W.E.F-01.08.2021 to 31.07.2022) | Assistant Engineer |  | ORD/000122/2021-2022 | 230/Kly SD-1 | 27/07/2021 | 27/07/2022 | TARUN KUMAR BHATTACHARYA | 3.12 | 3.13 | 100.12 | 0
9 | NADIA |  | Nadia Division | Annual Procurement of Chemicals, Consumables, Glassware, Instruments & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of Different Water Testing Laboratories under Nadia Division, PHE Dte. | SM/10401 | Support-WQMSP | Supply of Chemical, Certified Reference Material, Glassware and instrument for Different Water Testing Laboratories under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000002/2022-2023 | 1800/ND | 19/04/2022 | 19/05/2022 | M/S MANDAL SCIENTIFIC AND WATER ANALYSIS | 27.61 | 27.61 | 100 | 0
10 | NADIA |  | Nadia Division | Annual Procurement of Chemicals, Consumables, Glassware, Instruments & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of Different Water Testing Laboratories under Nadia Division, PHE Dte. | SM/10401 | Support-WQMSP | Supply of different laboratory instruments, refrigerator etc for maintaining NABL standard of Nadia District Water Testing Laboratory under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000164/2022-2023 | 922/Kly SD-I | 29/09/2022 | 14/10/2022 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.9 | 0.9 | 100 | 0
11 | NADIA |  | Nadia Division | Annual Procurement of Chemicals, Consumables, Glassware, Instruments & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of Different Water Testing Laboratories under Nadia Division, PHE Dte. | SM/10401 | Support-WQMSP | Providing consultancy services for NABL Accreditation of Nadia District Water Testing Laboratory as per ISO/IEC 17025: 2017 including supply of required materials under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000013/2023-2024 | 542/ Kly SD-I | 24/04/2023 | 24/10/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 3.95 | 3.95 | 100 | 100
12 | NADIA |  | Nadia Division | Annual Procurement of Chemicals, Consumables, Glassware, Instruments & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of Different Water Testing Laboratories under Nadia Division, PHE Dte. | SM/10401 | Support-WQMSP | Water Supply connection including installation of AC at Nadia District Water Testing Laboratory under Nadia Division, PHE Dte. |  | Junior Engineer 2 | ORD/000064/2023-2024 | 661/KlySD-I | 25/05/2023 | 09/06/2023 | MANISHIKA CONSTRUCTION | 1 | 1 | 99.91 | 100
13 | NADIA |  | Nadia Division | Annual Procurement of Chemicals, Consumables, Glassware, Instruments & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of Different Water Testing Laboratories under Nadia Division, PHE Dte. | SM/10401 | Support-WQMSP | SUPPLY AND INSTALLATION OF 01 NO LCD MONITOR 19 AT NADIA DISTRICT WATER TESTING LABORATORY UNDER NADIA DIVISION, PHE,DTE |  |  | BILL/00056/2023-2024 | 79/PFMS | 02/06/2023 | 02/06/2023 | IONET | 0.09 | 0 | 0 | 0
14 | NADIA |  | Nadia Division | Annual Procurement of Chemicals, Consumables, Glassware, Instruments & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of Different Water Testing Laboratories under Nadia Division, PHE Dte. | SM/10401 | Support-WQMSP | SUPPLY AND INSTALLATION OF 01 NO CCTV CAMERA AND ACCESSORIES AT NADIA DISTRICT WATER TESTING LABORATORY UNDER NADIA DIVISION, PHE,DTE |  |  | BILL/00054/2023-2024 | 80/PFMS | 02/06/2023 | 02/06/2023 | IONET | 0.1 | 0 | 0 | 0
15 | NADIA |  | Nadia Division | Annual Procurement of Chemicals, Consumables, Glassware, Instruments & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of Different Water Testing Laboratories under Nadia Division, PHE Dte. | SM/10401 | Support-WQMSP | SUPPLY OF CHEMICAL REGENT AT DIFFERENT WATER TESTING LABORATORIES UNDER NADIA DIVISION PHE DTE. |  |  | BILL/00114/2023-2024 | 54/PFMS | 02/06/2023 | 02/06/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 4.95 | 0 | 0 | 0
16 | NADIA |  | Nadia Division | Annual Procurement of Chemicals, Consumables, Glassware, Instruments & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of Different Water Testing Laboratories under Nadia Division, PHE Dte. | SM/10401 | Support-WQMSP | SUPPLY OF FOLLOWING ITEMS AT THE OFFICE OF THE ASSISTANT ENGINEER, KALYANI SUB-DIVISION, PHE,DTE |  |  | BILL/00058/2023-2024 | 82/PFMS | 02/06/2023 | 02/06/2023 | IONET | 0.09 | 0 | 0 | 0
17 | NADIA |  | Nadia Division | Annual Procurement of Chemicals, Consumables, Glassware, Instruments & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of Different Water Testing Laboratories under Nadia Division, PHE Dte. | SM/10401 | Support-WQMSP | SUPPLY OF FOLLOWING ITEMS AT THE OFFICE OF THE ASSISTANT ENGINEER, KALYANI SUB-DIVISION, PHE,DTE |  |  | BILL/00057/2023-2024 | 81/PFMS | 02/06/2023 | 02/06/2023 | IONET | 0.1 | 0 | 0 | 0
Total | [13 empty] | 56.49 | 51.11 | 90.47