## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing FHTC by Augmentation of Payradanga PWSS Block: Hanskhali, District: Nadia | SM/10413 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000106/2022-2023 | 5171/ND | 13/12/2022 | 13/12/2022 | Resource Division | 13.09 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing FHTC by Augmentation of Payradanga PWSS Block: Hanskhali, District: Nadia | SM/10413 | Augmentation | Providing FHTC by Augmentation of Payradanga PWSS Block: Hanskhali, District: Nadia |  |  | VCH/000351/2022-2023 | 51/PFMS | 22/06/2022 | 22/06/2022 | HORIZEN | 2.78 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Providing FHTC by Augmentation of Payradanga PWSS Block: Hanskhali, District: Nadia | SM/10413 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000028/2023-2024 | 1876/ND | 26/04/2023 | 26/04/2023 | Resource Division | 5.56 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Providing FHTC by Augmentation of Payradanga PWSS Block: Hanskhali, District: Nadia | SM/10413 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000061/2023-2024 | 2301/ND | 29/05/2023 | 29/05/2023 | Resource Division | 22.33 | 0 | 0 | 0
5 | NADIA |  | Eastern Mechanical | Providing FHTC by Augmentation of Payradanga PWSS Block: Hanskhali, District: Nadia | SM/10413 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under PAYRADANGA W/S Scheme, Block- Hanskhali , Dist. - Nadia. NIET No.- 28 of EE/EMD of 2022-23 (Sl. No.- 09) | Assistant Engineer | Junior Engineer | ORD/001014/2022-2023 | 502/EMD | 24/01/2023 | 23/02/2023 | BARISAL TRADING CO. | 29.84 | 12.63 | 42.33 | 30
6 | NADIA |  | Central Drilling | Providing FHTC by Augmentation of Payradanga PWSS Block: Hanskhali, District: Nadia | SM/10413 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Pyradanga W/S Scheme (TW-I) , Hanskhali Block under Nadia District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000137/2023-2024 | 1236/CDD | 04/09/2023 | 31/05/2024 | RAJ & ENTERPRISE | 18.7 | 16.17 | 86.47 | 100
7 | NADIA |  | Nadia Division | Providing FHTC by Augmentation of Payradanga PWSS Block: Hanskhali, District: Nadia | SM/10413 | Augmentation | Construction of Arsenic-Cum- Iron Removal Plant (AIRP) of 90 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Payradanga to accommodate FHTC within Hanskhali block under Ranaghat Sub-division under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000192/2024-2025 | 5045/ND | 13/09/2024 | 07/03/2026 | ODISSI INNOVATIONS ENGINEERS PRIVATE LIMITED | 237.16 | 0 | 0 | 70
8 | NADIA |  | Eastern Mechanical | Providing FHTC by Augmentation of Payradanga PWSS Block: Hanskhali, District: Nadia | SM/10413 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Payradanga ground water based water supply scheme under Block_ Hanskhali Dist. - Nadia under EMD, PHE Dte. SM/10413 | Assistant Engineer |  | ORD/000173/2025-2026 | 1106/EMD | 04/06/2025 | 02/09/2025 | A.K. ENTERPRISE | 20.79 | 0 | 0 | 0
9 | NADIA |  | Nadia Division | Providing FHTC by Augmentation of Payradanga PWSS Block: Hanskhali, District: Nadia | SM/10413 | Augmentation | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule, saddle piece etc. all complete, Construction of 500 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (including pile foundation), pipe connection and cost of pipes, specials & Soil investigation for construction of one no. 500 cum OHR of staging height 20 mtr. for augmentation of Ground Water Based Water Supply Scheme for Payradanga to accommodate FHTC in Hanskhali block of Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000192/2022-2023 | 4543/ND | 21/10/2022 | 20/10/2025 | AMAL DUTTA ROY, 204/1A, LINTON STREET, KOLKATTA-700014 | 504.52 | 386.63 | 76.63 | 96
10 | NADIA |  | Nadia Division | Providing FHTC by Augmentation of Payradanga PWSS Block: Hanskhali, District: Nadia | SM/10413 | Augmentation | Repairing of PH-II and Construction of Sanitary arrangement under augmentation of Payradanga under Ranaghat Sub-Division under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000390/2024-2025 | 1426/RSD | 19/11/2024 | 03/01/2025 | M/S LALTI ENTERPRISE | 2.14 | 0.52 | 24.22 | 95
11 | NADIA |  | Nadia Division | Providing FHTC by Augmentation of Payradanga PWSS Block: Hanskhali, District: Nadia | SM/10413 | Augmentation | Repairing of Pump house-I with sanitary arrangement under augmentation of Payradanga piped water supply scheme under Ranaghat Sub-Division, under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000180/2024-2025 | 1149/RSD | 11/09/2024 | 26/10/2024 | M/S LALTI ENTERPRISE | 1.89 | 0 | 0 | 100
Total | [13 empty] | 858.81 | 415.94 | 48.43