## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Betai Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | SM/10414 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for Betai Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. |  |  | VCH/000286/2022-2023 | 11/PFMS | 11/05/2022 | 11/05/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.93 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Betai Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | SM/10414 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000177/2022-2023 | 156/ND | 06/01/2023 | 06/01/2023 | Resource Division | 40.09 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Betai Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | SM/10414 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000083/2023-2024 | 2316/ND | 29/05/2023 | 29/05/2023 | Resource Division | 27.29 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Betai Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | SM/10414 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 83 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Betai Zone-II to accommodate FHTC under Tehatta Sub-division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000155/2024-2025 | 4350/ND | 07/08/2024 | 03/02/2025 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 227.43 | 0 | 0 | 0
5 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Betai Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | SM/10414 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under BETAI (ZONE-I) W/S Scheme, Block-Tehatta-I, Dist. - Nadia. NIET NO. 25 OF EE/EMD OF 2022-23 (SL. NO. 05) | Assistant Engineer | Junior Engineer | ORD/001254/2022-2023 | 811/EMD | 16/02/2023 | 01/01/2025 | A.K. ENTERPRISE | 24.7 | 0 | 0 | 80
6 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Betai Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | SM/10414 | Augmentation | Construction of 4.88 mtr. x 3.66 mtr. Size pump house including Sanitary Arrangement at third Tube well site under Betai Zone I Water Supply Scheme under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000315/2023-2024 | 4322/ND | 26/09/2023 | 25/12/2023 | TOTAN DAS | 6.75 | 0 | 0 | 100
7 | NADIA |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Betai Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | SM/10414 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Betai W/S Scheme (Z-I,T/W-I) , Tehatta-I Block under Nadia District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000071/2023-2024 | 898/CDD | 18/07/2023 | 11/03/2024 | DIPALI CONSTUCTION | 18.57 | 0 | 0 | 100
8 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Betai Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | SM/10414 | Augmentation | Collection of Household data through mobile app for FHTC Connection (Phase-IV), under Nadia Division, P.H.E. Dte. |  | Junior Engineer 2 | ORD/000696/2023-2024 | 210/KLYSD-I | 09/02/2024 | 09/08/2024 | HORIZEN | 4.85 | 0 | 0 | 100
9 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Betai Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | SM/10414 | Augmentation | Quotation for new service connection at P.H-III under Betai Zone-I W/S Scheme, Dist-Nadia |  |  | BILL/04633/2023-2024 | BP-284-23-24 | 16/02/2024 | 16/02/2024 | W.B.S.E.D.C.L (GROUP NAZIRPUR C.C.C) | 10.9 | 0 | 0 | 0
10 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Betai Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | SM/10414 | Augmentation | Laying of Distribution System Including Specials, Valves & Pipe Supporting Structure All Complete, Augmentation Of Rising Main System, Providing FHTC, Construction Of 550 Cum Capacity 20 Mtr. Staging Height RCC Over Head Reservoir (With Pile Foundation), Pipe Connection And Cost Of Pipes, Specials And Soil Investigation For Construction Of One No. 550 Cum OHR Of Staging Height 20 Mtr Under Augmentation Of Ground Water Based Water Supply Scheme For Betai Zone-I To Accommodate FHTC under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000430/2022-2023 | 875/ND | 01/03/2023 | 01/03/2024 | M/S S.S ENTERPRISE | 610.04 | 0 | 0 | 54
11 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Betai Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | SM/10414 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 122 cum/hour capacity for Augmentation of Ground Based Water Supply Scheme at Betai Zone-I to accommodate FHTC including 3 Months Trial Run & 3 Years O&M under Tehatta Sub-division under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000736/2023-2024 | 1492/ND | 04/03/2024 | 22/02/2026 | MONDAL PRECISION PRIVATE LIMITED | 302.94 | 0 | 0 | 0
12 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Betai Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | SM/10414 | Augmentation | Construction of Boundary wall at Head Work Site & 2nd Tube Well ,3rd Tube Well site of Betai Zone- I Ground water based water supply scheme under Tehatta Sub-Division PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000752/2023-2024 | 1627/ND | 07/03/2024 | 03/03/2025 | GANGULY ENTERPRISE | 23.18 | 0 | 0 | 40
13 | NADIA |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Betai Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | SM/10414 | Augmentation | Continuation for Hiring of Diesel Driven Motor cab (BS-IV & Above) having contract carriage permit along with driver for the office of the Calcutta Mechanical Sub Division-ll (D),CDD, P.H.Enginering Dte. for supervision of JJM Related works. | Driller In Charge | Junior Engineer | ORD/000028/2024-2025 | 153/CMSD-II(D) | 30/07/2024 | 30/01/2025 | MD NIZAMUDDIN | 0.87 | 0 | 0 | 0
14 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Betai Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | SM/10414 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Betai Zone-I ground water based water supply scheme under Block_Tehatta-I Dist. - Nadia under EMD, PHE Dte. SM/10414 |  |  | ORD/000194/2025-2026 | 1119/EMD | 04/06/2025 | 02/09/2025 | MA ANNAPURNA ENTERPRISE | 24.48 | 0 | 0 | 0
Total | [13 empty] | 1326.04 | 0 | 0