## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-II to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | SM/10416 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-II to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. |  |  | VCH/000288/2022-2023 | 12/PFMS | 11/05/2022 | 11/05/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2.18 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-II to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | SM/10416 | Augmentation | Supplying, Laying, Fitting & Fixing of Distribution System including all type of specials, valves,pipes all complete, Augmentation of Rising Main, Providing FHTC including Supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule, saddle piece etc. all complete, Construction of 4.88 mtr. x 3.66 mtr. Size pump house including Sanitary Arrangement at H/W Site and 2nd Tube Well Site, Construction of OHR of 300 Cum capacity, Soil investigation for construction of OHR of 300 Cum capacity, Construction Of Boundary Wall At HW Site, Construction Of Boundary Wall At 2nd Tube Well Site And Construction Of Service Road At 2nd Tube Well Site for Natna Zone-II to accommodate FHTC in Tehatta-I Block of Nadia District under Nadia Division,PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000203/2023-2024 | 3538/ND | 11/08/2023 | 28/08/2026 | JOY HIND TUBEWELL'S, BELEDANGA GHOSHPARA 2ND LANE, P.O. KRISHNAGAR, DIST. NADIA. PIN-741101. | 560.77 | 216.06 | 38.53 | 55
3 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-II to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | SM/10416 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 30/01/2024 | IMAGIN | 96.97 | 2.8 | 2.89 | 40
4 | NADIA |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-II to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | SM/10416 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Nathna W/S Scheme (Z-II,T/W-I & II) , Tehatta-I Block under Nadia District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000070/2023-2024 | 902/CDD | 18/07/2023 | 15/11/2023 | SANKAR PRASAD DUTTA & CO. | 37.16 | 30.75 | 82.75 | 50
5 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-II to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | SM/10416 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under MADHPUR W/S Scheme, Block- Karimpur-I AND NATNA W/S Scheme, Block- Tehatta-I, Dist. - Nadia. NIET No.- 28 of EE/EMD of 2022-23 (Sl. No.- 03) | Assistant Engineer | Junior Engineer | ORD/001009/2022-2023 | 497/EMD | 24/01/2023 | 23/01/2025 | KARTICK BAL | 56.7 | 24.72 | 43.59 | 30
6 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-II to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | SM/10416 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000179/2022-2023 | 157/ND | 06/01/2023 | 06/01/2023 | Resource Division | 27.89 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-II to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | SM/10416 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000038/2023-2024 | 1886/ND | 26/04/2023 | 26/04/2023 | Resource Division | 10.67 | 0 | 0 | 0
8 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-II to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | SM/10416 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 53 m3/hr at Nathna Zone-II Water Supply Scheme within Tehatta-I Block under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000341/2024-2025 | 7106/ND | 06/12/2024 | 30/05/2026 | JOY HIND TUBEWELL'S | 185.75 | 0 | 0 | 0
9 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-II to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | SM/10416 | Augmentation | Collection of Household data through mobile app for FHTC Connection (Phase-I), under Nadia Division, P.H.E. Dte. |  | Junior Engineer 2 | ORD/000687/2023-2024 | 207/KLYSD-I | 09/02/2024 | 09/08/2024 | HORIZEN | 4.85 | 4.85 | 100 | 100
10 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-II to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | SM/10416 | Augmentation | Laying additional pipe line for distribution system and rising main for Nathna Zone-II PWSS under augmentation of Nathna Zone-II PWSS (Phase-II) under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000352/2024-2025 | 7051/ND | 02/12/2024 | 29/08/2025 | JOY HIND TUBEWELL'S | 100.01 | 0 | 0 | 75
11 | NADIA |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-II to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | SM/10416 | Augmentation | Supply & delivery of Bentonite Powder at site for construction of T/W at Nathna W/S Scheme (Z-II, TW-II), Tehatta-I Block, Nadia Under S&WSD, C.D.D, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000033/2024-2025 | 133/S&WSD | 14/06/2024 | 29/06/2024 | SANKAR PRASAD DUTTA & CO. | 0.49 | 0.13 | 26.48 | 100
12 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-II to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | SM/10416 | Augmentation | Quotation for new service connection at Pump House No-I under Natna w/s scheme, Dist-Nadia. |  |  | BILL/05673/2023-2024 | BP-377-23-24 | 22/03/2024 | 22/03/2024 | W.B.S.E.D.C.L (TEHATTA CCC) | 6.29 | 0 | 0 | 0
13 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-II to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | SM/10416 | Augmentation | Quotation for new service connection at Pump House No-II under Natna w/s Scheme, Dist-Nadia. |  |  | BILL/05672/2023-2024 | BP-378-23-24 | 22/03/2024 | 22/03/2024 | W.B.S.E.D.C.L (TEHATTA CCC) | 5.88 | 0 | 0 | 0
14 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-II to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | SM/10416 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Nathna ground water based water supply scheme under Block_ Tehatta-I Dist. - Nadia under EMD, PHE Dte. SM/10416 | Assistant Engineer |  | ORD/000188/2025-2026 | 1126/EMD | 04/06/2025 | 02/09/2025 | DITHI ENTERPRISE | 16.89 | 0 | 0 | 0
Total | [13 empty] | 1112.5 | 279.31 | 25.11