## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for GOBRAPOTA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte | SM/10417 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for GOBRAPOTA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte |  |  | VCH/000293/2022-2023 | 15/PFMS | 11/05/2022 | 11/05/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.8 | 0 | 0 | 0
2 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for GOBRAPOTA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte | SM/10417 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under Gobrapota Naldaha W/S Scheme, Block- Krishnagar-I , Dist. - Nadia. NIET No. 33 of EE/EMD of 2022-23 (Sl. No.- 10) | Assistant Engineer | Junior Engineer | ORD/001919/2022-2023 | 1175/EMD | 21/03/2023 | 20/04/2023 | SWAPAN KUMAR BHANJA | 18.62 | 14.2 | 76.23 | 75
3 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for GOBRAPOTA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte | SM/10417 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete and Construction Of 350 Cum Capacity 20 Mtr. Staging Height Rcc Over Head Reservoir (With Pile Foundation), Pipe Connection And Cost Of Pipes, Specials, Soil investigation for the work of construction of 350 cum OHR staging height 20 mtr., Construction Of 1 (One) No. Pump House (4.88m X 3.66m) Including Sanitary Arrangement And Construction Of Boundary Wall for Augmentation of Ground Based Water Supply Scheme at GOBRAPOTA to accommodate FHTC within Krishnagar-I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte | Assistant Engineer |  | ORD/000199/2023-2024 | 3509/ND | 10/08/2023 | 10/08/2024 | M/S GHOSH CONSTRUCTION, SUKUL ROAD, P.O-KRISHNAGAR, DIST.NADIA, PIN-741101, WB | 587.44 | 0 | 0 | 0
4 | NADIA |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for GOBRAPOTA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte | SM/10417 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Gobrapota W/S Scheme (TW-I) , Krishnagar-I Block under Nadia District, Central Drilling Division, P.H.E. Dte. |  |  | ORD/000134/2023-2024 | 1658/CDD | 17/10/2023 | 16/11/2023 | MENAKA ENTERPRISE | 18.88 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for GOBRAPOTA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte | SM/10417 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000152/2022-2023 | 122/ND | 05/01/2023 | 05/01/2023 | Resource Division | 99.77 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for GOBRAPOTA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte | SM/10417 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 30/01/2024 | IMAGIN | 96.97 | 1.4 | 1.44 | 40
7 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for GOBRAPOTA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte | SM/10417 | Augmentation | Construction of 2 nos Pump House (3.6mtr. X 3.0 mtr.) at 1st & 2nd T/W site for Gobrapota water supply scheme under Krishnagar Sub-Division under Nadia Division PHE Dte. | Assistant Engineer |  | ORD/000009/2024-2025 | 3263/ND | 10/06/2024 | 25/07/2024 | M/S RAJESH CONSTRUCTION | 12.17 | 0 | 0 | 0
8 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for GOBRAPOTA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte | SM/10417 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000153/2023-2024 | 264/ND | 11/01/2024 | 11/01/2024 | Resource Division | 17.22 | 0 | 0 | 0
Total | [13 empty] | 854.88 | 15.6 | 1.82