## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Karimpur-Jalangi PWSS Zone-VII to accommodate FHTC in Karimpur-I block with in Nadia District under Nadia Division, PHE Dte. | SM/10419 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Karimpur Jalangi Zone-VII to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000098/2022-2023 | 3403/ND | 01/08/2022 | 24/07/2025 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 326.43 | 278.26 | 85.24 | 98
2 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Karimpur-Jalangi PWSS Zone-VII to accommodate FHTC in Karimpur-I block with in Nadia District under Nadia Division, PHE Dte. | SM/10419 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000066/2022-2023 | 4316/ND | 29/09/2022 | 29/09/2022 | Resource Division | 21.75 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Karimpur-Jalangi PWSS Zone-VII to accommodate FHTC in Karimpur-I block with in Nadia District under Nadia Division, PHE Dte. | SM/10419 | Augmentation | Augmentation of Ground Water Based Karimpur-Jalangi PWSS Zone-VII to accommodate FHTC in Karimpur-I block with in Nadia District under Nadia Division, PHE Dte. |  |  | VCH/000207/2022-2023 | 31/PFMS | 20/05/2022 | 20/05/2022 | RADIANT | 2.99 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Karimpur-Jalangi PWSS Zone-VII to accommodate FHTC in Karimpur-I block with in Nadia District under Nadia Division, PHE Dte. | SM/10419 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000186/2022-2023 | 150/ND | 06/01/2023 | 06/01/2023 | Resource Division | 2.34 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Karimpur-Jalangi PWSS Zone-VII to accommodate FHTC in Karimpur-I block with in Nadia District under Nadia Division, PHE Dte. | SM/10419 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000047/2023-2024 | 1900/ND | 27/04/2023 | 27/04/2023 | Resource Division | 14.22 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Karimpur-Jalangi PWSS Zone-VII to accommodate FHTC in Karimpur-I block with in Nadia District under Nadia Division, PHE Dte. | SM/10419 | Augmentation | Repairing and renovation of Elevated Reservoir , Pump House ,boundary wall of ground based piped water supply scheme for Karimpur Jalangi Zone-VII water supply scheme under Tehatta Sub Division in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000372/2024-2025 | 7058/ND | 04/12/2024 | 27/02/2026 | TULIP ENGINEER'S CO-OP SOCIETY LTD | 31.24 | 0 | 0 | 40
7 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Karimpur-Jalangi PWSS Zone-VII to accommodate FHTC in Karimpur-I block with in Nadia District under Nadia Division, PHE Dte. | SM/10419 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Replacement Tube Well in connection to Accommodate FHTC at Pump House No.-I , II Zone-VII under Karimpur-Jalangi ground water based water supply scheme under Block_ Karimpur-I Dist. - North 24PGS under EMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002969/2023-2024 | 872/EMD | 15/03/2024 | 01/12/2024 | TARUN KUMAR BHATTACHARYA | 25.34 | 0 | 0 | 100
8 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Karimpur-Jalangi PWSS Zone-VII to accommodate FHTC in Karimpur-I block with in Nadia District under Nadia Division, PHE Dte. | SM/10419 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme (Phase- II) at Karimpur Jalangi Zone-VIPart-A & B W/S to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000229/2025-2026 | 2035/ND | 29/04/2025 | 28/07/2025 | BALAJI UDDYOG | 111.41 | 0 | 0 | 0
Total | [13 empty] | 535.71 | 278.26 | 51.94