## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Habibpur PWSS to accommodate FHTC in Ranaghat-I block with in Nadia District under Nadia Division, PHE Dte. | SM/10420 | Augmentation | Augmentation of Ground Water Based Habibpur PWSS to accommodate FHTC in Ranaghat-I block with in Nadia District under Nadia Division, PHE Dte. |  |  | VCH/000354/2022-2023 | 54/PFMS | 22/06/2022 | 22/06/2022 | RADIANT | 3.21 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Habibpur PWSS to accommodate FHTC in Ranaghat-I block with in Nadia District under Nadia Division, PHE Dte. | SM/10420 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000193/2022-2023 | 695/ND | 17/02/2023 | 17/02/2023 | Resource Division | 69.17 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Habibpur PWSS to accommodate FHTC in Ranaghat-I block with in Nadia District under Nadia Division, PHE Dte. | SM/10420 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000032/2023-2024 | 1869/ND | 26/04/2023 | 26/04/2023 | Resource Division | 28.48 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Habibpur PWSS to accommodate FHTC in Ranaghat-I block with in Nadia District under Nadia Division, PHE Dte. | SM/10420 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000102/2023-2024 | 3542/ND | 11/08/2023 | 11/08/2023 | Resource Division | 105.14 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Habibpur PWSS to accommodate FHTC in Ranaghat-I block with in Nadia District under Nadia Division, PHE Dte. | SM/10420 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000070/2023-2024 | 2293/ND | 29/05/2023 | 29/05/2023 | Resource Division | 21.56 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Habibpur PWSS to accommodate FHTC in Ranaghat-I block with in Nadia District under Nadia Division, PHE Dte. | SM/10420 | Augmentation | Providing Functional Household Tap Connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for augmentation of Ground Water Based Water Supply Scheme for Habibpur to accommodate FHTC in Ranaghat-I block of Nadia District under Nadia Division P.H.Engineering Dte. (PART-I) | Assistant Engineer | Junior Engineer 2 | ORD/000341/2022-2023 | 240/ND | 13/01/2023 | 04/04/2025 | M/S DIPAK ENTERPRISE | 401.25 | 334.94 | 83.48 | 95
7 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Habibpur PWSS to accommodate FHTC in Ranaghat-I block with in Nadia District under Nadia Division, PHE Dte. | SM/10420 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under HABIBPUR W/S Scheme, Block-Ranaghat I , Dist. - Nadia. NIET No.- 36 of EE/EMD of 2022-23 (Sl. No.- 06) | Assistant Engineer | Junior Engineer | ORD/000015/2023-2024 | 1578/EMD | 24/04/2023 | 01/07/2025 | BIDYUT KUMAR MUKHERJEE | 12.79 | 0 | 0 | 100
Total | [13 empty] | 641.6 | 334.94 | 52.2