## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | SM/10421 | Augmentation | Laying of Distribution system including specials, valves & pipe supporting structure all complete & providing FHTC at Augmentation of ground water based water supply scheme for Natna Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division PHe Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000086/2022-2023 | 3292/ND | 27/07/2022 | 25/10/2022 | JOY HIND TUBEWELL'S | 172.64 | 172.47 | 99.9 | 100
2 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | SM/10421 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000021/2022-2023 | 3524/ND | 05/08/2022 | 05/08/2022 | Resource Division | 4.6 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | SM/10421 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000063/2022-2023 | 4329/ND | 29/09/2022 | 29/09/2022 | Resource Division | 10.55 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | SM/10421 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. |  |  | VCH/000356/2022-2023 | 56/PFMS | 22/06/2022 | 22/06/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2.84 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | SM/10421 | Augmentation | Special repair and renovation work at Nathna pump house no: 2(Head work site) under Nathna w/s zone:1, Tehatta -I under Kalyani Sub-Div-I, Nadia Division PHE Dte. | Assistant Engineer |  | ORD/000003/2023-2024 | 495/ Kly SD-I | 06/04/2023 | 06/05/2023 | M/S DREAM INFRASTRUCTURE | 2 | 1.94 | 97.05 | 10
6 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | SM/10421 | Augmentation | Special repair and renovation work at Nathna pump house no: 1 under Nathna w/s zone:1, Tehatta -I under Kalyani Sub-Div-I, Nadia Division PHE Dte. | Assistant Engineer |  | ORD/000004/2023-2024 | 496/ Kly SD-1 | 06/04/2023 | 06/05/2023 | GANGULY ENTERPRISE | 2.37 | 2.25 | 94.66 | 10
7 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | SM/10421 | Augmentation | Repairing and renovation of Boundary Wall at Nathna pump house no: 2 (Head Work site) under Nathna w/s zone:1, Tehatta -I under Kalyani Sub-Div-I, Nadia Division PHE Dte. | Assistant Engineer |  | ORD/000002/2023-2024 | 494/ Kly SD-I | 06/04/2023 | 06/05/2023 | M/S BISWAS ENTERPRISE | 4.84 | 4.84 | 99.98 | 5
8 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | SM/10421 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 36 m3/hr at Nathna Zone-I Water Supply Scheme within Tehatta-I Block under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000108/2024-2025 | 4340/ND | 07/08/2024 | 28/07/2026 | MERCURY ENGINEERING COMPANY | 166.08 | 0 | 0 | 0
9 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | SM/10421 | Augmentation | Collection of Household data through mobile app for FHTC Connection (Phase-II) under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000694/2023-2024 | 208/KLYSD-I | 09/02/2024 | 09/08/2024 | HORIZEN | 4.85 | 4.85 | 100 | 100
10 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | SM/10421 | Augmentation | Laying additional pipe line for distribution system and rising main for Nathna Zone-II PWSS under augmentation of Nathna Zone-II PWSS (Phase-II) under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000352/2024-2025 | 7051/ND | 02/12/2024 | 29/08/2025 | JOY HIND TUBEWELL'S | 100.01 | 0 | 0 | 75
11 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | SM/10421 | Augmentation | Repair and renovation works of R.C.C. Elevated Reservoir (190 cum) at Natna Zone-I water supply scheme under Tehatta Sub Division in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000479/2024-2025 | 7265/ND | 13/12/2024 | 13/03/2025 | BABLU MALLICK | 16.98 | 0 | 0 | 100
12 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | SM/10421 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Nathna Zone-II Ground Based Water Supply Scheme under Tehatta-I Block under Nadia Division, P.H.E Dte. in connection with Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Nathna Zone-II at Tehatta-I Block by Augmentation of Ground Water based PWSS for Nathna Zone-II Water Supply Schemes under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000742/2024-2025 | 420/ND | 27/01/2025 | 23/11/2025 | NIVEDITA CONSTRUCTION | 22.08 | 0 | 0 | 0
13 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | SM/10421 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme (Phase- III) at village Nazirpur, Bagadoba, Chhitka, Aztullanagar under Tehatta-I Block to accommodate FHTC under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000019/2025-2026 | 1805/ND | 22/04/2025 | 17/01/2026 | M/S DIPAK ENTERPRISE | 71.65 | 0 | 0 | 30
14 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | SM/10421 | Augmentation | Laying of Distribution system including specials, valves & pipe supporting structure all complete & providing FHTC at Augmentation of ground water based water supply scheme for Natna Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division PHe Dte. |  |  | BILL/00670/2024-2025 | BP-2024-025-419 | 28/03/2025 | 28/03/2025 | JOY HIND TUBEWELL'S | 9.15 | 0 | 0 | 0
Total | [13 empty] | 590.64 | 186.35 | 31.55