## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing FHTC by Augmentation of Ground Water Based Piped Water Supply Scheme for PURBA KHAMAR SIMULIA Block: Hanskhali, Dist: Nadia | SM/10422 | Augmentation | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete by augmentation of Purba Khamarsimulia Water Supply scheme Hanskhali block in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000099/2022-2023 | 3404/ND | 01/08/2022 | 25/07/2024 | B.M. ENGINEERING & CONSTRUCTION | 330.45 | 252.33 | 76.36 | 92
2 | NADIA |  | Nadia Division | Providing FHTC by Augmentation of Ground Water Based Piped Water Supply Scheme for PURBA KHAMAR SIMULIA Block: Hanskhali, Dist: Nadia | SM/10422 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000061/2022-2023 | 4320/ND | 29/09/2022 | 29/09/2022 | Resource Division | 0.02 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Providing FHTC by Augmentation of Ground Water Based Piped Water Supply Scheme for PURBA KHAMAR SIMULIA Block: Hanskhali, Dist: Nadia | SM/10422 | Augmentation | Providing FHTC by Augmentation of Ground Water Based Piped Water Supply Scheme for PURBA KHAMAR SIMULIA Block: Hanskhali, Dist: Nadia |  |  | VCH/000285/2022-2023 | 10/PFMS | 11/05/2022 | 11/05/2022 | HORIZEN | 2.89 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Providing FHTC by Augmentation of Ground Water Based Piped Water Supply Scheme for PURBA KHAMAR SIMULIA Block: Hanskhali, Dist: Nadia | SM/10422 | Augmentation | Supplying and laying of distribution system including providing Functional Household Tap Connection (FHTC) for Augmentation of Purbakhamar Simulia Piped Water Supply Scheme under Ranaghat Sub-Division, under Nadia Division, PHE Dte.. | Assistant Engineer | Junior Engineer 1 | ORD/000417/2023-2024 | 5224/ND | 24/11/2023 | 14/09/2026 | B.M. ENGINEERING & CONSTRUCTION | 215.24 | 134.98 | 62.71 | 75
5 | NADIA |  | Nadia Division | Providing FHTC by Augmentation of Ground Water Based Piped Water Supply Scheme for PURBA KHAMAR SIMULIA Block: Hanskhali, Dist: Nadia | SM/10422 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000097/2023-2024 | 2584/ND | 13/06/2023 | 13/06/2023 | Resource Division | 15.12 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | Providing FHTC by Augmentation of Ground Water Based Piped Water Supply Scheme for PURBA KHAMAR SIMULIA Block: Hanskhali, Dist: Nadia | SM/10422 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000029/2023-2024 | 1879/ND | 26/04/2023 | 26/04/2023 | Resource Division | 13.4 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | Providing FHTC by Augmentation of Ground Water Based Piped Water Supply Scheme for PURBA KHAMAR SIMULIA Block: Hanskhali, Dist: Nadia | SM/10422 | Augmentation | Construction of Backwash chamber of AIRP at Head Work Site & Renovation of Gravity Type AIRP in Purba Khamarsimulia PWSS within Ranaghat Sub-Division under Nadia Division PHE Dte.Capacity 105.00 Cu.m/hr | Assistant Engineer | Junior Engineer 1 | ORD/000469/2023-2024 | 136/ND | 09/01/2024 | 08/04/2024 | M/S R.K.ENTERPRISE | 99.27 | 0 | 0 | 0
8 | NADIA |  | Nadia Division | Providing FHTC by Augmentation of Ground Water Based Piped Water Supply Scheme for PURBA KHAMAR SIMULIA Block: Hanskhali, Dist: Nadia | SM/10422 | Augmentation | Repairing of PH-II and Construction of Sanitary arrangement under augmentation of Purba Khamarsimulia under Ranaghat Sub-Division under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000391/2024-2025 | 1427/RSD | 19/11/2024 | 03/01/2025 | MANARAMA ENTERPRISE | 2.15 | 0 | 0 | 100
9 | NADIA |  | Eastern Mechanical | Providing FHTC by Augmentation of Ground Water Based Piped Water Supply Scheme for PURBA KHAMAR SIMULIA Block: Hanskhali, Dist: Nadia | SM/10422 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Replacement Tube Well in connection to Accommodate FHTC at Pump House No.-I , II under Purba Khamar Simulia ground water based water supply scheme under Block_ Hanskhali Dist. - Nadia under EMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000016/2024-2025 | 1308/EMD | 09/05/2024 | 08/06/2024 | SHIVAM ENTERPRISE | 23.6 | 21.7 | 91.91 | 100
10 | NADIA |  | Nadia Division | Providing FHTC by Augmentation of Ground Water Based Piped Water Supply Scheme for PURBA KHAMAR SIMULIA Block: Hanskhali, Dist: Nadia | SM/10422 | Augmentation | Repairing of Pump house-I with sanitary arrangement under augmentation of Purba Khamarsimulia piped water supply scheme under Ranaghat Sub-Division, under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000292/2024-2025 | 1278/RSD | 04/10/2024 | 18/11/2024 | ABHAYANANDA ENTERPRISE | 1.9 | 0 | 0 | 100
11 | NADIA |  | Eastern Mechanical | Providing FHTC by Augmentation of Ground Water Based Piped Water Supply Scheme for PURBA KHAMAR SIMULIA Block: Hanskhali, Dist: Nadia | SM/10422 | Augmentation | Supply, delivery, installation Commissioning of Electro Mechanical Equipments and allied works at PURBA KHAMAR SIMULIA W/S Scheme Block- Hanskhali under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia. [SM/10422] | Assistant Engineer |  | ORD/000146/2025-2026 | 1147/EMD | 04/06/2025 | 02/09/2025 | M.S. ENTERPRISE | 51.04 | 0 | 0 | 0
12 | NADIA |  | Nadia Division | Providing FHTC by Augmentation of Ground Water Based Piped Water Supply Scheme for PURBA KHAMAR SIMULIA Block: Hanskhali, Dist: Nadia | SM/10422 | Augmentation | Supplying and laying of distribution and rising main for Augmentation of Ground water based water supply scheme of Purba Khamarsimulia under Hanskhali Block under Ranaghat Sub-Division under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000099/2025-2026 | 2264/ND | 15/05/2025 | 10/05/2026 | B.M. ENGINEERING & CONSTRUCTION | 75.28 | 0 | 0 | 0
13 | NADIA |  | Nadia Division | Providing FHTC by Augmentation of Ground Water Based Piped Water Supply Scheme for PURBA KHAMAR SIMULIA Block: Hanskhali, Dist: Nadia | SM/10422 | Augmentation | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 11/10/2025 | IMAGIN | 96.97 | 0 | 0 | 0
14 | NADIA |  | Nadia Division | Providing FHTC by Augmentation of Ground Water Based Piped Water Supply Scheme for PURBA KHAMAR SIMULIA Block: Hanskhali, Dist: Nadia | SM/10422 | Augmentation | Construction and installation of MANIFOLD and allied works at Head Works site under Purba Khamarshimulia Ground Based Water Supply Scheme under Hanskhali Block under Nadia Division,P.H.E Dte. in connection with uniform distribution of drinking water through FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) . | Assistant Engineer | Junior Engineer 1 | ORD/000634/2025-2026 | 3436/F-6104/ND | 22/07/2025 | 15/10/2026 | BISHAL CONSTRUCTION | 11.9 | 0 | 0 | 0
15 | NADIA |  | Nadia Division | Providing FHTC by Augmentation of Ground Water Based Piped Water Supply Scheme for PURBA KHAMAR SIMULIA Block: Hanskhali, Dist: Nadia | SM/10422 | Augmentation | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete by augmentation of Purba Khamarsimulia Water Supply scheme Hanskhali block in Nadia District under Nadia Division P.H.Engineering Dte. |  |  | BILL/01082/2025-2026 |  | 24/12/2025 | 24/12/2025 | B.M. ENGINEERING & CONSTRUCTION | 13.38 | 0 | 0 | 0
Total | [13 empty] | 952.61 | 409.01 | 42.94