## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ISWARCHANDRAPUR to Accommodate FHTC in Tehatta-II block of Nadia district under Nadia division P.H.E. Dte | SM/10423 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for ISWARCHANDRAPUR to Accommodate FHTC in Tehatta-II block of Nadia district under Nadia division P.H.E. Dte |  |  | VCH/000289/2022-2023 | 13/PFMS | 11/05/2022 | 11/05/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2.6 | 0 | 0 | 0
2 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for ISWARCHANDRAPUR to Accommodate FHTC in Tehatta-II block of Nadia district under Nadia division P.H.E. Dte | SM/10423 | Augmentation | Supply, Delivery Installation of Submersible Pumping Machinery alongwith allied Electro Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. rejuvenation to Accommodate FHTC at Pump House No.- I AND II under Iswarchandrapur W/S Scheme, Block Tehatta II, Dist. Nadia. NIET No. 23 of EE/EMD of 2022-23 (Sl. No.- 01) |  |  | ORD/000884/2022-2023 | 152/EMD | 06/01/2023 | 05/02/2023 | M/S. G.P. ENTERPRISE | 21.36 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ISWARCHANDRAPUR to Accommodate FHTC in Tehatta-II block of Nadia district under Nadia division P.H.E. Dte | SM/10423 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000060/2022-2023 | 4308/ND | 29/09/2022 | 29/09/2022 | Resource Division | 5.94 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ISWARCHANDRAPUR to Accommodate FHTC in Tehatta-II block of Nadia district under Nadia division P.H.E. Dte | SM/10423 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000178/2022-2023 | 155/ND | 06/01/2023 | 06/01/2023 | Resource Division | 0.96 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ISWARCHANDRAPUR to Accommodate FHTC in Tehatta-II block of Nadia district under Nadia division P.H.E. Dte | SM/10423 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Iswarchandrapur to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 1,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000095/2022-2023 | 3382/ND | 29/07/2022 | 27/10/2022 | M/S SHIL & CO. | 79.62 | 0 | 0 | 98
6 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ISWARCHANDRAPUR to Accommodate FHTC in Tehatta-II block of Nadia district under Nadia division P.H.E. Dte | SM/10423 | Augmentation | Additional work of providing FHTC and additional work of Laying Distribution System in connection with Augmentation of Iswarchandrapur PWSS within Tehatta-II Block under RWS Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000726/2023-2024 | 1255/ND | 22/02/2024 | 07/04/2024 | M/S SHIL & CO. | 6.19 | 0 | 0 | 95
7 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ISWARCHANDRAPUR to Accommodate FHTC in Tehatta-II block of Nadia district under Nadia division P.H.E. Dte | SM/10423 | Augmentation | Repairing Works (existing OHR, Pump House, Boundary wall etc.) for Iswarchandrapur Water Supply Scheme Under RWS Nadia Sub-Divn.PHE Dte. | Assistant Engineer | Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000679/2023-2024 | 1178/ND | 21/02/2024 | 21/05/2024 | U-TURN CONSTRUCTION | 25.12 | 0 | 0 | 75
8 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ISWARCHANDRAPUR to Accommodate FHTC in Tehatta-II block of Nadia district under Nadia division P.H.E. Dte | SM/10423 | Augmentation | Health Check up of existing Over Head Reservoir(OHR) based on inspection and Non-destructive Test (NDT) at Iswarchandrapur PWSS, Tehatta-II Block under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000017/2024-2025 | 3374/ND | 14/06/2024 | 29/06/2024 | JADAVPUR UNIVERSITY | 3.48 | 0 | 0 | 100
9 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ISWARCHANDRAPUR to Accommodate FHTC in Tehatta-II block of Nadia district under Nadia division P.H.E. Dte | SM/10423 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 30 cum/hr at Iswarchandrapur water supply scheme including 3 Months Trial Run & 3 Years O&M within Tehatta-II block under RWS Nadia Sub-division under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000735/2023-2024 | 1491/ND | 04/03/2024 | 31/08/2024 | SATYABRATA CHAKRABORTY | 162.34 | 0 | 0 | 45
10 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for ISWARCHANDRAPUR to Accommodate FHTC in Tehatta-II block of Nadia district under Nadia division P.H.E. Dte | SM/10423 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under ISWARCHANDRAPUR ground water based water supply scheme under Block_ Tehatta-I Dist. - Nadia under EMD, PHE Dte. SM/10423 | Assistant Engineer |  | ORD/000185/2025-2026 | 1122/EMD | 04/06/2025 | 02/09/2025 | M/S DILIP MITRA | 16.93 | 0 | 0 | 0
Total | [13 empty] | 324.54 | 0 | 0