## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing FHTC by Augmentation for Fatepur PWSS Block: Hanskhali, District: Nadia | SM/10428 | Augmentation | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Fatepur W/S Scheme in Hanskhali Block of Nadia District under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000430/2021-2022 | 1050/RSD | 02/12/2021 | 01/01/2022 | HORIZEN | 2.74 | 2.59 | 94.49 | 100
2 | NADIA |  | Nadia Division | Providing FHTC by Augmentation for Fatepur PWSS Block: Hanskhali, District: Nadia | SM/10428 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000024/2023-2024 | 1875/ND | 26/04/2023 | 26/04/2023 | Resource Division | 17.01 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Providing FHTC by Augmentation for Fatepur PWSS Block: Hanskhali, District: Nadia | SM/10428 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000086/2023-2024 | 2314/ND | 29/05/2023 | 29/05/2023 | Resource Division | 3.28 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Providing FHTC by Augmentation for Fatepur PWSS Block: Hanskhali, District: Nadia | SM/10428 | Augmentation | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (Schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc., Construction of 100 cum capacity 20 Mtr. staging height RCC Over Head Reservoir, pipe connection and cost of pipes, specials and Soil Investigation for Construction of OHR all complete for augmentation of Ground Water Based Water Supply Scheme for Fatepur to accommodate FHTC in Hanskhali block of Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000447/2022-2023 | 964/ND | 09/03/2023 | 29/01/2026 | SUMAN CHAKRABORTY, A-7/40, KALYANI, NADIA | 175.81 | 87.93 | 50.01 | 92
5 | NADIA |  | Nadia Division | Providing FHTC by Augmentation for Fatepur PWSS Block: Hanskhali, District: Nadia | SM/10428 | Augmentation | Construction of Backwash chamber of AIRP at Head Work Site & Renovation of Gravity Type AIRP in Fatepur PWSS within Ranaghat Sub-Division under Nadia Division PHE Dte.Capacity 45.00 Cu.m/hr. | Assistant Engineer | Junior Engineer 3 | ORD/000583/2023-2024 | 839/ND | 06/02/2024 | 06/05/2025 | ZEOLITE FRESH INDIA | 58.36 | 0 | 0 | 60
6 | NADIA |  | Eastern Mechanical | Providing FHTC by Augmentation for Fatepur PWSS Block: Hanskhali, District: Nadia | SM/10428 | Augmentation | Supply, delivery, installation Commissioning of Electro Mechanical Equipments and allied works at Fatepur W/S Scheme Block- Hanskhali under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia. SM/10428 | Assistant Engineer |  | ORD/000148/2025-2026 | 1149/EMD | 04/06/2025 | 02/09/2025 | DEY ENTERPRISE | 33.38 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | Providing FHTC by Augmentation for Fatepur PWSS Block: Hanskhali, District: Nadia | SM/10428 | Augmentation | Repairing of Pump house-I with sanitary arrangement under augmentation of Fatepur piped water supply scheme under Ranaghat Sub-Division, under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000290/2024-2025 | 1275/RSD | 04/10/2024 | 18/11/2024 | K.D ENTERPRISE. | 1.89 | 0 | 0 | 100
8 | NADIA |  | Nadia Division | Providing FHTC by Augmentation for Fatepur PWSS Block: Hanskhali, District: Nadia | SM/10428 | Augmentation | Repairing of PH-II and Construction of Sanitary arrangement under augmentation of Fatepur under Ranaghat Sub-Division under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000379/2024-2025 | 1414/RSD | 19/11/2024 | 03/01/2025 | BUDDHADEV MONDAL | 2.15 | 0 | 0 | 85
Total | [13 empty] | 294.63 | 90.52 | 30.72