## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Kamgachi PWSS Part to accommodate FHTC in Ranaghat-I block with in Nadia District under Nadia Division, PHE Dte. | SM/10460 | Augmentation | Augmentation of Ground Water Based Kamgachi PWSS Part to accommodate FHTC in Ranaghat-I block with in Nadia District under Nadia Division, PHE Dte. |  |  | VCH/000204/2022-2023 | 28/PFMS | 20/05/2022 | 20/05/2022 | RADIANT | 3.53 | 0 | 0 | 0
2 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Kamgachi PWSS Part to accommodate FHTC in Ranaghat-I block with in Nadia District under Nadia Division, PHE Dte. | SM/10460 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under KAMGACHI(Z-I) W/S Scheme, Block- RANAGHAT I , Dist. - Nadia. NIET No.- 36 of EE/EMD of 2022-23 (Sl. No.- 07) | Assistant Engineer | Junior Engineer | ORD/000016/2023-2024 | 1579/EMD | 24/04/2023 | 24/05/2023 | CINZANO | 32.65 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Kamgachi PWSS Part to accommodate FHTC in Ranaghat-I block with in Nadia District under Nadia Division, PHE Dte. | SM/10460 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000033/2023-2024 | 1870/MD | 26/04/2023 | 26/04/2023 | Resource Division | 53.35 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Kamgachi PWSS Part to accommodate FHTC in Ranaghat-I block with in Nadia District under Nadia Division, PHE Dte. | SM/10460 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000053/2023-2024 | 2124/ND | 16/05/2023 | 16/05/2023 | Resource Division | 71.38 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Kamgachi PWSS Part to accommodate FHTC in Ranaghat-I block with in Nadia District under Nadia Division, PHE Dte. | SM/10460 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000066/2023-2024 | 2309/ND | 29/05/2023 | 29/05/2023 | Resource Division | 28.03 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Kamgachi PWSS Part to accommodate FHTC in Ranaghat-I block with in Nadia District under Nadia Division, PHE Dte. | SM/10460 | Augmentation | Construction of Pump House (3.6m x 3.0m) Including Sanitary Arrangement at Pump house No-1 site at Kamgachi Zone-I Water supply scheme under Ranaghat Sub ¿ Division, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000318/2024-2025 | 1279(A)RSD | 04/10/2024 | 18/12/2024 | M/S SAYAN ENTERPRISE | 4.46 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Kamgachi PWSS Part to accommodate FHTC in Ranaghat-I block with in Nadia District under Nadia Division, PHE Dte. | SM/10460 | Augmentation | Collection of Household data through mobile app for FHTC Connection at following schemes under Nadia Division PHE Dte.Schemes: i) Banpur ii) Dakshinpara (Zone-I)iii) Dakshinpara (Zone-II) iv) Kamgachi (Zone-I)(Part-I) v)Kamgachi (Zone-I)(Part-II)vi)Kamgachi (Zone-II)(Part-I) vii) Kamgachi (Zone-II)(Part-II) | Assistant Engineer | Junior Engineer 2 | ORD/000440/2022-2023 | 246/Kly SD-I | 27/02/2023 | 27/08/2023 | HORIZEN | 4.99 | 1.59 | 31.78 | 100
8 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Kamgachi PWSS Part to accommodate FHTC in Ranaghat-I block with in Nadia District under Nadia Division, PHE Dte. | SM/10460 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000113/2023-2024 | 27/ND | 03/01/2024 | 03/01/2024 | Resource Division | 61.68 | 0 | 0 | 0
9 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Kamgachi PWSS Part to accommodate FHTC in Ranaghat-I block with in Nadia District under Nadia Division, PHE Dte. | SM/10460 | Augmentation | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for augmentation of Ground Water Based Water Supply Scheme for Kamgachi Zone-II to accommodate FHTC in Ranaghat-I block of Nadia District under Nadia Division P.H.Engineering Dte. (PART-I) | Assistant Engineer | Junior Engineer 2 | ORD/000302/2022-2023 | 5352/ND | 22/12/2022 | 06/12/2025 | TANMOY ROY CHOWDHURY | 221.89 | 162.85 | 73.39 | 85
10 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Kamgachi PWSS Part to accommodate FHTC in Ranaghat-I block with in Nadia District under Nadia Division, PHE Dte. | SM/10460 | Augmentation | Repairing of Pump house-I with sanitary arrangement under augmentation of Kamgachi Zone-I piped water supply scheme under Ranaghat Sub-Division, under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000302/2024-2025 | 1276/RSD | 04/10/2024 | 18/11/2024 | SAGAR ENTERPRISE | 1.9 | 0 | 0 | 100
11 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Kamgachi PWSS Part to accommodate FHTC in Ranaghat-I block with in Nadia District under Nadia Division, PHE Dte. | SM/10460 | Augmentation | Surging of 05(Five) nos. big dia tube well at Dakshinpara Zone-II (Tubewell No- 1 & 2), Kamgachi Zone-I (Pump- 2), Magurkhali (Tubewell- 1) & Udaypur (Tubewell-2) water supply schemes under Ranaghat Sub-Division under Nadia Division P.H.E Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000137/2024-2025 | 875(A)RSD | 20/08/2024 | 20/09/2024 | PROGRESSIVE ENGINEERING & CONSTRUCTION | 2.84 | 2.18 | 76.84 | 100
Total | [13 empty] | 486.69 | 166.62 | 34.24