## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Tehatata (Phase-I) to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | SM/10461 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for Tehatata (Phase-I) to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. |  |  | VCH/000199/2022-2023 | 23/PFMS | 20/05/2022 | 20/05/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.14 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Tehatata (Phase-I) to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | SM/10461 | Augmentation | Laying of Distribution system including specials, valves & pipe supporting structure all complete & Providing FHTC at Augmentation of Ground Water Based Water Supply Scheme for Tehatta(Phase-I) to accommodate FHTC in Tehatta-I Block of Nadia District under Nadia Division PHE Dte. | Assistant Engineer |  | ORD/000102/2022-2023 | 3419/ND | 02/08/2022 | 31/10/2022 | H I ENTERPRISE | 465.49 | 460.45 | 98.92 | 93
3 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Tehatata (Phase-I) to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | SM/10461 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000064/2022-2023 | 4288/ND | 29/09/2022 | 29/09/2022 | Resource Division | 0.04 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Tehatata (Phase-I) to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | SM/10461 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000028/2022-2023 | 4020/ND | 16/09/2022 | 16/09/2022 | Resource Division | 70.86 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Tehatata (Phase-I) to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | SM/10461 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000168/2022-2023 | 112/ND | 05/01/2023 | 05/01/2023 | Resource Division | 2.19 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Tehatata (Phase-I) to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | SM/10461 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 135 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Tehatta to accommodate FHTC within Tehatta-I block under Tehatta Sub-division under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000094/2024-2025 | 4230/ND | 02/08/2024 | 29/01/2025 | TARUN KUMAR BHATTACHARYA | 315.65 | 0 | 0 | 0
Total | [13 empty] | 858.37 | 460.45 | 53.64