## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Karimpur-Jalangi PWSS Zone-IX(A) to accommodate FHTC in Karimpur-II block with in Nadia District under Nadia Division, PHE Dte. | SM/10462 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Karimpur Jalangi Zone-IX(A) to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000085/2022-2023 | 3278/ND | 26/07/2022 | 24/10/2022 | A ONE CONSTRUCTION | 138.52 | 133.83 | 96.62 | 99
2 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Karimpur-Jalangi PWSS Zone-IX(A) to accommodate FHTC in Karimpur-II block with in Nadia District under Nadia Division, PHE Dte. | SM/10462 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000065/2022-2023 | 4300/ND | 29/09/2022 | 29/09/2022 | Resource Division | 9.31 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Karimpur-Jalangi PWSS Zone-IX(A) to accommodate FHTC in Karimpur-II block with in Nadia District under Nadia Division, PHE Dte. | SM/10462 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000020/2022-2023 | 3523/ND | 05/08/2022 | 05/08/2022 | Resource Division | 25.05 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Karimpur-Jalangi PWSS Zone-IX(A) to accommodate FHTC in Karimpur-II block with in Nadia District under Nadia Division, PHE Dte. | SM/10462 | Augmentation | Augmentation of Ground Water Based Karimpur-Jalangi PWSS Zone-IX(A) to accommodate FHTC in Karimpur-II block with in Nadia District under Nadia Division, PHE Dte. |  |  | VCH/000206/2022-2023 | 30/PFMS | 20/05/2022 | 20/05/2022 | RADIANT | 2.61 | 0 | 0 | 0
5 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Karimpur-Jalangi PWSS Zone-IX(A) to accommodate FHTC in Karimpur-II block with in Nadia District under Nadia Division, PHE Dte. | SM/10462 | Augmentation | Supply, Delivery Installation of Submersible Pumping Machinery alongwith allied Electro Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. rejuvenation to Accomodate FHTC at Pump House No. I , II under KARIMPUR JALANGI Zone X A WS Scheme, Block Karimpur-II, Dist. Nadia. NIET No.- 23 of EE/EMD of 2022-23 (Sl. No.-14) | Assistant Engineer | Junior Engineer | ORD/000894/2022-2023 | 162/EMD | 06/01/2023 | 05/02/2023 | S.B.ENTERPRISE | 9.73 | 0 | 0 | 70
6 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Karimpur-Jalangi PWSS Zone-IX(A) to accommodate FHTC in Karimpur-II block with in Nadia District under Nadia Division, PHE Dte. | SM/10462 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under Karimpur jalangi (Zone-IX,A & B) W/S Scheme, Block-Tehatta-II, Dist. - Nadia. NIET No. 25 of EE/EMD of 2022-23 (Sl. No.- 19) |  |  | ORD/002779/2022-2023 | 419EMD | 20/01/2023 | 19/02/2023 | SINHA ELECTRICALS | 14.88 | 13.14 | 88.34 | 85
7 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Karimpur-Jalangi PWSS Zone-IX(A) to accommodate FHTC in Karimpur-II block with in Nadia District under Nadia Division, PHE Dte. | SM/10462 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Karimpur Jalangi Zone-IX A Ground Based Water Supply Scheme under Karimpur II Block under Nadia Division,P.H.E Dte. in connection with Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Karimpur Jalangi Zone-IX A at Karimpur II Block by Augmentation of Ground Water based PWSS for Karimpur Jalangi Zone-IX A Water Supply Schemes under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000640/2024-2025 | 7366/ND | 18/12/2024 | 16/02/2025 | SUBIR KUMAR DEY | 21.9 | 0 | 0 | 0
8 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Karimpur-Jalangi PWSS Zone-IX(A) to accommodate FHTC in Karimpur-II block with in Nadia District under Nadia Division, PHE Dte. | SM/10462 | Augmentation | Laying of additional pipeline for Dakshin Gopalpur & Nandanpur mouzas under Karimpur Jalangi Zone- IX(A) PWSS under Tehatta Sub-Division under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000652/2024-2025 | 7407/ND | 19/12/2024 | 10/09/2026 | SHYAMAL SHIL | 54.11 | 0 | 0 | 30
9 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Karimpur-Jalangi PWSS Zone-IX(A) to accommodate FHTC in Karimpur-II block with in Nadia District under Nadia Division, PHE Dte. | SM/10462 | Augmentation | Repairing and renovation of Elevated Reservoir , Pump House ,boundary wall of ground basaedpiped water supply scheme for Karimpur Jalangi Zone-IX(A) water supply scheme under Tehatta Sub Division in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000310/2024-2025 | 6838/ND | 12/11/2024 | 10/02/2025 | B.S. ENTERPRISE | 30.73 | 0 | 0 | 100
Total | [13 empty] | 306.83 | 146.98 | 47.9