## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-II) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/10472 | Augmentation | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-II) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE |  |  | VCH/000203/2022-2023 | 27/PFMS | 20/05/2022 | 20/05/2022 | ENVIROTECH SOLUTIONS | 2.56 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-II) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/10472 | Augmentation | Sinking of 1 no. Tubewell 300mm. x 200mm. dia and 150 mtr deep by direct rotary rig method for Teinpur Zone-II PWSS within Karimpur-II block under RWS Nadia sub-division under Nadia Division, PHE Dte. (SM / 10472) | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000038/2023-2024 | 2105/ND | 15/05/2023 | 29/06/2023 | MANISHIKA CONSTRUCTION | 14.18 | 12.16 | 85.8 | 100
3 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-II) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/10472 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000025/2022-2023 | 3896/ND | 08/09/2022 | 08/09/2022 | Resource Division | 39.48 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-II) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/10472 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000073/2022-2023 | 4327/ND | 29/09/2022 | 29/09/2022 | Resource Division | 2.69 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-II) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/10472 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000108/2023-2024 | 3786/ND | 24/08/2023 | 24/08/2023 | Resource Division | 1.6 | 0 | 0 | 0
6 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-II) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/10472 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under TEINPUR (ZONE-I ,II, III & IV) W/S Scheme, Block- Karimpur-II , Dist. - Nadia. NIET No.- 28 of EE/EMD of 2022-23 (Sl. No.- 06) | Assistant Engineer | Junior Engineer | ORD/001012/2022-2023 | 500/EMD | 24/01/2023 | 23/02/2023 | M/S DILIP MITRA | 64.62 | 10.18 | 15.75 | 85
7 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-II) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/10472 | Augmentation | Making & Fixation of Information Board (Swajal/Scheme) for various augmentation schemes with related to Jal Jeevan Mission ( JJM) under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000033/2024-2025 | 3450/ND | 20/06/2024 | 04/08/2024 | IMAGIN | 19.44 | 8.84 | 45.45 | 100
8 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-II) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/10472 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Teinpur Zone-II to accommodate FHTC within Karimpur-II block under RWS Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000135/2022-2023 | 3818/ND | 05/09/2022 | 23/11/2024 | CHANDAN ROY | 183.58 | 148.46 | 80.87 | 100
9 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-II) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/10472 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site of Teinpur zone-II PWSS under Karimpur-II Block under RWS Sub Division under Nadia Division-,P.H.E Dte. | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000329/2024-2025 | 7003/ND | 26/11/2024 | 21/11/2025 | DURGADAS BASU | 22.95 | 0 | 0 | 40
10 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-II) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/10472 | Augmentation | Repairing Works Of Tenpur (Zone-II) Water Supply Scheme,Karimpur-I Block Under RWS Nadia Sub Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000010/2024-2025 | 3264/ND | 10/06/2024 | 02/12/2025 | DURGADAS BASU | 25.29 | 10.53 | 41.65 | 45
11 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-II) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/10472 | Augmentation | Conversion of IEP to AIRP of capacity 32 Cu.m/hr at Teinpur Zone-II Water Supply Scheme within Karimpur-II block under RWS Nadia Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000798/2023-2024 | 1910/ND | 15/03/2024 | 13/07/2024 | MONDAL ENTERPRISE | 124.86 | 0 | 0 | 30
12 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-II) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/10472 | Augmentation | Repairing and renovation of Elevated Reservoir , Pump House and allied works for Fazilnagar within Karimpur-II Block Under Tehatta Sub-Division under Nadia Division P.H.E. Dte. | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000773/2024-2025 | 660/ND | 11/02/2025 | 08/11/2025 | U-TURN CONSTRUCTION | 50.44 | 0 | 0 | 70
Total | [13 empty] | 551.69 | 190.17 | 34.47