## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI ZONE-VIII PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/10473 | Augmentation | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Karimpur-Jalangi Z-8(I&II) W/S Scheme in Karimpur-II Block of Nadia District under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000402/2021-2022 | 317/TSD | 24/11/2021 | 24/12/2021 | RADIANT | 4.72 | 4.72 | 100 | 100
2 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI ZONE-VIII PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/10473 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000185/2022-2023 | 148/ND | 06/01/2023 | 06/01/2023 | Resource Division | 43.02 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI ZONE-VIII PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/10473 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000010/2023-2024 | 1853/ND | 26/04/2023 | 26/04/2023 | Resource Division | 33.06 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI ZONE-VIII PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/10473 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000082/2023-2024 | 2285/ND | 29/05/2023 | 29/05/2023 | Resource Division | 25.03 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI ZONE-VIII PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/10473 | Augmentation | Collection of Household data through mobile app for FHTC Connection at following schemes under Nadia Division PHE Dte.Schemes: i) Betai Zone-I ii) Karimpur Jalangi Zone-IXB iii)Fatepur iv)Anjangarh v)Kamalpur Zone-II vi) Shyamnagar vii)Karimpur Jalangi Zone-VIII | Assistant Engineer | Junior Engineer 2 | ORD/000007/2023-2024 | 497/ Kly SD-I | 06/04/2023 | 06/10/2023 | TECHVISION | 4.96 | 4.96 | 100 | 100
6 | NADIA |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI ZONE-VIII PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/10473 | Augmentation | Providing drilling crew and other allied works for construction of tube well (300mm x 200mm x 250 mtrs depth) by utilising departmental machineries for karimpur jalangi w/s scheme, (zone- IV & VIII), karimpur-I & II block under Nadia district, CDD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000068/2023-2024 | 137/CDD | 17/04/2023 | 17/05/2023 | SUNRISE ENGINEERING CORPORATION | 37.28 | 23.71 | 63.58 | 100
7 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI ZONE-VIII PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/10473 | Augmentation | Quotation charges for new service connection and security deposit at Karimpur Jalangi Zone-IX,B (Garaimari) PH-II under EMSD-III,Nadia |  |  | BILL/02300/2024-2025 | BP-192-24-25 | 16/12/2024 | 16/12/2024 | W.B.S.E.D.C.L (GROUP NAZIRPUR C.C.C) | 10.76 | 0 | 0 | 0
8 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI ZONE-VIII PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/10473 | Augmentation | Quotation charges for new service connection and security deposit at Karimpur Jalangi Zone-VIII (Barbakpur) PH-III under EMSD-III,Nadia |  |  | BILL/02240/2024-2025 | BP-177 | 13/12/2024 | 13/12/2024 | W.B.S.E.D.C.L (GROUP NAZIRPUR C.C.C) | 5.28 | 0 | 0 | 0
9 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI ZONE-VIII PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/10473 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc., Construction of 250 cum capacity 20 mtr. height RCC Over Head Reservoir (excluding pile foundation), pipe connection and cost of pipes, specials and Soil Investigation for determination the safe bearing capacity and other relevant parameters of soil for construction of 250 cum. O.H.R. all complete for Augmentation of Ground Based Water Supply Scheme at Karimpur Jalangi Zone-VIII to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. (SM/10473) | Assistant Engineer | Junior Engineer 1 | ORD/000428/2022-2023 | 843/ND | 28/02/2023 | 02/07/2026 | M/S TAPAS KUMAR CHAKRABORTY | 545.01 | 107.3 | 19.69 | 40
10 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI ZONE-VIII PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/10473 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accommodate FHTC under KARIMPUR JALANGI(Z-8) W/S Scheme, Block- Karimpur II, PALSONDHA W/S Scheme, Block- Tehatta II, & MAIDANPUR W/S Scheme, Block- Chapra, Dist. - Nadia. NIET No.- 33 of EE/EMD of 2022-23 (Sl. No.- 06) | Assistant Engineer | Junior Engineer | ORD/001923/2022-2023 | 1179/EMD | 21/03/2023 | 16/10/2025 | CREATIVE WATER & PROCESS TECHNOLOGIES PVT. LTD. | 77.9 | 0 | 0 | 85
11 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI ZONE-VIII PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/10473 | Augmentation | Construction Of Pump House (3.6x 3.0m) Including Sanitary Arrangemen and consruction of Boundary wall at 3rd Tube Well Site of Karimpur-Jalangi Zone- (VIII) Water Supply Scheme Under Tehatta Sub-Division PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000746/2023-2024 | 1624/ND | 07/03/2024 | 02/03/2025 | SAMAR ENTERPRISE | 10.92 | 0 | 0 | 100
12 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI ZONE-VIII PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/10473 | Augmentation | Detail route survey, design of distribution network and preparation of estimate, drawing & dpr for providing FHTC in Arabpur, Betai Zone II, Nathna Zone II, Andherkota, Karimpur Jalangi Zone VII W/S Scheme | Assistant Engineer | Junior Engineer 2 | ORD/000016/2025-2026 | 1802/ND | 22/04/2025 | 13/05/2025 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 11.11 | 0 | 0 | 100
Total | [13 empty] | 809.05 | 140.68 | 17.39