## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR ARABPUR PWSS BLOCK: KARIMPUR - I DISTRICT: NADIA | SM/10517 | Augmentation | PROVIDING FHTC BY AUGMENTATION FOR ARABPUR PWSS BLOCK: KARIMPUR - I DISTRICT: NADIA |  |  | VCH/000195/2022-2023 | 19/PFMS | 20/05/2022 | 20/05/2022 | HORIZEN | 2.67 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR ARABPUR PWSS BLOCK: KARIMPUR - I DISTRICT: NADIA | SM/10517 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000070/2022-2023 | 4276/ND | 29/09/2022 | 29/09/2022 | Resource Division | 7.53 | 0 | 0 | 0
3 | NADIA |  | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR ARABPUR PWSS BLOCK: KARIMPUR - I DISTRICT: NADIA | SM/10517 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under BANPUR W/S Scheme, Block- Krishnaganj, ARABPUR W/S Scheme, Block-Karimpur, BHIMPUR W/S Scheme, Block-Krishnagar AND MONIPOTA W/S Scheme, Block- Krishnagar-I, Dist. - Nadia. | Assistant Engineer | Junior Engineer | ORD/001444/2023-2024 | 5127/EMD | 04/09/2023 | 01/07/2025 | C.M.S. ENGINEERING CONCERN. | 70.97 | 0 | 0 | 12
4 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR ARABPUR PWSS BLOCK: KARIMPUR - I DISTRICT: NADIA | SM/10517 | Augmentation | Laying of additional pipeline for Fazilnagar Mouza and Phulkhali Mouza under Fazilnagar PWSS and Arabpur PWSS".under Tehatta Sub-Division under Nadia Division P.H.Engineering Dte. |  |  | ORD/000162/2024-2025 | 4905/ND | 10/09/2024 | 09/12/2024 | PATHIK PABAN NANDI | 41.67 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR ARABPUR PWSS BLOCK: KARIMPUR - I DISTRICT: NADIA | SM/10517 | Augmentation | Laying of additional pipeline for Arabpur PWSS"under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000120/2024-2025 | 4532/ND | 20/08/2024 | 16/02/2025 | BIDYUT KUMAR | 12.99 | 0 | 0 | 100
6 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR ARABPUR PWSS BLOCK: KARIMPUR - I DISTRICT: NADIA | SM/10517 | Augmentation | Laying of additional pipeline for Hazrakhali, Fulkhali, Betbaria, Marttajapur, Mollahad, Chaugachha, Haripur & Arabpur mouzas under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000831/2024-2025 | 246/ND | 14/01/2025 | 09/04/2026 | JOY HIND TUBEWELL'S | 153.86 | 0 | 0 | 30
7 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR ARABPUR PWSS BLOCK: KARIMPUR - I DISTRICT: NADIA | SM/10517 | Augmentation | Laying of additional pipeline for providing balance FHTC and inerease functionality in Baro Jangal, Majlishpur, Basotipara Villages under Karimpur-I Block under Tehatta Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000329/2025-2026 | .4686/4533/P-3/ND | 09/10/2025 | 07/01/2026 | JOY HIND TUBEWELL'S | 79.19 | 0 | 0 | 40
8 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR ARABPUR PWSS BLOCK: KARIMPUR - I DISTRICT: NADIA | SM/10517 | Augmentation | Repairing and renovation of Elevated Reservoir , Pump House ,boundary wall of ground basedpiped water supply scheme for Arabpur water supply scheme under Tehatta Sub Division in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000306/2024-2025 | 6835/ND | 12/11/2024 | 10/02/2025 | CHOWDHURY & CO. | 32.85 | 0 | 0 | 100
Total | [13 empty] | 401.73 | 0 | 0