## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-IV) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/10518 | Augmentation | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-IV) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE |  |  | VCH/000200/2022-2023 | 24/PFMS | 20/05/2022 | 20/05/2022 | ENVIROTECH SOLUTIONS | 2.43 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-IV) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/10518 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000075/2022-2023 | 4324/ND | 29/09/2022 | 29/09/2022 | Resource Division | 2.3 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-IV) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/10518 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000024/2022-2023 | 3898/ND | 08/09/2022 | 08/09/2022 | Resource Division | 18.84 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-IV) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/10518 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20 mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Teinpur Zone-IV to accommodate FHTC within Karimpur-II block under RWS Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000094/2022-2023 | 3381/ND | 29/07/2022 | 27/10/2022 | CHOWDHURY & CO. | 71.97 | 0 | 0 | 100
5 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-IV) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/10518 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under TEINPUR (ZONE-I ,II, III & IV) W/S Scheme, Block- Karimpur-II , Dist. - Nadia. NIET No.- 28 of EE/EMD of 2022-23 (Sl. No.- 06) | Assistant Engineer | Junior Engineer | ORD/001012/2022-2023 | 500/EMD | 24/01/2023 | 23/02/2023 | M/S DILIP MITRA | 64.62 | 0 | 0 | 85
6 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-IV) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/10518 | Augmentation | Renovation and modification of AIRP (Pressure Type) of capacity 20.87 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site in Teinpur Zone IV PWSS under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000008/2023-2024 | 1807/ND | 24/04/2023 | 22/10/2024 | MONDAL PRECISION PRIVATE LIMITED | 39.12 | 0 | 0 | 90
7 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-IV) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/10518 | Augmentation | Additional work of providing FHTC and additional work of Laying Distribution System in connection with Augmentation of Teinpur Zone-IV PWSS within Karimpur-II Block under RWS Nadia Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000006/2024-2025 | 3260/ND | 10/06/2024 | 03/09/2025 | DIAMOND ENGINEERS CO.OP SOCIETY LTD. | 82.42 | 0 | 0 | 80
Total | [13 empty] | 281.7 | 0 | 0