## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-I) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/10522 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Teinpur Zone-I to accommodate FHTC within Karimpur-II block under RWS Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000093/2022-2023 | 3380/ND | 29/07/2022 | 27/09/2022 | M/S FREEDOM CONSTRUCTION | 42.67 | 42.1 | 98.67 | 86
2 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-I) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/10522 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000072/2022-2023 | 4277/ND | 29/09/2022 | 29/09/2022 | Resource Division | 1.23 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-I) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/10522 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000023/2022-2023 | 3895/ND | 08/09/2022 | 08/09/2022 | Resource Division | 16.85 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-I) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/10522 | Augmentation | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-I) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE |  |  | VCH/000202/2022-2023 | 26/PFMS | 20/05/2022 | 20/05/2022 | ENVIROTECH SOLUTIONS | 2.44 | 0 | 0 | 0
5 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-I) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/10522 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under TEINPUR (ZONE-I ,II, III & IV) W/S Scheme, Block- Karimpur-II , Dist. - Nadia. NIET No.- 28 of EE/EMD of 2022-23 (Sl. No.- 06) | Assistant Engineer | Junior Engineer | ORD/001012/2022-2023 | 500/EMD | 24/01/2023 | 23/02/2023 | M/S DILIP MITRA | 64.62 | 10.71 | 16.57 | 85
6 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-I) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/10522 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000107/2023-2024 | 3789/ND | 24/08/2023 | 24/08/2023 | Resource Division | 1.6 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-I) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/10522 | Augmentation | Renovation and modification of AIRP (Pressure Type) & Construction of Backwash chamber for AIRP at Head Work Site in Teinpur ZONE-I PWSS under Nadia Division PHE Dte. Capacity- 15.5 cum/hr. | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000551/2023-2024 | 781/ND | 05/02/2024 | 05/05/2024 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 37.22 | 18.21 | 48.91 | 93
8 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-I) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/10522 | Augmentation | Repairing Works (existing OHR, Pump House, Boundary wall etc.) for Tenpur (Zone-I) Water Supply Scheme, Karimpur-I Block Under RWS Nadia Sub Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000676/2023-2024 | 1175/ND | 21/02/2024 | 17/11/2024 | CHOWDHURY & CO. | 25.11 | 10.44 | 41.56 | 95
9 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-I) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/10522 | Augmentation | Making & Fixation of Information Board (Swajal/Scheme) for various augmentation schemes with related to Jal Jeevan Mission ( JJM) under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000033/2024-2025 | 3450/ND | 20/06/2024 | 04/08/2024 | IMAGIN | 19.44 | 5.3 | 27.27 | 100
Total | [13 empty] | 211.18 | 86.75 | 41.08