## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI ZONE-V PWSS TO ACCOMMODATE FHTC IN KARIMPUR-I BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/10523 | Augmentation | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Karimpur-Jalangi Z-5 W/S Scheme in Karimpur-I Block of Nadia District under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000399/2021-2022 | 314/TSD | 24/11/2021 | 24/12/2021 | RADIANT | 2.98 | 0 | 0 | 100
2 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI ZONE-V PWSS TO ACCOMMODATE FHTC IN KARIMPUR-I BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/10523 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000109/2022-2023 | 5285/ND | 19/12/2022 | 19/12/2022 | Resource Division | 31.89 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI ZONE-V PWSS TO ACCOMMODATE FHTC IN KARIMPUR-I BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/10523 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000054/2023-2024 | 2283/ND | 29/05/2023 | 29/05/2023 | Resource Division | 16.79 | 0 | 0 | 0
4 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI ZONE-V PWSS TO ACCOMMODATE FHTC IN KARIMPUR-I BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/10523 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under KARIMPUR JALANGI (Z-IV, V & XB) W/S Scheme, Block-Karimpur I , Dist. - Nadia. NIET NO. - 33 OF EE/EMD OF 2022-23 (SL. NO. - 03) | Assistant Engineer | Junior Engineer | ORD/001926/2022-2023 | 1198/EMD | 22/03/2023 | 01/05/2025 | AVINABA ENGINEERING CONCERN | 62.41 | 0 | 0 | 80
5 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI ZONE-V PWSS TO ACCOMMODATE FHTC IN KARIMPUR-I BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/10523 | Augmentation | Repairing and renovation works of Pump House and allied works of ground based piped water supply scheme for Karimpur Jalangi Zone-V water supply scheme under Tehatta Sub Division in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer |  | ORD/000375/2024-2025 | 7060/ND | 04/12/2024 | 04/03/2025 | BANERJEE ENTERPRISE | 12.66 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI ZONE-V PWSS TO ACCOMMODATE FHTC IN KARIMPUR-I BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/10523 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc., Construction of 300 cum capacity 20 mtr. staging height RCC Over Head reservoir (Excluding pile Foundation), pipe connection and cost of pipes, specials and soil investigation all complete for Augmentation of Ground Based Water Supply Scheme at Karimpur Jalangi Zone-V to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000178/2022-2023 | 4386/ND | 13/10/2022 | 01/01/2026 | APURBA MANDAL | 339.55 | 0 | 0 | 95
7 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI ZONE-V PWSS TO ACCOMMODATE FHTC IN KARIMPUR-I BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/10523 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Karimpur Jalangi Zone-V Ground Based Water Supply Scheme under Karimpur I Block under Nadia Division,P.H.E Dte. in connection with Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Karimpur Jalangi Zone-V at Karimpur I Block by Augmentation of Ground Water based PWSS for Karimpur Jalangi Zone-V Water Supply Schemes under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000750/2024-2025 | 456/ND | 29/01/2025 | 30/03/2025 | DEL DELTA CONSTRUCTION | 23.39 | 0 | 0 | 0
8 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI ZONE-V PWSS TO ACCOMMODATE FHTC IN KARIMPUR-I BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/10523 | Augmentation | Laying of additional pipeline for Hazrakhali, Fulkhali, Betbaria, Marttajapur, Mollahad, Chaugachha, Haripur & Arabpur mouzas under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000831/2024-2025 | 246/ND | 14/01/2025 | 09/04/2026 | JOY HIND TUBEWELL'S | 153.86 | 0 | 0 | 30
9 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI ZONE-V PWSS TO ACCOMMODATE FHTC IN KARIMPUR-I BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/10523 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 49.81 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Karimpur Jalangi Zone-V to accommodate FHTC under Tehatta Sub-division under Nadia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000835/2024-2025 | 4353/ND | 07/08/2024 | 03/02/2025 | G.D. CONSTRUCTION AND CO. | 181.93 | 0 | 0 | 0
Total | [13 empty] | 825.48 | 0 | 0