## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for GANGNAPUR to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. | SM/10524 | Augmentation | Providing functional household tap connection including supply of 15mm dia PVC pipe of average length of 15 mtr along with laying of different dia UPVC pipe line and other allied works etc all complete for AUGMENTATION Of GANGNAPUR W/S scheme (for Gangnapur & Korabari Mouza) under Ranaghat Sub Division of Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 4 | ORD/000108/2022-2023 | 3530/ND | 05/08/2022 | 03/11/2022 | APURBA MANDAL | 393.18 | 388.5 | 98.81 | 80
2 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for GANGNAPUR to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. | SM/10524 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000068/2022-2023 | 4289/ND | 29/09/2022 | 29/09/2022 | Resource Division | 24.31 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for GANGNAPUR to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. | SM/10524 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000108/2022-2023 | 5202/ND | 14/12/2022 | 14/12/2022 | Resource Division | 38.66 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for GANGNAPUR to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. | SM/10524 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for GANGNAPUR to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. |  |  | VCH/000197/2022-2023 | 21/PFMS | 20/05/2022 | 20/05/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.87 | 0 | 0 | 0
5 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for GANGNAPUR to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. | SM/10524 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC at under GANGNAPUR W/S Scheme, Block-Ranaghat , Dist. - Nadia. NIET No.- 36 of EE/EMD of 2022-23 (Sl. No.- 11) | Assistant Engineer | Junior Engineer | ORD/000020/2023-2024 | 1583/EMD | 24/04/2023 | 24/05/2023 | A.S. ENTERPRISE | 25.94 | 0 | 0 | 0
6 | NADIA |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for GANGNAPUR to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. | SM/10524 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Gangnapur W/S Scheme (TW-I) , Ranaghat-II Block under Nadia District, Central Drilling Division, P.H.E. Dte. |  |  | ORD/000138/2023-2024 | 1234/CDD | 04/09/2023 | 04/10/2023 | DEV AND COMPANY | 18.88 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for GANGNAPUR to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. | SM/10524 | Augmentation | Laying of different dia UPVC pipe and other allied works etc. all complete for augmentation of Gangnapur W/S Scheme (for Gangnapur and Korabari Mouza) under Ranaghat Sub-Division of Nadia Division P.H. Engineering Dte. | Assistant Engineer | Junior Engineer 4 | ORD/000294/2023-2024 | 920/RSD | 13/09/2023 | 23/10/2023 | APURBA MONDAL, VILL+P.O. BADKULLA, DIST.NADIA, PIN-741121 W.B | 3.91 | 3.87 | 99.15 | 100
8 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for GANGNAPUR to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. | SM/10524 | Augmentation | Balance Laying of different dia UPVC pipe and other allied works etc. all complete for augmentation of Gangnapur W/S Scheme (for Gangnapur and Korabari Mouza) under Ranaghat Sub-Division of Nadia Division P.H. Engineering Dte. | Assistant Engineer | Junior Engineer 4 | ORD/000295/2023-2024 | 923/RSD | 14/09/2023 | 14/10/2023 | APURBA MONDAL, VILL+P.O. BADKULLA, DIST.NADIA, PIN-741121 W.B | 4.59 | 4.58 | 99.91 | 100
9 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for GANGNAPUR to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. | SM/10524 | Augmentation | Repairing of Pump house-I with sanitary arrangement under augmentation of Gangnapur piped water supply scheme under Ranaghat Sub-Division, under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 4 | ORD/000186/2024-2025 | 1145/RSD | 11/09/2024 | 26/10/2024 | B K ENGINEERING | 1.9 | 0.47 | 24.71 | 100
10 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for GANGNAPUR to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. | SM/10524 | Augmentation | Left-out Functional Household Tap Connection including Balance Laying of different dia UPVC pipe and other allied works etc. all complete of Gangnapur W/S Scheme (for Gangnapur and Korabari Mouza) under Ranaghat Sub Division of Nadia Divisio P.H. Engineering Dte. | Assistant Engineer | Junior Engineer 4 | ORD/000284/2024-2025 | 6713/ND | 30/10/2024 | 14/12/2024 | APURBA MANDAL | 16.79 | 4.43 | 26.41 | 100
11 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for GANGNAPUR to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. | SM/10524 | Augmentation | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 11/10/2025 | IMAGIN | 96.97 | 0 | 0 | 0
Total | [13 empty] | 630 | 401.86 | 63.79