## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KAMALPUR ZONE-I to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. | SM/10525 | Augmentation | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Kamalpur Zone-I W/S Scheme in Ranaghat-II Block of Nadia District under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000440/2021-2022 | 1060/RSD | 02/12/2021 | 01/01/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.64 | 4.64 | 100 | 100
2 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KAMALPUR ZONE-I to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. | SM/10525 | Augmentation | Additional Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Kamalpur Zone-I W/S Scheme in Ranaghat-I Block of Nadia District under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000742/2021-2022 | 1119/RSD | 21/12/2021 | 20/01/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 0.78 | 0.56 | 72 | 100
3 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KAMALPUR ZONE-I to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. | SM/10525 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000105/2022-2023 | 5104/ND | 08/12/2022 | 08/12/2022 | Resource Division | 188.62 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KAMALPUR ZONE-I to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. | SM/10525 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000069/2022-2023 | 4301/ND | 29/09/2022 | 29/09/2022 | Resource Division | 0.05 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KAMALPUR ZONE-I to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. | SM/10525 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000013/2023-2024 | 1859/ND | 26/04/2023 | 26/04/2023 | Resource Division | 84.8 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KAMALPUR ZONE-I to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. | SM/10525 | Augmentation | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for augmentation of Ground Water Based Water Supply Scheme for Kamalpur Zone-I to accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000128/2022-2023 | 3697/ND | 26/08/2022 | 24/11/2022 | HANNAN BUILDERS PRIVATE LIMITED | 592.18 | 546.44 | 92.28 | 95
7 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KAMALPUR ZONE-I to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. | SM/10525 | Augmentation | Repairing of PH-II and Construction of Sanitary arrangement under augmentation of Kamalpur Zone-I under Ranaghat Sub-Division under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000382/2024-2025 | 1418/RSD | 19/11/2024 | 03/01/2025 | RENUKA ENTERPRISE | 2.15 | 0 | 0 | 100
8 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KAMALPUR ZONE-I to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. | SM/10525 | Augmentation | Repairing of PH-III and Construction of Sanitary arrangement under augmentation of Kamalpur Zone-I under Ranaghat Sub-Division under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000675/2024-2025 | 1419/RSD | 19/11/2024 | 03/01/2025 | MAA ENTERPRISE | 2.15 | 0 | 0 | 100
9 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for KAMALPUR ZONE-I to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. | SM/10525 | Augmentation | Supply, delivery, installation Commissioning of Electro Mechanical Equipments and allied works at KAMALPUR ZONE-I W/S Scheme Block- Ranaghat-II under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia. [SM/10525] | Assistant Engineer |  | ORD/000136/2025-2026 | 1137/EMD | 04/06/2025 | 02/09/2025 | H.K. DAS & CO. | 52.38 | 0 | 0 | 0
10 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KAMALPUR ZONE-I to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. | SM/10525 | Augmentation | Construction and installation of MANIFOLD and allied works at Head Works site under Kamalpur Zone-I Ground Based Water Supply Scheme under Ranaghat-II Block under Nadia Division, P.H.E Dte. in connection with uniform distribution of drinking water through FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) | Assistant Engineer |  | ORD/000065/2025-2026 | 2374/ND | 22/05/2025 | 20/08/2025 | AREOCON | 11.89 | 0 | 0 | 0
Total | [13 empty] | 939.63 | 551.63 | 58.71