## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KAMALPUR ZONE-I to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. | SM/10525 | Augmentation | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Kamalpur Zone-I W/S Scheme in Ranaghat-II Block of Nadia District under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000440/2021-2022 | 1060/RSD | 02/12/2021 | 01/01/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.64 | 4.64 | 100 | 100
2 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KAMALPUR ZONE-I to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. | SM/10525 | Augmentation | Additional Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Kamalpur Zone-I W/S Scheme in Ranaghat-I Block of Nadia District under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000742/2021-2022 | 1119/RSD | 21/12/2021 | 20/01/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 0.78 | 0.56 | 72 | 100
3 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KAMALPUR ZONE-I to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. | SM/10525 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000105/2022-2023 | 5104/ND | 08/12/2022 | 08/12/2022 | Resource Division | 188.62 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KAMALPUR ZONE-I to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. | SM/10525 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000069/2022-2023 | 4301/ND | 29/09/2022 | 29/09/2022 | Resource Division | 0.05 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KAMALPUR ZONE-I to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. | SM/10525 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000013/2023-2024 | 1859/ND | 26/04/2023 | 26/04/2023 | Resource Division | 84.8 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KAMALPUR ZONE-I to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. | SM/10525 | Augmentation | Repairing of Pump house-I with sanitary arrangement under augmentation of Kamalpur Zone-I piped water supply scheme under Ranaghat Sub-Division, under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000293/2024-2025 | 1278(A)RSD | 04/10/2024 | 18/11/2024 | KUHELI ENTERPRISE | 1.89 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KAMALPUR ZONE-I to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. | SM/10525 | Augmentation | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for augmentation of Ground Water Based Water Supply Scheme for Kamalpur Zone-I to accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000128/2022-2023 | 3697/ND | 26/08/2022 | 24/11/2022 | HANNAN BUILDERS PRIVATE LIMITED | 592.18 | 546.44 | 92.28 | 95
8 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KAMALPUR ZONE-I to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. | SM/10525 | Augmentation | Laying 315 mm and 110 mm dia uPVC pipe line in place of damaged 315 mm and 110 mm dia uPVC pipe from Purba Naoapara to Kamalpur for smooth running of Ground Water Based Water Supply Scheme for Kamalpur Zone-I in Ranaghat-I block of Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000289/2023-2024 | 910/RSD | 13/09/2023 | 13/10/2023 | M/S BISWAS ENTERPRISE | 4.72 | 0 | 0 | 0
9 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KAMALPUR ZONE-I to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. | SM/10525 | Augmentation | Repairing of PH-II and Construction of Sanitary arrangement under augmentation of Kamalpur Zone-I under Ranaghat Sub-Division under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000382/2024-2025 | 1418/RSD | 19/11/2024 | 03/01/2025 | RENUKA ENTERPRISE | 2.15 | 0 | 0 | 100
10 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KAMALPUR ZONE-I to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. | SM/10525 | Augmentation | Repairing of PH-III and Construction of Sanitary arrangement under augmentation of Kamalpur Zone-I under Ranaghat Sub-Division under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000675/2024-2025 | 1419/RSD | 19/11/2024 | 03/01/2025 | MAA ENTERPRISE | 2.15 | 0 | 0 | 100
11 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for KAMALPUR ZONE-I to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. | SM/10525 | Augmentation | Supply, delivery, installation Commissioning of Electro Mechanical Equipments and allied works at KAMALPUR ZONE-I W/S Scheme Block- Ranaghat-II under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia. [SM/10525] | Assistant Engineer |  | ORD/000136/2025-2026 | 1137/EMD | 04/06/2025 | 02/09/2025 | H.K. DAS & CO. | 52.38 | 0 | 0 | 0
12 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KAMALPUR ZONE-I to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. | SM/10525 | Augmentation | Construction and installation of MANIFOLD and allied works at Head Works site under Kamalpur Zone-I Ground Based Water Supply Scheme under Ranaghat-II Block under Nadia Division, P.H.E Dte. in connection with uniform distribution of drinking water through FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) | Assistant Engineer |  | ORD/000065/2025-2026 | 2374/ND | 22/05/2025 | 20/08/2025 | AREOCON | 11.89 | 0 | 0 | 0
Total | [13 empty] | 946.25 | 551.63 | 58.3