## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Pansila Block: Nabadwip, Dist: Nadia. | SM/10527 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Pansila to accommodate FHTC within Nabadwip block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000101/2022-2023 | 3418/ND | 02/08/2022 | 31/10/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 452.17 | 390.57 | 86.38 | 95
2 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Pansila Block: Nabadwip, Dist: Nadia. | SM/10527 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000029/2022-2023 | 4088/ND | 21/09/2022 | 21/09/2022 | Resource Division | 84.05 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Pansila Block: Nabadwip, Dist: Nadia. | SM/10527 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000067/2022-2023 | 4321/ND | 29/09/2022 | 29/09/2022 | Resource Division | 17.77 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Pansila Block: Nabadwip, Dist: Nadia. | SM/10527 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for Pansila Block: Nabadwip, Dist: Nadia. |  |  | VCH/000198/2022-2023 | 22/PFMS | 20/05/2022 | 20/05/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.18 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Pansila Block: Nabadwip, Dist: Nadia. | SM/10527 | Augmentation | Renovation of AIRP (Gravity Type) of capacity 93 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Pansila PWSS under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000085/2023-2024 | 2998/ND | 13/07/2023 | 03/01/2025 | TARUN KUMAR BHATTACHARYA | 90.1 | 0 | 0 | 0
6 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Pansila Block: Nabadwip, Dist: Nadia. | SM/10527 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under PANSILA W/S Scheme, Block-Nabadwip , Dist. - Nadia. NIET No.- 28 of EE/EMD of 2022-23 (Sl. No.- 08) | Assistant Engineer | Junior Engineer | ORD/001013/2022-2023 | 501/EMDdt.24.01.2023 | 16/03/2023 | 15/04/2023 | ASHOKE ADHIKARY | 15.59 | 11.92 | 76.42 | 100
7 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Pansila Block: Nabadwip, Dist: Nadia. | SM/10527 | Augmentation | Repair and renovation works of R.C.C. Elevated Reservoir 450 cum, Repair & Renovation of Pump House, Boundary wall and allied works at 1st and 2nd Pump House at Pansila Water Supply Scheme within Nabadwip block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000393/2023-2024 | 5122/ND | 17/11/2023 | 15/02/2024 | INDUSTRIAL CONSTRUCTION | 29.08 | 21.22 | 72.98 | 70
8 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Pansila Block: Nabadwip, Dist: Nadia. | SM/10527 | Augmentation | Reimbursement of additional GST due to enhancement of rate from 12% to 18% vide notification no 03/2022-Central Tax Rate dt 13/7/2022 of Laying and Distribution system including specials,valves and pipe carrying structure all complete,proposed augmentation of rising main system and providing FHTC including supplying ,laying,fitting,fixing of 15mm NB PVC(Schedule 80)/20mm OD HDPE (PE 100,PN 16) pipe with all necessary specials,saddle piece etc all complete for augmentation of ground based water supply scheme at Pansila to accomodate FHTC within Nabadwip block under Krishnagar Sub-Division under Nadia Divn,PHE Dte |  |  | BILL/00247/2024-2025 | 151/PFMS | 31/07/2024 | 31/07/2024 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 18.57 | 0 | 0 | 0
9 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Pansila Block: Nabadwip, Dist: Nadia. | SM/10527 | Augmentation | Laying of UPVC Pipeline and providing FHTC including supplying, laying, fitting, fixing with all necessary specials, saddle piece etc. all complete for Ground Based piped water supply scheme in Bankar Dhopadi village to accommodate FHTC within Nabadwip block under Krishnanagar Sub-Division under Nadia Division,PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000139/2025-2026 | 2975/ND | 25/06/2025 | 20/02/2026 | SARKAR CONSTRUCTION | 91.91 | 0 | 0 | 0
10 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Pansila Block: Nabadwip, Dist: Nadia. | SM/10527 | Augmentation | Construction and installation of Manifold at OHR site and allied works in connection to the Augmentation of Pansila Water Supply Scheme under Nabadwip Block under Nadia Division, P.H.E Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000335/2025-2026 | 5355/6043/ND | 03/12/2025 | 02/04/2026 | KESHOB ENTERPRISE | 28.71 | 0 | 0 | 0
11 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Pansila Block: Nabadwip, Dist: Nadia. | SM/10527 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Pansila to accommodate FHTC within Nabadwip block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. |  |  | BILL/00415/2025-2026 |  | 09/07/2025 | 09/07/2025 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2.15 | 0 | 0 | 0
Total | [13 empty] | 834.29 | 423.71 | 50.79