## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR MONIPOTA PWSS BLOCK: KRISHNAGAR - I DISTRICT: NADIA | SM/10567 | Augmentation | PROVIDING FHTC BY AUGMENTATION FOR MONIPOTA PWSS BLOCK: KRISHNAGAR - I DISTRICT: NADIA |  |  | VCH/000350/2022-2023 | 50/PFMS | 22/06/2022 | 22/06/2022 | HORIZEN | 2.69 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR MONIPOTA PWSS BLOCK: KRISHNAGAR - I DISTRICT: NADIA | SM/10567 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000194/2022-2023 | 696/ND | 17/02/2023 | 17/02/2023 | Resource Division | 21.74 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR MONIPOTA PWSS BLOCK: KRISHNAGAR - I DISTRICT: NADIA | SM/10567 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000027/2023-2024 | 1874/ND | 26/04/2023 | 26/04/2023 | Resource Division | 12.46 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR MONIPOTA PWSS BLOCK: KRISHNAGAR - I DISTRICT: NADIA | SM/10567 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000096/2023-2024 | 2583/ND | 13/06/2023 | 13/06/2023 | Resource Division | 21.74 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR MONIPOTA PWSS BLOCK: KRISHNAGAR - I DISTRICT: NADIA | SM/10567 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000076/2023-2024 | 2297/ND | 29/05/2023 | 29/05/2023 | Resource Division | 10.28 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR MONIPOTA PWSS BLOCK: KRISHNAGAR - I DISTRICT: NADIA | SM/10567 | Augmentation | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for augmentation of Ground Water Based Water Supply Scheme for Monipota to accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000380/2022-2023 | 376/ND | 27/01/2023 | 01/04/2025 | SUMAN CHAKRABORTY | 196.42 | 120.17 | 61.18 | 100
7 | NADIA |  | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR MONIPOTA PWSS BLOCK: KRISHNAGAR - I DISTRICT: NADIA | SM/10567 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Replacement Tube Well in connection to Accommodate FHTC at Pump House No.-I under Monipota ground water based water supply scheme under Block_ Krishnanagar_I Dist. - Nadia under EMD, PHE Dte.(Phase-II) (SM/15135) | Assistant Engineer |  | ORD/001463/2024-2025 | 234/EMD | 06/02/2025 | 08/03/2025 | M/S.A.K. BANERJEE. | 11.76 | 0 | 0 | 0
8 | NADIA |  | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR MONIPOTA PWSS BLOCK: KRISHNAGAR - I DISTRICT: NADIA | SM/10567 | Augmentation | Supply, delivery, installation Commissioning of Electro Mechanical Equipments and allied works at MONIPOTA W/S Scheme Block- KRISHNAGAR - I under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia. [SM/10567 | Assistant Engineer | Junior Engineer | ORD/000143/2025-2026 | 1144/EMD | 04/06/2025 | 02/09/2025 | GOENKA ENTERPRISE | 37.8 | 0 | 0 | 0
9 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR MONIPOTA PWSS BLOCK: KRISHNAGAR - I DISTRICT: NADIA | SM/10567 | Augmentation | Construction of 51m Boundary Wall (2.5m panel) having 200X200mm R.C.C. Column footing (1.0X1.0m) with 125mm thick brick panel wall and 200x300 RCC beam at GL including M.S gate at Monipota PWSS at PH-2 site. | Assistant Engineer | Junior Engineer 1 | ORD/000795/2024-2025 | 85/RSD | 14/01/2025 | 30/03/2025 | BISHAL CONSTRUCTION | 4.6 | 0 | 0 | 0
10 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR MONIPOTA PWSS BLOCK: KRISHNAGAR - I DISTRICT: NADIA | SM/10567 | Augmentation | Construction and installation of MANIFOLD and allied works at Head Works site under Monipota Ground Based Water Supply Scheme under Krishnagar-I Block under Nadia Division, P.H.E Dte. in connection with uniform distribution of drinking water through FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) | Assistant Engineer |  | ORD/000069/2025-2026 | 2401/ND | 23/05/2025 | 21/08/2025 | R M TRADING | 11.91 | 0 | 0 | 0
11 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR MONIPOTA PWSS BLOCK: KRISHNAGAR - I DISTRICT: NADIA | SM/10567 | Augmentation | Special repair & renovation of head work site pump house & allied works of Monipota W/S scheme of Krishnanagar-I block under Ranaghat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000231/2022-2023 | 558/RSD | 30/08/2022 | 21/04/2024 | ROMI TRADERS | 2.22 | 1.5 | 67.41 | 80
12 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR MONIPOTA PWSS BLOCK: KRISHNAGAR - I DISTRICT: NADIA | SM/10567 | Augmentation | Special repair & renovation & repair of CWR pump house & allied works of Monipota W/S scheme of Krishnanagar block under Ranaghat Sub-Division, P.H.E. Dte | Assistant Engineer | Junior Engineer 1 | ORD/000232/2022-2023 | 558/A/RSD | 30/08/2022 | 22/01/2024 | M/S PHANINDRA NATH ROY | 2 | 0 | 0 | 85
13 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR MONIPOTA PWSS BLOCK: KRISHNAGAR - I DISTRICT: NADIA | SM/10567 | Augmentation | Restoration of Delivery pipe line and laying of distribution pipe line in Rowtara village under Monipota Ground water based water supply scheme under Ranaghat Sub-Division under Nadia Division PHED. | Assistant Engineer | Junior Engineer 1 | ORD/000020/2025-2026 | 1806/ND | 22/04/2025 | 22/07/2025 | PROGRESSIVE ENGINEERING & CONSTRUCTION | 28.82 | 0 | 0 | 70
14 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR MONIPOTA PWSS BLOCK: KRISHNAGAR - I DISTRICT: NADIA | SM/10567 | Augmentation | Repairing of PH-II and Construction of Sanitary arrangement under augmentation of Monipota under Ranaghat Sub-Division under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000890/2024-2025 | 202/RSD | 06/02/2025 | 23/03/2025 | SAYANTAN PANDEY | 2.15 | 0 | 0 | 70
15 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR MONIPOTA PWSS BLOCK: KRISHNAGAR - I DISTRICT: NADIA | SM/10567 | Augmentation | Construction of Backwash chamber of AIRP at Head Work Site & Renovation of Gravity Type AIRP in Monipota PWSS within Ranaghat Sub-Division under Nadia Division PHE Dte.Capacity 65.00 Cu.m/hr | Assistant Engineer | Junior Engineer 1 | ORD/000468/2023-2024 | 135/ND | 09/01/2024 | 03/01/2025 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 74.19 | 9.58 | 12.91 | 100
Total | [13 empty] | 440.77 | 131.24 | 29.78