## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BANPUR PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA | SM/10568 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000107/2022-2023 | 5172/ND | 13/12/2022 | 13/12/2022 | Resource Division | 6.18 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BANPUR PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA | SM/10568 | Augmentation | PROVIDING FHTC BY AUGMENTATION FOR MONIPOTA PWSS BLOCK: KRISHNAGAR - I DISTRICT: NADIA |  |  | VCH/000349/2022-2023 | 49/PFMS | 22/06/2022 | 22/06/2022 | HORIZEN | 2.69 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BANPUR PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA | SM/10568 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000076/2022-2023 | 4279/ND | 29/09/2022 | 29/09/2022 | Resource Division | 8.45 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BANPUR PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA | SM/10568 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000023/2023-2024 | 1867/ND | 26/04/2023 | 26/04/2023 | Resource Division | 23.96 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BANPUR PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA | SM/10568 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000092/2023-2024 | 2323/ND | 29/05/2023 | 29/05/2023 | Resource Division | 8.45 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BANPUR PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA | SM/10568 | Augmentation | Balance Laying distribution system for augmentation of Ground Water Based Water Supply Scheme for Banpur to accommodate FHTC in Krishnaganj block of Nadia District under Nadia Division P.H. Engineering Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000645/2023-2024 | 123/RSD | 29/01/2024 | 28/02/2024 | A.P. POWER & CONCRETE | 4.76 | 0 | 0 | 100
7 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BANPUR PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA | SM/10568 | Augmentation | Repairing of Pump house-I with sanitary arrangement under augmentation of Banpur piped water supply scheme under Ranaghat Sub-Division, under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000177/2024-2025 | 1143/RSD | 11/09/2024 | 26/10/2024 | ILA CONSTRUCTION | 1.89 | 0 | 0 | 85
8 | NADIA |  | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR BANPUR PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA | SM/10568 | Augmentation | Supply, delivery, installation Commissioning of Electro Mechanical Equipments and allied works at BANPUR W/S Scheme Block- KRISHNAGANJ under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia. [SM/10568] | Assistant Engineer |  | ORD/000142/2025-2026 | 1143/EMD | 04/06/2025 | 02/09/2025 | AHALYA ENGINEERING WORKS | 37.79 | 0 | 0 | 0
9 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BANPUR PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA | SM/10568 | Augmentation | Repairing of PH-II and Construction of Sanitary arrangement under Augmentation of Banpur PWSS. | Assistant Engineer | Junior Engineer 3 | ORD/000814/2024-2025 | 205/RSD | 06/02/2025 | 23/03/2025 | ABHAYANANDA ENTERPRISE | 2.52 | 0 | 0 | 100
10 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BANPUR PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA | SM/10568 | Augmentation | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 11/10/2025 | IMAGIN | 96.97 | 0 | 0 | 0
11 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BANPUR PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA | SM/10568 | Augmentation | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for augmentation of Ground Water Based Water Supply Scheme for Banpur to accommodate FHTC in Krishnaganj block of Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000145/2022-2023 | 4041/ND | 19/09/2022 | 01/05/2024 | A.P. POWER & CONCRETE | 146.68 | 0 | 0 | 96
12 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BANPUR PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA | SM/10568 | Augmentation | Laying distribution system for augmentation of Ground Water Based Water Supply Scheme for Banpur to accommodate FHTC in Krishnaganj block of Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000314/2023-2024 | 4321/ND | 26/09/2023 | 25/11/2023 | A.P. POWER & CONCRETE | 27.65 | 0 | 0 | 100
Total | [13 empty] | 368 | 0 | 0