## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-II) PWSS BLOCK: HANSKHALI DISTRICT: NADIA | SM/10571 | Augmentation | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-II) PWSS BLOCK: HANSKHALI DISTRICT: NADIA |  |  | VCH/000353/2022-2023 | 53/PFMS | 22/06/2022 | 22/06/2022 | HORIZEN | 2.53 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-II) PWSS BLOCK: HANSKHALI DISTRICT: NADIA | SM/10571 | Augmentation | Special repair & renovation of boundary wall & allied works in the premises at pump house no 2 of Dakshinpra-II W/S scheme of Hanskhali block under Ranaghat Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000243/2022-2023 | 468/A/RSD | 26/07/2022 | 25/08/2022 | MASUM CONSTRUCTION | 3.15 | 3.13 | 99.49 | 90
3 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-II) PWSS BLOCK: HANSKHALI DISTRICT: NADIA | SM/10571 | Augmentation | Special repair & renovation of head work site pump house & allied works of Dakshinpara-II W/S scheme of Hanskhali block under Ranaghat Sub-Division, P.H.E. Dte | Assistant Engineer | Junior Engineer 2 | ORD/000225/2022-2023 | 555/RSD | 30/08/2022 | 29/09/2022 | DURGADAS BASU | 2.15 | 1.78 | 82.97 | 85
4 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-II) PWSS BLOCK: HANSKHALI DISTRICT: NADIA | SM/10571 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000110/2022-2023 | 23/ND | 03/01/2023 | 03/01/2023 | Resource Division | 8.8 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-II) PWSS BLOCK: HANSKHALI DISTRICT: NADIA | SM/10571 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000022/2023-2024 | 1866/ND | 26/04/2023 | 26/04/2023 | Resource Division | 19.87 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-II) PWSS BLOCK: HANSKHALI DISTRICT: NADIA | SM/10571 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000065/2023-2024 | 2308/ND | 29/05/2023 | 29/05/2023 | Resource Division | 1.48 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-II) PWSS BLOCK: HANSKHALI DISTRICT: NADIA | SM/10571 | Augmentation | Special repair & renovation of pump house & allied works in the premises at pump house no-I of Dakshinpara-II W/S scheme of Hanskhali block under Ranaghat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000226/2022-2023 | 555/A/RSD | 30/08/2022 | 29/09/2022 | TINA CONSTRUCTION | 2.5 | 2.16 | 86.14 | 80
8 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-II) PWSS BLOCK: HANSKHALI DISTRICT: NADIA | SM/10571 | Augmentation | Special repair & renovation & repair of AIRP pump house & allied works of Dakshinpara-II W/S scheme of Hanskhali block under Ranaghat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000244/2022-2023 | 476/RSD | 27/07/2022 | 26/08/2022 | CONSTRUCTURE | 1.96 | 1.41 | 71.8 | 90
9 | NADIA |  | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-II) PWSS BLOCK: HANSKHALI DISTRICT: NADIA | SM/10571 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under DAKSHINPARA (Zone-I & II) W/S Scheme, Block- Hanskhali , AND GOPINATHPUR W/S Scheme, Block- Tehatta-II, Dist. - Nadia. NIET No.- 28 of EE/EMD of 2022-23 (Sl. No.- 01) | Assistant Engineer | Junior Engineer | ORD/001008/2022-2023 | 496/EMDdt.24.01.2023 | 17/03/2023 | 01/01/2025 | GLACIER ENGINEERING CO. | 66.71 | 8.5 | 12.74 | 100
10 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-II) PWSS BLOCK: HANSKHALI DISTRICT: NADIA | SM/10571 | Augmentation | Providing functional household tap connection including supplying,laying,fitting,fixing of 15mm NB PVC(schedule 80/20 mm) OD HDPE(PE 100 , PN16) pipe with all necessary specials, saddle piece etc. all complete for augmentation of Ground Water Based Water Supply scheme for dakshinpara Zone-II to accommodate FHTC in Hanskhali block of Nadia District under Nadia Division P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000292/2022-2023 | 5331/ND | 21/12/2022 | 04/02/2023 | NEERMAN | 96.27 | 60.98 | 63.35 | 91
11 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-II) PWSS BLOCK: HANSKHALI DISTRICT: NADIA | SM/10571 | Augmentation | Construction and installation of MANIFOLD and allied works at Head Works site under Dakshinpara Zone-II Ground Based Water Supply Scheme under Hanskhali Block under Nadia Division, P.H.E Dte. in connection with uniform distribution of drinking water through FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) | Assistant Engineer |  | ORD/000072/2025-2026 | 2433/ND | 26/05/2025 | 24/08/2025 | M/S S.K. ENTERPRISE | 12.34 | 0 | 0 | 0
12 | NADIA |  | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-II) PWSS BLOCK: HANSKHALI DISTRICT: NADIA | SM/10571 | Augmentation | Supply, delivery, installation Commissioning of Electro Mechanical Equipments and allied works at DAKSHINPARA (ZONE-II) W/S Scheme Block- HANSKHALI under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia. SM/10571 | Assistant Engineer |  | ORD/000140/2025-2026 | 1141/EMD | 04/06/2025 | 02/09/2025 | PADMA ENGINEERING CO. | 32.63 | 0 | 0 | 0
13 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-II) PWSS BLOCK: HANSKHALI DISTRICT: NADIA | SM/10571 | Augmentation | Land development of Dakshinpara Zone-II piped water supply scheme Head works site under Ranaghat Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000804/2024-2025 | 199/RSD | 06/02/2025 | 21/02/2025 | TARUN KUMAR BHATTACHARYA | 7.05 | 0 | 0 | 100
14 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-II) PWSS BLOCK: HANSKHALI DISTRICT: NADIA | SM/10571 | Augmentation | Construction of Backwash chamber of AIRP at Head Work Site & Renovation of Gravity Type AIRP in Dakshinpara-II PWSS within Ranaghat Sub-Division under Nadia Division PHE Dte.Capacity 35.00 Cu.m/hr | Assistant Engineer | Junior Engineer 2 | ORD/000467/2023-2024 | 134/ND | 09/01/2024 | 03/04/2025 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 60.46 | 0 | 0 | 100
Total | [13 empty] | 317.89 | 77.97 | 24.53