## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR MAIDANPUR PWSS BLOCK: CHAPRA DISTRICT: NADIA | SM/10572 | Augmentation | Survey , Design and preparation of Augmentation DPR in connection with " Providing functional household tap connection to every Household under Maidanpur W/S scheme in Nadia District under Nadia Division P.H.E. Dte. (Sl.No. 02) | Assistant Engineer |  | ORD/000341/2021-2022 | 905/KSD | 29/11/2021 | 14/12/2021 | HORIZEN | 3.2 | 0 | 0 | 93
2 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR MAIDANPUR PWSS BLOCK: CHAPRA DISTRICT: NADIA | SM/10572 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000155/2022-2023 | 127/ND | 05/01/2023 | 05/01/2023 | Resource Division | 11.98 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR MAIDANPUR PWSS BLOCK: CHAPRA DISTRICT: NADIA | SM/10572 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000080/2023-2024 | 2320/ND | 29/05/2023 | 29/05/2023 | Resource Division | 13.63 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR MAIDANPUR PWSS BLOCK: CHAPRA DISTRICT: NADIA | SM/10572 | Augmentation | Repair & Renovation of Pump House, Boundary wall and allied works at 1st and 2nd Pump House at Maidanpur Water Supply Scheme within Chapra block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000500/2023-2024 | 157/ND | 09/01/2024 | 09/03/2024 | M/S S.K. ENTERPRISE | 18.07 | 0 | 0 | 90
5 | NADIA |  | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR MAIDANPUR PWSS BLOCK: CHAPRA DISTRICT: NADIA | SM/10572 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accommodate FHTC under KARIMPUR JALANGI(Z-8) W/S Scheme, Block- Karimpur II, PALSONDHA W/S Scheme, Block- Tehatta II, & MAIDANPUR W/S Scheme, Block- Chapra, Dist. - Nadia. NIET No.- 33 of EE/EMD of 2022-23 (Sl. No.- 06) | Assistant Engineer | Junior Engineer | ORD/001923/2022-2023 | 1179/EMD | 21/03/2023 | 16/10/2025 | CREATIVE WATER & PROCESS TECHNOLOGIES PVT. LTD. | 77.9 | 0 | 0 | 85
6 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR MAIDANPUR PWSS BLOCK: CHAPRA DISTRICT: NADIA | SM/10572 | Augmentation | Laying of dedicated pipeline for Pipragachhi and part of Elangi Mouza for augmentation of Elangi Water Supply Scheme in Chapra Block, Nadia under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000010/2025-2026 | 1773/ND | 21/04/2025 | 18/10/2025 | TULIP ENGINEER'S CO-OP SOCIETY LTD | 86.27 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR MAIDANPUR PWSS BLOCK: CHAPRA DISTRICT: NADIA | SM/10572 | Augmentation | Laying distribution system [LDS] for providing Functional Household Tap Connection (FHTC), Rising main with Inter-Connection in between Tube wells including specials and valves, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule, saddle piece etc. all complete, Construction of 300 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (including pile foundation), pipe connection and cost of pipes, specials and Soil Investigation for Construction of One No. 300 Cum OHR of Staging Height 20 Mtr. by Augmentation for Maidanpur Piped Water Supply Scheme within Chapra Block under Krishnagar Sub Divn. under Nadia Divn. PHE Dte. in the District of Nadia. | Assistant Engineer | Junior Engineer 2 | ORD/000390/2022-2023 | 479/ND | 02/02/2023 | 01/06/2025 | JOY HIND TUBEWELL'S | 332.37 | 0 | 0 | 80
Total | [13 empty] | 543.42 | 0 | 0