## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR GEDE PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA | SM/10573 | Augmentation | Survey , Design and preparation of Augmentation DPR in connection with " Providing functional household tap connection to every Household under Gede W/S scheme in Nadia District under Nadia Division P.H.E. Dte. (Sl.No. 03) | Assistant Engineer |  | ORD/000342/2021-2022 | 906/KSD | 29/11/2021 | 14/12/2021 | HORIZEN | 2.48 | 2.39 | 96.33 | 100
2 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR GEDE PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA | SM/10573 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000151/2022-2023 | 120/ND | 05/01/2023 | 05/01/2023 | Resource Division | 10.97 | 0 | 0 | 0
3 | NADIA |  | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR GEDE PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA | SM/10573 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accommodate FHTC under GEDE W/S Scheme, Block- Krishnaganj , Dist. - Nadia. NIET No. 33 of EE/EMD of 2022-23 (Sl. No. -08) |  |  | ORD/001921/2022-2023 | 1177/EMD | 21/03/2023 | 20/04/2023 | PS AND ASSOCIATES | 13.6 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR GEDE PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA | SM/10573 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 30/01/2024 | IMAGIN | 96.97 | 2.8 | 2.89 | 40
5 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR GEDE PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA | SM/10573 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 15 m3/hr at Gede Water Supply Scheme within Krishnaganj Block under Krishnagar Sub-Divn. under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000195/2024-2025 | 6222/ND | 23/09/2024 | 22/03/2025 | GHOSH ENTERPRISE | 137.17 | 0 | 0 | 0
6 | NADIA |  | Central Drilling | PROVIDING FHTC BY AUGMENTATION FOR GEDE PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA | SM/10573 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Gede W/S Scheme (TW-I) , Krishanjganj Block under Nadia District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000132/2023-2024 | 1233/CDD | 04/09/2023 | 08/09/2024 | DEV AND COMPANY | 18.88 | 15.08 | 79.86 | 100
7 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR GEDE PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA | SM/10573 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000150/2023-2024 | 261/ND | 11/01/2024 | 11/01/2024 | Resource Division | 3.31 | 0 | 0 | 0
8 | NADIA |  | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR GEDE PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA | SM/10573 | Augmentation | WBSEDCL Quotation for New Service Connection to the newly constructed Head Work Site under GEDE W/S Scheme in Krishnaganj Block, P.H.E. Dte., Dist.- Nadia. (Application No. 3004956395) |  |  | BILL/01889/2024-2025 | BP-165-24-25 | 25/11/2024 | 25/11/2024 | W.B.S.E.D.C.LTD (KRISHNAGANJ C.C.C) | 6.04 | 0 | 0 | 0
9 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR GEDE PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA | SM/10573 | Augmentation | Augmentation of Ground Based Water Supply Scheme at GEDE to accommodate FHTC within Krishnaganj Block under Krishnagar Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 4 | ORD/000157/2023-2024 | 3221/ND | 26/07/2023 | 02/11/2025 | A.P. POWER & CONCRETE | 70.25 | 0 | 0 | 40
10 | NADIA |  | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR GEDE PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA | SM/10573 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Gede ground water based water supply scheme under Block_ Krishnaganj Dist. - Nadia under EMD, PHE Dte. SM/10573 | Assistant Engineer |  | ORD/000180/2025-2026 | 1117/EMD | 04/06/2025 | 02/09/2025 | KUNDU ELECTRICAL ENTERPRISE | 17.48 | 0 | 0 | 0
Total | [13 empty] | 377.14 | 20.27 | 5.37