## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA KULTA to Accommodate FHTC in Ranaghat-I Block of Nadia District under Nadia Division, P.H.E. Dte | SM/10595 | Augmentation | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Barakulta W/S Scheme in Ranaghat-I Block of Nadia District under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000442/2021-2022 | 1062/RSD | 02/12/2021 | 01/01/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.76 | 0 | 0 | 100
2 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA KULTA to Accommodate FHTC in Ranaghat-I Block of Nadia District under Nadia Division, P.H.E. Dte | SM/10595 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000104/2022-2023 | 5103/ND | 08/12/2022 | 08/12/2022 | Resource Division | 154.18 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA KULTA to Accommodate FHTC in Ranaghat-I Block of Nadia District under Nadia Division, P.H.E. Dte | SM/10595 | Augmentation | Special repair & renovation of head work site pump house & allied works of Barakulta W/S scheme of Ranaghat-I block under Ranaghat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000236/2022-2023 | 461/A/RSD | 22/07/2022 | 21/08/2022 | PALLAB KARMAKAR | 2.25 | 0 | 0 | 90
4 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA KULTA to Accommodate FHTC in Ranaghat-I Block of Nadia District under Nadia Division, P.H.E. Dte | SM/10595 | Augmentation | Special repair & renovation & repair of IEP pump house & allide works of Barakulta W/S scheme of Ranaghat-I block under Ranaghat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000235/2022-2023 | 461/RSD | 22/07/2022 | 21/08/2022 | RENUKA ENTERPRISE | 1.49 | 0 | 0 | 90
5 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA KULTA to Accommodate FHTC in Ranaghat-I Block of Nadia District under Nadia Division, P.H.E. Dte | SM/10595 | Augmentation | River crossing at Anjana River Barakulta including construction of anchor block Barakulta W/S Scheme of Ranaghat -I block under Ranaghat Sub-Division,P.H.E.Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000291/2022-2023 | 5330/ND | 21/12/2022 | 04/02/2023 | CHOWDHURY & CO. | 15.3 | 0 | 0 | 100
6 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA KULTA to Accommodate FHTC in Ranaghat-I Block of Nadia District under Nadia Division, P.H.E. Dte | SM/10595 | Augmentation | Special repair & renovation of pump house & allied works in the premises at pump house no-I of Barakulta W/S scheme of Ranaghat-I block under Ranaghat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000237/2022-2023 | 462/RSD | 22/07/2022 | 21/08/2022 | JYOTIRMOY ENTERPRISE | 2.54 | 0 | 0 | 85
7 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA KULTA to Accommodate FHTC in Ranaghat-I Block of Nadia District under Nadia Division, P.H.E. Dte | SM/10595 | Augmentation | Special repair & renovation of boundary wall & allied works in the premises at pump house no 2 of Barakulta W/S scheme of Ranaghat-I block under Ranaghat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000238/2022-2023 | 462/A/RSD | 22/07/2022 | 21/08/2022 | M/S LOKENATH ENTERPRISE | 2.84 | 0 | 0 | 95
8 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA KULTA to Accommodate FHTC in Ranaghat-I Block of Nadia District under Nadia Division, P.H.E. Dte | SM/10595 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000071/2022-2023 | 4322/ND | 29/09/2022 | 29/09/2022 | Resource Division | 19.74 | 0 | 0 | 0
9 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA KULTA to Accommodate FHTC in Ranaghat-I Block of Nadia District under Nadia Division, P.H.E. Dte | SM/10595 | Augmentation | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule, saddle piece etc. all complete for augmentation of Ground Water Based Water Supply Scheme for Barakulta to accommodate FHTC in Ranaghat-I block of Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000107/2022-2023 | 3529/ND | 05/08/2022 | 03/11/2022 | TAPU SAHA | 354 | 0 | 0 | 94
10 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA KULTA to Accommodate FHTC in Ranaghat-I Block of Nadia District under Nadia Division, P.H.E. Dte | SM/10595 | Augmentation | Construction and installation of MANIFOLD and allied works at Head Works site under Barakulta Ground Based Water Supply Scheme under Ranaghat-I Block under Nadia Division, P.H.E Dte. in connection with uniform distribution of drinking water through FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) | Assistant Engineer | Junior Engineer 2 | ORD/000074/2025-2026 | 2435/ND | 26/05/2025 | 22/11/2025 | M/S G.M ASSOCIATES | 12.36 | 0 | 0 | 0
11 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA KULTA to Accommodate FHTC in Ranaghat-I Block of Nadia District under Nadia Division, P.H.E. Dte | SM/10595 | Augmentation | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 11/10/2025 | IMAGIN | 96.97 | 0 | 0 | 0
Total | [13 empty] | 666.43 | 0 | 0