## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA KULTA to Accommodate FHTC in Ranaghat-I Block of Nadia District under Nadia Division, P.H.E. Dte | SM/10595 | Augmentation | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Barakulta W/S Scheme in Ranaghat-I Block of Nadia District under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000442/2021-2022 | 1062/RSD | 02/12/2021 | 01/01/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.76 | 0 | 0 | 100
2 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA KULTA to Accommodate FHTC in Ranaghat-I Block of Nadia District under Nadia Division, P.H.E. Dte | SM/10595 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000104/2022-2023 | 5103/ND | 08/12/2022 | 08/12/2022 | Resource Division | 154.18 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA KULTA to Accommodate FHTC in Ranaghat-I Block of Nadia District under Nadia Division, P.H.E. Dte | SM/10595 | Augmentation | Special repair & renovation of head work site pump house & allied works of Barakulta W/S scheme of Ranaghat-I block under Ranaghat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000236/2022-2023 | 461/A/RSD | 22/07/2022 | 21/08/2022 | PALLAB KARMAKAR | 2.25 | 0 | 0 | 90
4 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA KULTA to Accommodate FHTC in Ranaghat-I Block of Nadia District under Nadia Division, P.H.E. Dte | SM/10595 | Augmentation | Special repair & renovation & repair of IEP pump house & allide works of Barakulta W/S scheme of Ranaghat-I block under Ranaghat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000235/2022-2023 | 461/RSD | 22/07/2022 | 21/08/2022 | RENUKA ENTERPRISE | 1.49 | 0 | 0 | 90
5 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA KULTA to Accommodate FHTC in Ranaghat-I Block of Nadia District under Nadia Division, P.H.E. Dte | SM/10595 | Augmentation | River crossing at Anjana River Barakulta including construction of anchor block Barakulta W/S Scheme of Ranaghat -I block under Ranaghat Sub-Division,P.H.E.Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000291/2022-2023 | 5330/ND | 21/12/2022 | 04/02/2023 | CHOWDHURY & CO. | 15.3 | 0 | 0 | 100
6 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA KULTA to Accommodate FHTC in Ranaghat-I Block of Nadia District under Nadia Division, P.H.E. Dte | SM/10595 | Augmentation | Special repair & renovation of pump house & allied works in the premises at pump house no-I of Barakulta W/S scheme of Ranaghat-I block under Ranaghat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000237/2022-2023 | 462/RSD | 22/07/2022 | 21/08/2022 | JYOTIRMOY ENTERPRISE | 2.54 | 0 | 0 | 85
7 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA KULTA to Accommodate FHTC in Ranaghat-I Block of Nadia District under Nadia Division, P.H.E. Dte | SM/10595 | Augmentation | Special repair & renovation of boundary wall & allied works in the premises at pump house no 2 of Barakulta W/S scheme of Ranaghat-I block under Ranaghat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000238/2022-2023 | 462/A/RSD | 22/07/2022 | 21/08/2022 | M/S LOKENATH ENTERPRISE | 2.84 | 0 | 0 | 95
8 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA KULTA to Accommodate FHTC in Ranaghat-I Block of Nadia District under Nadia Division, P.H.E. Dte | SM/10595 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000071/2022-2023 | 4322/ND | 29/09/2022 | 29/09/2022 | Resource Division | 19.74 | 0 | 0 | 0
9 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA KULTA to Accommodate FHTC in Ranaghat-I Block of Nadia District under Nadia Division, P.H.E. Dte | SM/10595 | Augmentation | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 11/10/2025 | IMAGIN | 96.97 | 0 | 0 | 0
Total | [13 empty] | 300.06 | 0 | 0