## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KAMALPUR ZONE-II to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. | SM/10596 | Augmentation | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, , Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Kamalpur Z-II Water Supply scheme Ranaghat-II block in Nadia District under Nadia Division P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000246/2021-2022 | 5701/ND | 03/11/2021 | 30/11/2024 | PRIYA CONSTRUCTION | 63.6 | 0 | 0 | 100
2 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KAMALPUR ZONE-II to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. | SM/10596 | Augmentation | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Kamalpur Zone-II W/S Scheme in Ranaghat-II Block of Nadia District under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000441/2021-2022 | 1061/RSD | 02/12/2021 | 01/01/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.64 | 2.95 | 63.52 | 100
3 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KAMALPUR ZONE-II to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. | SM/10596 | Augmentation | Augmentation of Ground Water Based piped Water Supply scheme for Kamalpur Zone-II to accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000431/2022-2023 | 893/ND | 02/03/2023 | 20/05/2025 | CHOWDHURY & CO. | 94.41 | 19.07 | 20.2 | 85
4 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KAMALPUR ZONE-II to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. | SM/10596 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000001/2023-2024 | 1516/ND | 04/04/2023 | 04/04/2023 | Resource Division | 0.96 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KAMALPUR ZONE-II to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. | SM/10596 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000014/2023-2024 | 1860/ND | 26/04/2023 | 26/04/2023 | Resource Division | 12.64 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KAMALPUR ZONE-II to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. | SM/10596 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000084/2023-2024 | 2286/ND | 29/05/2023 | 29/05/2023 | Resource Division | 1.29 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KAMALPUR ZONE-II to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. | SM/10596 | Augmentation | Repairing of PH-II and Construction of Sanitary arrangement under augmentation of Kamalpur Zone-II under Ranaghat Sub-Division under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000383/2024-2025 | 1420/RSD | 19/11/2024 | 03/01/2025 | M/S DAYANIDHI CONSTRUCTIONS | 2.15 | 0 | 0 | 100
8 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KAMALPUR ZONE-II to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. | SM/10596 | Augmentation | Urgent basis carriage of different dia DI Pipe which is supply by Resource Division at different water supply scheme under Ranaghat Sub-Division, Nadia Division P.H. Engineering Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000153/2024-2025 | 796/RSD | 02/08/2024 | 17/08/2024 | PROGRESSIVE ENGINEERING & CONSTRUCTION | 0.98 | 0 | 0 | 100
9 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KAMALPUR ZONE-II to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. | SM/10596 | Augmentation | Repairing of Pump house-I with sanitary arrangement under augmentation of Kamalpur Zone-II piped water supply scheme under Ranaghat Sub-Division, under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000178/2024-2025 | 1146/RSD | 11/09/2024 | 26/10/2024 | AMIT KUMAR GHOSH | 1.87 | 1.7 | 91.12 | 100
10 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for KAMALPUR ZONE-II to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. | SM/10596 | Augmentation | Supply, delivery, installation Commissioning of Electro Mechanical Equipments and allied works at KAMALPUR ZONE-II W/S Scheme Block- Ranaghat-II under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia. [SM/10596] | Assistant Engineer |  | ORD/000147/2025-2026 | 1148/EMD | 04/06/2025 | 02/09/2025 | M/S. G.P. ENTERPRISE | 29.62 | 0 | 0 | 0
Total | [13 empty] | 212.17 | 23.72 | 11.18