## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Tehatatta(Phase-II) to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | SM/10597 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000180/2022-2023 | 143/ND | 06/01/2023 | 06/01/2023 | Resource Division | 107.61 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Tehatatta(Phase-II) to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | SM/10597 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000079/2023-2024 | 2322/ND | 29/05/2023 | 29/05/2023 | Resource Division | 16.74 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Tehatatta(Phase-II) to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | SM/10597 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Tehatta (Phase-2) Ground Based Water Supply Scheme under Tehatta-I Block under Nadia Division,P.H.E Dte. in connection with Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Tehatta (Phase-2) at Tehatta- I Block by Augmentation of Ground Water based PWSS for Tehatta (Phase-2) Water Supply Schemes under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000634/2024-2025 | 7362/ND | 18/12/2024 | 16/02/2025 | MANISHIKA CONSTRUCTION | 20.92 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Tehatatta(Phase-II) to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | SM/10597 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 135 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Tehatta to accommodate FHTC within Tehatta-I block under Tehatta Sub-division under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000094/2024-2025 | 4230/ND | 02/08/2024 | 29/01/2025 | TARUN KUMAR BHATTACHARYA | 315.65 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Tehatatta(Phase-II) to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | SM/10597 | Augmentation | Collection of Household data through mobile app for FHTC Connection at followingschemes under Nadia Division PHE Dte.Schemes: i) Hanspukuria (Zone-II) ii) Tehatta (Phase-II) iii) Dhoradaha iv)Karimpur Jalangi(Zone-XA) v)Karimpur Jalangi(Zone-XB) vi) Hanspukuria (Zone-I) | Assistant Engineer | Junior Engineer 2 | ORD/000479/2022-2023 | 371/ Kly SD-I | 17/03/2023 | 17/09/2023 | HORIZEN | 4.96 | 4.96 | 100 | 100
6 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Tehatatta(Phase-II) to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | SM/10597 | Augmentation | Sinking of Tube Well at Tehatta PH-2 including dismantling of old pump house for entry of tube well rig, construction of pump house and boundary wall under Augmentation of Ground Water Based Piped Water Supply Scheme for Tehatta (Phase-II) at Tehatta-I block under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000001/2023-2024 | 1545/ND | 05/04/2023 | 26/09/2024 | JOY HIND TUBEWELL'S | 36.83 | 11.46 | 31.12 | 100
7 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Tehatatta(Phase-II) to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | SM/10597 | Augmentation | Reimbursement of additional GST due to enhancement of rate from 12% to 18% vide notification no 03/2022 central tax rate dt-13.07.2022 |  |  | BILL/00214/2024-2025 | 126/PFMS | 23/07/2024 | 23/07/2024 | H I ENTERPRISE | 24.42 | 0 | 0 | 0
8 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Tehatatta(Phase-II) to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | SM/10597 | Augmentation | Laying of additional pipeline for Tehatta PWSS".under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000123/2024-2025 | 4576/ND | 21/08/2024 | 18/04/2025 | SHYAMAL SHIL | 21.44 | 0 | 0 | 0
9 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Tehatatta(Phase-II) to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | SM/10597 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Replacement Tube well and Newly Sinkinng Tube Well in connection to Accommodate FHTC at Pump House No.-I,II,III,IV under Tehatta ground water based water supply scheme under Block_ Tehatta-I Dist. - Nadia under EMD, PHE Dte. [SM/10597] | Assistant Engineer | Junior Engineer | ORD/000024/2025-2026 | 694/EMD | 04/04/2025 | 04/05/2025 | C.M.S. ENGINEERING CONCERN. | 51.99 | 0 | 0 | 0
10 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Tehatatta(Phase-II) to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | SM/10597 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme (Phase- III) at village Nazirpur, Bagadoba, Chhitka, Aztullanagar under Tehatta-I Block to accommodate FHTC under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000019/2025-2026 | 1805/ND | 22/04/2025 | 19/10/2025 | M/S DIPAK ENTERPRISE | 71.65 | 0 | 0 | 30
11 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Tehatatta(Phase-II) to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | SM/10597 | Augmentation | Augmentation of rising main system, providing FHTC, construction of 700 cum capacity 20 mtr. staging height RCC over head reservoir (including pile foundation), pipe connection and cost of pipes, specials and soil investigation for augmentation of ground water based piped water supply scheme for Tehatta Phase-II to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000388/2022-2023 | 478/ND | 02/02/2023 | 01/04/2025 | H I ENTERPRISE, VILL&P.O- DHALTITHA, P.S. BASIRHAT, NORTH 24 PARGANAS, PIN-743412(WB) | 354.33 | 227.46 | 64.19 | 90
Total | [13 empty] | 1026.54 | 243.88 | 23.76