## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Mahisunra(Phase-II) to accommodate FHTC in Nabadwip block of Nadia District under Nadia Division, PHE Dte. | SM/10598 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000154/2022-2023 | 126/ND | 05/01/2023 | 05/01/2023 | Resource Division | 30.06 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Mahisunra(Phase-II) to accommodate FHTC in Nabadwip block of Nadia District under Nadia Division, PHE Dte. | SM/10598 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000049/2023-2024 | 1997/ND | 08/05/2023 | 08/05/2023 | Resource Division | 30.69 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Mahisunra(Phase-II) to accommodate FHTC in Nabadwip block of Nadia District under Nadia Division, PHE Dte. | SM/10598 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000051/2023-2024 | 1997/ND | 08/05/2023 | 08/05/2023 | Resource Division | 31.11 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Mahisunra(Phase-II) to accommodate FHTC in Nabadwip block of Nadia District under Nadia Division, PHE Dte. | SM/10598 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000089/2023-2024 | 2319/ND | 29/05/2023 | 29/05/2023 | Resource Division | 24.61 | 0 | 0 | 0
5 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Mahisunra(Phase-II) to accommodate FHTC in Nabadwip block of Nadia District under Nadia Division, PHE Dte. | SM/10598 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under MAHISUNRA W/S Scheme, Block-NABADWIP, PALASIPARA W/S Scheme, Block-Tehatta-II AND TOPLA W/S Scheme, Block-Karimpur-II Dist. - Nadia. NIET No.- 28 of EE/EMD of 2022-23 (Sl. No. - 05) | Assistant Engineer | Junior Engineer | ORD/001011/2022-2023 | 499/EMD | 24/01/2023 | 23/02/2023 | WEST BENGAL ENGINEERING CO. | 90.14 | 6.39 | 7.09 | 15
6 | NADIA |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Mahisunra(Phase-II) to accommodate FHTC in Nabadwip block of Nadia District under Nadia Division, PHE Dte. | SM/10598 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Mahisunra W/S Scheme (Phase-II,T/W-I& II) , Nabadwip Block under Nadia District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000072/2023-2024 | 510/CDD | 01/06/2023 | 01/07/2023 | UNIVERSAL ENTERPRISES | 37.73 | 0 | 0 | 10
7 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Mahisunra(Phase-II) to accommodate FHTC in Nabadwip block of Nadia District under Nadia Division, PHE Dte. | SM/10598 | Augmentation | Construction of Arsenic-Cum- Iron Removal Plant (AIRP) of capacity 156 m3/hr at Mahisura Water Supply Scheme within Nabadwip Block under Krishnagar Sub-Divn. under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000255/2024-2025 | 6571/ND | 21/10/2024 | 19/04/2025 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 348.3 | 0 | 0 | 0
8 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Mahisunra(Phase-II) to accommodate FHTC in Nabadwip block of Nadia District under Nadia Division, PHE Dte. | SM/10598 | Augmentation | Laying of Distribution System including Specials, Valves and Pipe Supporting Structure for providing FHTC in connection to Augmentation of Ground Water Based Piped Water Supply Scheme of Mahisura (Phase-II) in Nabadwip Block under Krishnagar Sub-Divn. under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000708/2023-2024 | 1298/ND | 23/02/2024 | 23/05/2024 | PATHIK PABAN NANDI | 63.92 | 56.11 | 87.78 | 80
9 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Mahisunra(Phase-II) to accommodate FHTC in Nabadwip block of Nadia District under Nadia Division, PHE Dte. | SM/10598 | Augmentation | Proposed Augmentation of Rising Main System, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc., Construction of 1 No. Pump House at proposed Head Work site & Tube Well site, Construction of R.C.C. Elevated Reservoir of 900 Cum capacity (including pile foundation), and Soil Investigation for construction of OHR all complete for Augmentation of Ground Based Water Supply Scheme at Mahisura (Phase-II) to accommodate FHTC within Nabadwip Block under Krishnanagar Sub-division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000536/2022-2023 | 1385/ND | 29/03/2023 | 01/01/2027 | M/S GHOSH CONSTRUCTION, SUKUL ROAD,P.O.-KRISHNAGAR, DIST. NADIA, PIN-741101, WB | 401.97 | 143.35 | 35.66 | 40
10 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Mahisunra(Phase-II) to accommodate FHTC in Nabadwip block of Nadia District under Nadia Division, PHE Dte. | SM/10598 | Augmentation | Quotation for new service connection at Mahisura Ph-4, at Nabadwip block, district-Nadia |  |  | BILL/02507/2024-2025 | BP-234 | 04/02/2025 | 04/02/2025 | WBSEDCL SAMUDRAGARH CCC | 4.63 | 0 | 0 | 0
11 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Mahisunra(Phase-II) to accommodate FHTC in Nabadwip block of Nadia District under Nadia Division, PHE Dte. | SM/10598 | Augmentation | Quotation for new service connection at Mahisura Ph-1, at Nabadwip block, district-Nadia, |  |  | BILL/02508/2024-2025 | BP-235 | 04/02/2025 | 04/02/2025 | WBSEDCL SAMUDRAGARH CCC | 5.27 | 0 | 0 | 0
12 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Mahisunra(Phase-II) to accommodate FHTC in Nabadwip block of Nadia District under Nadia Division, PHE Dte. | SM/10598 | Augmentation | Quotation for height extension of existing 11KV HT OH line at the premises of Mahisura Headwork site water supply scheme, at Nabadwip block, district-Nadia |  |  | BILL/02562/2024-2025 | BP-236 | 04/02/2025 | 04/02/2025 | WBSEDCL SAMUDRAGARH CCC | 1.37 | 0 | 0 | 0
13 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Mahisunra(Phase-II) to accommodate FHTC in Nabadwip block of Nadia District under Nadia Division, PHE Dte. | SM/10598 | Augmentation | Payment of Supplementary Quotation of WBSEDCL Authority against our Application for line diversion due to rising ROW Issue. |  |  | BILL/04584/2025-2026 |  | 19/03/2026 | 19/03/2026 | WBSEDCL SAMUDRAGARH CCC | 0.37 | 0 | 0 | 0
Total | [13 empty] | 1070.16 | 205.85 | 19.24