## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR GOPINATHPUR PWSS BLOCK: TEHATTA - II DISTRICT: NADIA | SM/10688 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000102/2022-2023 | 5101/ND | 08/12/2022 | 08/12/2022 | Resource Division | 3.64 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR GOPINATHPUR PWSS BLOCK: TEHATTA - II DISTRICT: NADIA | SM/10688 | Augmentation | PROVIDING FHTC BY AUGMENTATION FOR GOPINATHPUR PWSS BLOCK: TEHATTA - II DISTRICT: NADIA |  |  | VCH/000348/2022-2023 | 48/PFMS | 22/06/2022 | 22/06/2022 | HORIZEN | 2.8 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR GOPINATHPUR PWSS BLOCK: TEHATTA - II DISTRICT: NADIA | SM/10688 | Augmentation | Conversion of IEP to AIRP of capacity 120 Cu.m/hr at Gopinathpur Water Supply Scheme within Tehatta-II Block block under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer |  | ORD/000316/2024-2025 | 6841/ND | 12/11/2024 | 11/05/2025 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 172.22 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR GOPINATHPUR PWSS BLOCK: TEHATTA - II DISTRICT: NADIA | SM/10688 | Augmentation | Repairing and renovation of Elevated Reservoir , Pump House ,boundary wall of ground basaed piped water supply scheme for Gopinathpur water supply scheme under Tehatta Sub Division in Nadia District under Nadia Division P.H.Engineering Dte. |  |  | ORD/000401/2024-2025 | 7125/ND | 09/12/2024 | 09/03/2025 | REAL TIME | 37.78 | 0 | 0 | 0
5 | NADIA |  | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR GOPINATHPUR PWSS BLOCK: TEHATTA - II DISTRICT: NADIA | SM/10688 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under DAKSHINPARA (Zone-I & II) W/S Scheme, Block- Hanskhali , AND GOPINATHPUR W/S Scheme, Block- Tehatta-II, Dist. - Nadia. NIET No.- 28 of EE/EMD of 2022-23 (Sl. No.- 01) | Assistant Engineer | Junior Engineer | ORD/001008/2022-2023 | 496/EMDdt.24.01.2023 | 17/03/2023 | 01/01/2025 | GLACIER ENGINEERING CO. | 66.71 | 37.35 | 55.99 | 100
6 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR GOPINATHPUR PWSS BLOCK: TEHATTA - II DISTRICT: NADIA | SM/10688 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc., construction of 400 cum capacity 20 mtr. staging height rcc over head reservoir (including pile foundation), pipe connection and cost of pipes, specials. and soil investigation all complete for Augmentation of Ground Based Water Supply Scheme at Gopinathpur to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000149/2022-2023 | 4226/ND | 27/09/2022 | 27/10/2026 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 766.15 | 346.25 | 45.19 | 65
7 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR GOPINATHPUR PWSS BLOCK: TEHATTA - II DISTRICT: NADIA | SM/10688 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Gopinathpur Ground Based Water Supply Scheme under Tehatta-II Block under Nadia Division,P.H.E Dte. in connection with Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Gopinathpur at Tehatta-II Block by Augmentation of Ground Water based PWSS for Tehatta-II Water Supply Schemes under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000741/2024-2025 | 419/ND | 27/01/2025 | 28/03/2025 | DAS CONSTRUCTION | 26.96 | 0 | 0 | 0
8 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR GOPINATHPUR PWSS BLOCK: TEHATTA - II DISTRICT: NADIA | SM/10688 | Augmentation | Laying pipe line of rising main at Gopinathpur Under Augmentation of Gopinathpur PWSS under Tehatta Sub-Division Under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000679/2024-2025 | 7452/ND | 20/12/2024 | 13/06/2026 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 54.97 | 0 | 0 | 0
9 | NADIA |  | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR GOPINATHPUR PWSS BLOCK: TEHATTA - II DISTRICT: NADIA | SM/10688 | Augmentation | Supply, delivery, installation Commissioning of Electro Mechanical Equipments and allied works at GOPINATHPUR W/S Scheme Block- Tehatta-II under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia. [SM/10688] | Assistant Engineer |  | ORD/000137/2025-2026 | 1138/EMD | 04/06/2025 | 02/09/2025 | ABHISEK ENGINEERING CONCERN | 52.38 | 0 | 0 | 0
10 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR GOPINATHPUR PWSS BLOCK: TEHATTA - II DISTRICT: NADIA | SM/10688 | Augmentation | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 11/10/2025 | IMAGIN | 96.97 | 0 | 0 | 0
Total | [13 empty] | 1280.57 | 383.6 | 29.96