## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION OF PALASHIPARA PWSS BLOCK: TEHATTA-II DISTRICT: NADIA | SM/10691 | Augmentation | PROVIDING FHTC BY AUGMENTATION OF PALASHIPARA PWSS BLOCK: TEHATTA-II DISTRICT: NADIA |  |  | VCH/000347/2022-2023 | 47/PFMS | 22/06/2022 | 22/06/2022 | HORIZEN | 2.7 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION OF PALASHIPARA PWSS BLOCK: TEHATTA-II DISTRICT: NADIA | SM/10691 | Augmentation | Construction of barbed wire fencing with concrete pillars at Palashipara (3rd T.W). water supply scheme( New Land) under Tehatta Sub-Division under Nadia Division PHE Dte. in JJM project . | Assistant Engineer |  | ORD/000583/2022-2023 | 932/TSD | 14/03/2023 | 21/03/2023 | PRABIR KUMAR ROY | 0.65 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION OF PALASHIPARA PWSS BLOCK: TEHATTA-II DISTRICT: NADIA | SM/10691 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000174/2022-2023 | 140/ND | 06/01/2023 | 06/01/2023 | Resource Division | 7.35 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION OF PALASHIPARA PWSS BLOCK: TEHATTA-II DISTRICT: NADIA | SM/10691 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000196/2022-2023 | 1025/ND | 13/03/2023 | 13/03/2023 | Resource Division | 30.79 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION OF PALASHIPARA PWSS BLOCK: TEHATTA-II DISTRICT: NADIA | SM/10691 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000058/2023-2024 | 2290/ND | 29/05/2023 | 29/05/2023 | Resource Division | 34.16 | 0 | 0 | 0
6 | NADIA |  | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION OF PALASHIPARA PWSS BLOCK: TEHATTA-II DISTRICT: NADIA | SM/10691 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under MAHISUNRA W/S Scheme, Block-NABADWIP, PALASIPARA W/S Scheme, Block-Tehatta-II AND TOPLA W/S Scheme, Block-Karimpur-II Dist. - Nadia. NIET No.- 28 of EE/EMD of 2022-23 (Sl. No. - 05) | Assistant Engineer | Junior Engineer | ORD/001011/2022-2023 | 499/EMD | 24/01/2023 | 23/02/2023 | WEST BENGAL ENGINEERING CO. | 90.14 | 0 | 0 | 15
7 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION OF PALASHIPARA PWSS BLOCK: TEHATTA-II DISTRICT: NADIA | SM/10691 | Augmentation | Sinking of 01 no Tubewell 300 x 200 mm dia and 200 mtr. Deep Tubewell by Direct Rotary Rig Method, having 300 mm dia 48 mtr. long PVC Housing Pipe & 200 mm.dia Well Pipe & Deep well Screen (RDS strainer) at Palashipara Water Supply Scheme under Tehatta Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000689/2023-2024 | 1225/ND | 22/02/2024 | 23/10/2024 | M/S DIPAK ENTERPRISE | 17.38 | 0 | 0 | 100
8 | NADIA |  | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION OF PALASHIPARA PWSS BLOCK: TEHATTA-II DISTRICT: NADIA | SM/10691 | Augmentation | Quotation charges and security deposit for new power connection at Palashipara PH-III head worksite under Eastern Mechanical Subdivision-III, Nadia |  |  | BILL/02257/2024-2025 | BP-178 | 13/12/2024 | 13/12/2024 | W.B.S.E.D.C.L (PANCHDHARA ABHAYNAGAR C.C.C) | 3.49 | 0 | 0 | 0
9 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION OF PALASHIPARA PWSS BLOCK: TEHATTA-II DISTRICT: NADIA | SM/10691 | Augmentation | Reimbursement of additional GST due to enhancement of rate from 12% to 18% vide notification no 03/2022-central tax rate dt 13.07.2022 for the work of Laying Of Distribution System Including Specials, Valves & Pipe Carrying Structure All Complete ,rising main with interconnction in between tubewell including specials and valves, Providing FHTC Including Supplying, Laying, Fitting, Fixing Of 15mm NB PVC (Schedule 80)/20mm OD HDPE (PE 100, PN16) Pipe With All Necessary Specials, Saddle Piece Etc., Construction Of 400 Cum Capacity 20 Mtr. Staging Height Rcc Over Head Reservoir (including Pile Foundation), Pipe Connection And Cost Of Pipes, Specials And Soil Investigation All Complete For Augmentation Of Ground Based Water Supply Scheme At Palashipara to Accommodate FHTC Under Tehatta Sub-Divn Under Nadia Divn, PHE Dte |  |  | BILL/00218/2024-2025 | 131/PFMS | 27/07/2024 | 27/07/2024 | GHOSH ENTERPRISE | 25.43 | 0 | 0 | 0
10 | NADIA |  | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION OF PALASHIPARA PWSS BLOCK: TEHATTA-II DISTRICT: NADIA | SM/10691 | Augmentation | Supply, delivery, installation Commissioning of Electro Mechanical Equipments and allied works at PALASHIPARA W/S Scheme Block- Tehatta-II under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia. [SM/10691] | Assistant Engineer |  | ORD/000139/2025-2026 | 1140/EMD | 04/06/2025 | 02/09/2025 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 52.38 | 0 | 0 | 0
11 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION OF PALASHIPARA PWSS BLOCK: TEHATTA-II DISTRICT: NADIA | SM/10691 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Rising main with Inter-Connection in between Tube wells including specials and valves, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (Schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc., Construction of 400 cum capacity 20 mtr. staging height RCC Over Head Reservoir (including pile Foundation), pipe connection and cost of pipes, specials and Soil investigation all complete for Augmentation of Ground Based Water Supply Scheme at Palashipara to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000202/2022-2023 | 4412 /ND | 14/10/2022 | 01/02/2025 | GHOSH ENTERPRISE, B-2/183, KALYANI. P.O.& P.S. KALYANI, DIST.NADIA, PIN-741235,W.B | 514.08 | 0 | 0 | 95
12 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION OF PALASHIPARA PWSS BLOCK: TEHATTA-II DISTRICT: NADIA | SM/10691 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 120 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Palshipara to accommodate FHTC within Tehatta-II block under Tehatta Sub-division under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000092/2024-2025 | 4228/ND | 02/08/2024 | 29/01/2025 | B.M. ENGINEERING & CONSTRUCTION | 296.87 | 0 | 0 | 0
13 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION OF PALASHIPARA PWSS BLOCK: TEHATTA-II DISTRICT: NADIA | SM/10691 | Augmentation | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 11/10/2025 | IMAGIN | 96.97 | 0 | 0 | 0
14 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION OF PALASHIPARA PWSS BLOCK: TEHATTA-II DISTRICT: NADIA | SM/10691 | Augmentation | Construction Of Pump House (3.6x 3.0m) Including Sanitary Arrangement and Consruction of Boundary wall at 3rd Tube well Site at Palashipara Water Supply Scheme Under Tehatta Sub-Division PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000668/2023-2024 | 1100/ND | 19/02/2024 | 13/02/2025 | ROY CONSTRUCTION | 11.29 | 0 | 0 | 90
15 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION OF PALASHIPARA PWSS BLOCK: TEHATTA-II DISTRICT: NADIA | SM/10691 | Augmentation | Laying distribution system for Augmentation of Ground Water Based Pipe Water supply scheme at Palashipara PWSS [Part-B] of Under Tehatta Sub-Division under under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000809/2023-2024 | 1914/ND | 15/03/2024 | 07/03/2025 | GHOSH ENTERPRISE | 66.07 | 0 | 0 | 20
Total | [13 empty] | 1249.76 | 0 | 0