## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | EXTENSION OF INTAKE STRUCTURE UNDER SURFACE WATER BASED WATER SUPPLY SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT (NORTHERN SECTOR) PART-II | SM/10692 | Augmentation | Survey, Design, Construction, Supply, Erection & Commissioning of Raw Water Intake Structure (Floating Barge type), Pump House for drawing 34.52 MLD raw water from the river Hooghly with all related accessories, Substation Building with Laying of 700mm dia. DI(K9) Raw Water Pipe Line from Intake Pump House and connecting to the existing raw water main (Approx. 3450 Mtr. length), River Bank Protection works, Boundary Wall, Internal Road and Surface Water Drainage system at the Intake point on EPC-turnkey basis including 3(Three) months trial run & 6 (Six) months defect liability period and 5 (Five) year subsequent Operation and Maintenance complete for the surface water based water supply scheme for arsenic affected Block of Nakashipara in the district Nadia under PHE Dte | Assistant Engineer | Junior Engineer 2,Junior Engineer 3 | ORD/000367/2023-2024 | 4774/ND | 16/10/2023 | 16/10/2024 | TRADERS AND ENGINEERS PRIVATE LIMITED | 1551.6 | 672.95 | 43.37 | 7
2 | NADIA |  | Eastern Mechanical | EXTENSION OF INTAKE STRUCTURE UNDER SURFACE WATER BASED WATER SUPPLY SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT (NORTHERN SECTOR) PART-II | SM/10692 | Augmentation | Dismantling the existing Electro-Mechanical system from Barge and re-installation on the newly constructed Barge by providing axially split casing pumping machinery for the Surface based water supply scheme for Arsenic affected block of Nakashipara in the district of Nadia. | Assistant Engineer |  | ORD/000064/2024-2025 | 1541/EMD | 12/06/2024 | 12/12/2024 | TRADERS & ENGINEERS PVT. LTD. | 108.54 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | EXTENSION OF INTAKE STRUCTURE UNDER SURFACE WATER BASED WATER SUPPLY SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT (NORTHERN SECTOR) PART-II | SM/10692 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000006/2024-2025 | 6973/ND | 21/11/2024 | 21/11/2024 | Resource Division | 356.75 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | EXTENSION OF INTAKE STRUCTURE UNDER SURFACE WATER BASED WATER SUPPLY SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT (NORTHERN SECTOR) PART-II | SM/10692 | Augmentation | Repairing of HDPE pipeline at raw water rising main at Kashiadanga Intake point site, Gotpara site & Bypass connection system for different OHR site including with all necessary specials, valves all complete for Northern Sector Part-II under Nakashipara Block of Nadia District under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000140/2025-2026 | 2976/ND | 25/06/2025 | 22/12/2025 | BANERJEE CONSTRUCTION | 22.06 | 0 | 0 | 20
Total | [13 empty] | 2038.95 | 672.95 | 33