## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Jalangi Zone-X-A PWSS to accommodate FHTC in Karimpur-II Block under Tehatta Sub-Division of Nadia Division in Nadia District. | SM/10715 | Augmentation | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Karimpur-Jalangi Z-10A W/S Scheme in Karimpur-II Block of Nadia District under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000406/2021-2022 | 320/TSD | 24/11/2021 | 24/12/2021 | RADIANT | 2.66 | 2.66 | 100 | 100
2 | NADIA |  | Central Drilling | Augmentation of Ground Water Based Jalangi Zone-X-A PWSS to accommodate FHTC in Karimpur-II Block under Tehatta Sub-Division of Nadia Division in Nadia District. | SM/10715 | Augmentation | PROVIDING 300MM NOMINAL DIA UPVC PIPE CONFIRMING TO IS:12818:2010 AND OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL KARIMPUR-I BLOCK UNDER NADIA DIVISION CMSD-II (D), CDD PHE DTE | Driller In Charge | Junior Engineer | ORD/000130/2022-2023 | 287/CMSD -II (D) | 01/06/2022 | 16/06/2022 | UNIVERSAL ENTERPRISES | 4.39 | 4.05 | 92.39 | 0
3 | NADIA |  | Central Drilling | Augmentation of Ground Water Based Jalangi Zone-X-A PWSS to accommodate FHTC in Karimpur-II Block under Tehatta Sub-Division of Nadia Division in Nadia District. | SM/10715 | Augmentation | PROVIDING 200MM NOMINAL DIA UPCVC PIPE CONFIRMING TO IS: 12818:2010 AND OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL KARIMPUR -II BLOCK UNDER NADIA DISTRICT CMSD-II(D) ,CDD PHE DTE |  |  | ORD/000131/2022-2023 | 282/ CMSD-II (D) | 01/06/2022 | 16/06/2022 | UNIVERSAL ENTERPRISES | 4.44 | 0.72 | 16.11 | 0
4 | NADIA |  | Central Drilling | Augmentation of Ground Water Based Jalangi Zone-X-A PWSS to accommodate FHTC in Karimpur-II Block under Tehatta Sub-Division of Nadia Division in Nadia District. | SM/10715 | Augmentation | PROVIDING DRILLING CREWS AND OTHER MATERIALS FOR CONSTRUTION OF TUBE WELL 300 MM X 200MM X250 MTR DEPTH BY DEPARTMENTAL RIG MACHINE FOR KARIMPUR -II BLOCK UNDER NADIA DIST, CMSD-II(D) ,CDD,PHE DTE | Driller In Charge | Junior Engineer | ORD/000132/2022-2023 | 280/CMSD-II (D) | 01/06/2022 | 16/06/2022 | UNIVERSAL ENTERPRISES | 3.52 | 3.52 | 100 | 0
5 | NADIA |  | Central Drilling | Augmentation of Ground Water Based Jalangi Zone-X-A PWSS to accommodate FHTC in Karimpur-II Block under Tehatta Sub-Division of Nadia Division in Nadia District. | SM/10715 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 150 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR JALANGI W/S SCH, KARIMPUR-I BLOCK UNDER NADIA DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000316/2022-2023 | 1198/CDD | 11/11/2022 | 11/12/2022 | DIPALI CONSTUCTION | 10.17 | 7.44 | 73.11 | 0
6 | NADIA |  | Central Drilling | Augmentation of Ground Water Based Jalangi Zone-X-A PWSS to accommodate FHTC in Karimpur-II Block under Tehatta Sub-Division of Nadia Division in Nadia District. | SM/10715 | Augmentation | SUPPLY & DELIVERY OF PEA SIZE GRAVELS AT SITE FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 150 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR JALANGI W/S SCH, NADIA DISTRICT UNDER CMSD-II(D), CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000329/2022-2023 | 536/CMSD-II | 02/12/2022 | 12/12/2022 | DIPALI CONSTUCTION | 0.98 | 0.74 | 75.74 | 0
7 | NADIA |  | Central Drilling | Augmentation of Ground Water Based Jalangi Zone-X-A PWSS to accommodate FHTC in Karimpur-II Block under Tehatta Sub-Division of Nadia Division in Nadia District. | SM/10715 | Augmentation | SUPPLY & DELIVERY OF PEA SIZE GRAVELS AT SITE FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 150 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR JALANGI W/S SCH NADIA DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000350/2022-2023 | 542/CMSD-II | 07/12/2022 | 17/12/2022 | ASHUTOSH DAS & CO | 0.98 | 0.7 | 71.71 | 0
8 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Jalangi Zone-X-A PWSS to accommodate FHTC in Karimpur-II Block under Tehatta Sub-Division of Nadia Division in Nadia District. | SM/10715 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000073/2023-2024 | 2295/ND | 29/05/2023 | 29/05/2023 | Resource Division | 11.4 | 0 | 0 | 0
9 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Jalangi Zone-X-A PWSS to accommodate FHTC in Karimpur-II Block under Tehatta Sub-Division of Nadia Division in Nadia District. | SM/10715 | Augmentation | Supply, Delivery Installation of Submersible Pumping Machinery alongwith allied Electro Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. rejuvenation to Accomodate FHTC at Pump House No. I , II under KARIMPUR JALANGI Zone X A WS Scheme, Block Karimpur-II, Dist. Nadia. NIET No.- 23 of EE/EMD of 2022-23 (Sl. No.-14) | Assistant Engineer | Junior Engineer | ORD/000894/2022-2023 | 162/EMD | 06/01/2023 | 05/02/2023 | S.B.ENTERPRISE | 9.73 | 8.78 | 90.26 | 70
10 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Jalangi Zone-X-A PWSS to accommodate FHTC in Karimpur-II Block under Tehatta Sub-Division of Nadia Division in Nadia District. | SM/10715 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed Augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Karimpur Jalangi Zone X-A to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000344/2022-2023 | 254/ND | 16/01/2023 | 05/01/2025 | SANJUKTA ENGINEERS | 157.12 | 108.69 | 69.17 | 98
11 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Jalangi Zone-X-A PWSS to accommodate FHTC in Karimpur-II Block under Tehatta Sub-Division of Nadia Division in Nadia District. | SM/10715 | Augmentation | Sinking of 01 nos Tubewell 300 x 200 mm dia and 200 mtr. Deep Tubewell by Direct Rotary Rig Method, having 300 mm dia 48 mtr. long PVC Housing Pipe & 200 mm.dia Well Pipe & Deep well Screen (RDS strainer) at 1ST Tube well Site Karimpur Jalangi-X(A) PWSS Water Supply Scheme under Tehatta Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000320/2024-2025 | 6975/ND | 21/11/2024 | 21/03/2025 | GENUINE | 17.56 | 0 | 0 | 100
Total | [13 empty] | 222.94 | 137.3 | 61.58